## BASE
BASE — LISTAS DE VALIDACAO (fonte unica de opcoes) ¦ adicione itens no fim de cada tabela que os menus atualizam sozinhos | [10 empty] | NOMENCLATURA DE ARQUIVOS
DISCIPLINA | TIPO / SUBSISTEMA | AREA | REV | AUDIT STATUS | RVT TYPE APROVAL | VERSION | RESPONSAVEL | ESTIMATED DELIVERY | EMPRESA | CODE | Padrao: | CPQ11-[DISCIPLINA]-[TIPO]-[AREA]-[REV].rvt
ARCH | ALUF | C12A | R22 | APPROVED | R22 | N/A | ALINNE | DONE | ALTAMIRA | 0000 | Exemplo: | CPQ11-ARCH-FENC-SITE-R24.rvt
BASM | ARCH | C345 | R23 | PREVIOUSLY APPROVED | R24 | NOT PUBLISHED | CAROL | ON HOLD | ARE ARQUITETURA | 1130 | (?) = sugestao nossa; revise conforme o padrao oficial do projeto.
CIVL | BLPR | DATA | R24 | REPROVED | N/A | V1 | FLAVIO | NOT PUBLISHED | AUTOBRÁS | 1116
DALI | CEIL | GUAR | R25 | IMPROPER | NOT PUBLISHED | V2 | GUI | N/A | BLACKBOX | 1114 | CAMPO | DESCRICAO | TIPO / SUBSISTEMA | SIGNIFICADO
DASM | CHAI | PUMP | R26 | OUTDATED |  | V3 | INGRYD |  | CADBIM | 1128 | CPQ11 | Codigo do projeto (fixo em todos os arquivos) | ALUF | Esquadrias de aluminio (?)
ELEC | COMN | SITE |  | NEXT ROUND |  | V4 | LUIZA |  | CONTRACTING | 0000 | DISCIPLINA | Disciplina do modelo (ver tabela DISCIPLINA) | ARCH | Arquitetura (geral)
EPMS | CONC | UTLS |  | ANALYSING |  | V5 | NICOLE |  | FCH | 1126 | TIPO | Subsistema / elemento (ver tabela TIPO) | BLPR | (?) revisar
FALM | DEVS |  |  | NOT PUBLISHED |  | V6 | SOPHIA |  | FERNANDES | 1121 | AREA | Localizacao no site (ver tabela AREA) | CEIL | Forro (Ceiling)
FPRT | DIES |  |  | N/A |  | V7 | YASMIN |  | FM SECURITY | 0000 | REV | Revisao / release do projeto (ver tabela REV) | CHAI | (?) revisar
LAND | DPF1 |  |  |  |  | V8 | N/A |  | GARCIA | 1119 | .rvt | Arquivo do Autodesk Revit | COMN | Comunicacao (?)
MECH | DPF2 |  |  |  |  | V9 |  |  | GEOFIX | 1122 |  |  | CONC | Concreto
PLMB | DPFN |  |  |  |  | V10 |  |  | GEOFIX/TECNOGEO | 0000 | DISCIPLINA | SIGNIFICADO | DEVS | Dispositivos (Devices)
ROIP | DRNG |  |  |  |  | V11 |  |  | IB TECH | 1113 | ARCH | Arquitetura | DIES | Diesel / Gerador (?)
SCTY | ELEC |  |  |  |  | V12 |  |  | IDEIA DRYWALL | 1101 | BASM | Subsolo / Basement (?) | DPF1 | (?) revisar
STRC | ERTH |  |  |  |  | V13 |  |  | INOVAGLASS | 1109 | CIVL | Civil | DPF2 | (?) revisar
SYST | FACD |  |  |  |  | V14 |  |  | ITS | 1107 | DALI | Iluminacao/controle DALI (?) | DPFN | (?) revisar
TCOM | FALM |  |  |  |  | V15 |  |  | MADEPISO | 0000 | DASM | (?) revisar | DRNG | Drenagem (Drainage)
| FENC |  |  |  |  | V16 |  |  | MEGADOORS | 1108 | ELEC | Eletrica | ELEC | Eletrica
| FLOO |  |  |  |  | V17 |  |  | MENDES HOLLER | 1112 | EPMS | Electrical Power Monitoring System | ERTH | Aterramento (Earthing)
| FNSH |  |  |  |  | V18 |  |  | MENDES HOLLER, IDEIA, SERV OBRAS | 1111 | FALM | Alarme de incendio (Fire Alarm) | FACD | Fachada (Facade)
| FPRT |  |  |  |  | V19 |  |  | METASA | 1125 | FPRT | Combate a incendio (Fire Protection) | FALM | Alarme de incendio
| FURN |  |  |  |  | V20 |  |  | MODAX | 1121 | LAND | Paisagismo (Landscape) | FENC | Cerca / Alambrado (Fence)
| GATE |  |  |  |  | V21 |  |  | OMNITRADE | 1110 | MECH | Mecanica / HVAC | FLOO | Piso (Floor)
| HM90 |  |  |  |  | V22 |  |  | ORGANISMO VIVO | 0000 | PLMB | Hidraulica (Plumbing) | FNSH | Acabamentos (Finishes)
| HMET |  |  |  |  | V23 |  |  | PETROTANQUE | 1117 | ROIP | Radio over IP / Comunicacao (?) | FPRT | Combate a incendio
| INFR |  |  |  |  | V24 |  |  | PGMAK | 1129 | SCTY | Seguranca (Security) | FURN | Mobiliario (Furniture)
| LAND |  |  |  |  | V25 |  |  | PMD | 0000 | STRC | Estrutura (Structural) | GATE | Portao (Gate)
| LOCK |  |  |  |  | V26 |  |  | RACIONAL | 1106 | SYST | Sistemas (Systems) | HM90 | (?) revisar
| MECH |  |  |  |  | V27 |  |  | RBV | 0000 | TCOM | Telecomunicacoes | HMET | Serralheria / metalica (?)
| METK |  |  |  |  | V28 |  |  | SEGURPRO | 1115 |  |  | INFR | Infraestrutura
| METL |  |  |  |  | V29 |  |  | SERCOP | 1103 |  |  | LAND | Paisagismo
| NEWJ |  |  |  |  | V30 |  |  | SERCOP, SERV OBRAS | 1124 | AREA | SIGNIFICADO | LOCK | Fechadura / controle de acesso (?)
| NPWT |  |  |  |  | V31 |  |  | SERV OBRAS | 1120 | C12A | Colocation 1-2 (?) | MECH | Mecanica
| OHCD |  |  |  |  | V32 |  |  | SMVIDROS | 1102 | C345 | Colocation 3-4-5 (?) | METK | (?) revisar
| PART |  |  |  |  | V33 |  |  | SPBIM | 1127 | DATA | Data Hall / Sala de dados | METL | Metalica (Metal)
| PAVM |  |  |  |  | V34 |  |  | STARCENTER | 1118 | GUAR | Guarita (Guardhouse) | NEWJ | (?) revisar
| PLMB |  |  |  |  | V35 |  |  | STEINER | 0000 | PUMP | Casa de bombas (Pump House) | NPWT | (?) revisar
| ROOF |  |  |  |  | V36 |  |  | STONE | 0000 | SITE | Terreno / Geral (Site) | OHCD | (?) revisar
| SGNH |  |  |  |  | V37 |  |  | S-VALE | 1104 | UTLS | Utilidades (Utilities) | PART | Divisorias (Partition)
| SGNV |  |  |  |  | V38 |  |  | T2B | 0000 |  |  | PAVM | Pavimentacao (Pavement)
| SHLV |  |  |  |  | V39 |  |  | TECNOGEO | 1123 |  |  | PLMB | Hidraulica
| SIGN |  |  |  |  | V40 |  |  | TENAX | 0000 | REV | SIGNIFICADO | ROOF | Cobertura (Roof)
| SPDA |  |  |  |  | V41 |  |  | VISUAL GEAC | 0000 | R22 | Revisao / Release 22 | SGNH | Sinalizacao horizontal (?)
| STON |  |  |  |  | V42 |  |  | ZEUS/PORTEX | 1105 | R23 | Revisao / Release 23 | SGNV | Sinalizacao vertical (?)
| WMES |  |  |  |  | V43 |  |  |  |  | R24 | Revisao / Release 24 | SHLV | Prateleiras (Shelving) (?)
| WOOD |  |  |  |  | V44 |  |  |  |  | R25 | Revisao / Release 25 | SIGN | Sinalizacao (Signage)
| WTRP |  |  |  |  | V45 |  |  |  |  | R26 | Revisao / Release 26 | SPDA | SPDA / Para-raios
[6 empty] | V46 | [6 empty] | STON | Pedra (Stone)
[6 empty] | V47 | [6 empty] | WMES | Tela / malha (Wire Mesh) (?)
[6 empty] | V48 | [6 empty] | WOOD | Madeira (Wood)
[6 empty] | V49 | [6 empty] | WTRP | Impermeabilizacao (Waterproofing)
V50
V51
V52
V53
V54
V55
V56
V57
V58
V59
V60

## LOD 500 - CONTROL
SPECIFIC AUDIT CONTROL ¦ LOD 500
| META DO DIA 17/07 | [28 empty] | ADMN | [26 empty] | COLO1 | [26 empty] | COLO2 | [22 empty] | COLO3 | [16 empty] | SITE | [22 empty] | GUAR | [26 empty] | UTLS | [28 empty] | WASTE SHED
| FILE NAME (R24) | FILE NAME (R22) | AREA | TRADE COMPANY | CODE | BIM COMPANY | CODE | ACC VERSION (R22) | ACC FILE DATE (R22) | ACC VERSION (R24) | ACC FILE DATE (R24) | VERSION (ADMN/GUAR) | FILE DATE (ADMN/GUAR) | RVT TYPE APROVAL (ADMN/GUAR) | VERSION (COLO1) | FILE DATE (COLO1) | RVT TYPE APROVAL (COLO1) | VERSION (COLO2/SITE) | FILE DATE (COLO2/SITE) | RVT TYPE APROVAL (COLO2/SITE) | VERSION COLO3 | FILE DATE COLO3 | RVT TYPE APROVAL (COLO3) | UTLS VERSION | UTLS FILE DATE | RVT TYPE APROVAL (UTLS) | WASTE SHED VERSION | WASTE SHED FILE DATE | RVT TYPE APROVAL (WASTE SHED) | R0- APPROVAL (%) | R1- APPROVAL (%) | R2- APPROVAL (%) | R3- APPROVAL (%) | R4- APPROVAL (%) | R5- APPROVAL (%) | R6- APPROVAL (%) | R7- APPROVAL (%) | R8- APPROVAL (%) | R9- APPROVAL (%) | R10- APPROVAL (%) | R11- APPROVAL (%) | R12- APPROVAL (%) | R13- APPROVAL (%) | R14- APPROVAL (%) | R15- APPROVAL (%) | R16- APPROVAL (%) | R17- APPROVAL (%) | R18- APPROVAL (%) | R19- APPROVAL (%) | R20- APPROVAL (%) | R21- APPROVAL (%) | R22- APPROVAL (%) | R23- APPROVAL (%) | R24- APPROVAL (%) | R25- APPROVAL (%) | GERAL ADMN | R0- APPROVAL (%) | R1- APPROVAL (%) | R2- APPROVAL (%) | R3- APPROVAL (%) | R4- APPROVAL (%) | R5- APPROVAL (%) | R6- APPROVAL (%) | R7- APPROVAL (%) | R8- APPROVAL (%) | R9- APPROVAL (%) | R10- APPROVAL (%) | R11- APPROVAL (%) | R12- APPROVAL (%) | R13- APPROVAL (%) | R14- APPROVAL (%) | R15- APPROVAL (%) | R16- APPROVAL (%) | R17- APPROVAL (%) | R18- APPROVAL (%) | R19- APPROVAL (%) | R20- APPROVAL (%) | R21- APPROVAL (%) | R22- APPROVAL (%) | R23- APPROVAL (%) | R24- APPROVAL (%) | R25- APPROVAL (%) | GERAL COL1 | R0- APPROVAL (%) | R1- APPROVAL (%) | R2- APPROVAL (%) | R3- APPROVAL (%) | R4- APPROVAL (%) | R5- APPROVAL (%) | R6- APPROVAL (%) | R7- APPROVAL (%) | R8- APPROVAL (%) | R9- APPROVAL (%) | R10- APPROVAL (%) | R11- APPROVAL (%) | R12- APPROVAL (%) | R13- APPROVAL (%) | R14- APPROVAL (%) | R15- APPROVAL (%) | R16- APPROVAL (%) | R17 - APPROVAL (%) | R18 - APPROVAL (%) | R19 - APPROVAL (%) | R20 - APPROVAL (%) | R21 - APPROVAL (%) | GERAL COL2 | R0- APPROVAL (%) | R1- APPROVAL (%) | R2- APPROVAL (%) | R3- APPROVAL (%) | R4- APPROVAL (%) | R5- APPROVAL (%) | R6- APPROVAL (%) | R7- APPROVAL (%) | R8- APPROVAL (%) | R9- APPROVAL (%) | R10- APPROVAL (%) | R11- APPROVAL (%) | R12- APPROVAL (%) | R13- APPROVAL (%) | R14- APPROVAL (%) | R15- APPROVAL (%) | GERAL COL3 | R0- APPROVAL (%) | R1- APPROVAL (%) | R2- APPROVAL (%) | R3- APPROVAL (%) | R4- APPROVAL (%) | R5- APPROVAL (%) | R6- APPROVAL (%) | R7- APPROVAL (%) | R8- APPROVAL (%) | R9- APPROVAL (%) | R10- APPROVAL (%) | R11- APPROVAL (%) | R12- APPROVAL (%) | R13- APPROVAL (%) | R14- APPROVAL (%) | R15- APPROVAL (%) | R16- APPROVAL (%) | R17- APPROVAL (%) | R18- APPROVAL (%) | R19- APPROVAL (%) | R20- APPROVAL (%) | R21- APPROVAL (%) | GERAL SITE | R0 - APPROVAL (%) | R1 - APPROVAL (%) | R2 - APPROVAL (%) | R3- APPROVAL (%) | R4- APPROVAL (%) | R5- APPROVAL (%) | R6- APPROVAL (%) | R7- APPROVAL (%) | R8- APPROVAL (%) | R9- APPROVAL (%) | R10- APPROVAL (%) | R11- APPROVAL (%) | R12- APPROVAL (%) | R13- APPROVAL (%) | R14- APPROVAL (%) | R15- APPROVAL (%) | R16- APPROVAL (%) | R17- APPROVAL (%) | R18- APPROVAL (%) | R19- APPROVAL (%) | R20- APPROVAL (%) | R21- APPROVAL (%) | R22- APPROVAL (%) | R23- APPROVAL (%) | R24- APPROVAL (%) | R25- APPROVAL (%) | GERAL GUAR | R0 - APPROVAL (%) | R1 - APPROVAL (%) | R2 - APPROVAL (%) | R3 - APPROVAL (%) | R4 - APPROVAL (%) | R5 - APPROVAL (%) | R6 - APPROVAL (%) | R7 - APPROVAL (%) | R8 - APPROVAL (%) | R9 - APPROVAL (%) | R10- APPROVAL (%) | R11- APPROVAL (%) | R12- APPROVAL (%) | R13- APPROVAL (%) | R14- APPROVAL (%) | R15- APPROVAL (%) | R16- APPROVAL (%) | R17- APPROVAL (%) | R18- APPROVAL (%) | R19- APPROVAL (%) | R20- APPROVAL (%) | R21- APPROVAL (%) | R22- APPROVAL (%) | R23- APPROVAL (%) | R24- APPROVAL (%) | R25- APPROVAL (%) | R26- APPROVAL (%) | R27- APPROVAL (%) | GERAL UTLS | R0 - APPROVAL (%) | R1 - APPROVAL (%) | R2 - APPROVAL (%) | R3 - APPROVAL (%) | R4 - APPROVAL (%) | R5 - APPROVAL (%) | R6 - APPROVAL (%) | R7 - APPROVAL (%) | R8 - APPROVAL (%) | R9 - APPROVAL (%) | R10 - APPROVAL (%) | R11 - APPROVAL (%) | R12 - APPROVAL (%) | R13 - APPROVAL (%) | R14 - APPROVAL (%) | R15 - APPROVAL (%) | GERAL WASTE
1 | ARCH ¦ ARCHITECTURE
2 | CPQ11-ARCH-ARCH-DATA-R24.rvt | CPQ11-ARCH-ARCH-DATA-R22.rvt | DATA | ARE ARQUITETURA | 1130 | ARE ARQUITETURA | 1130 | V29 | 13/04/2026 | V3 | 03/06/2026 | V3 | 2026-06-03 | R24 | V3 | 2026-06-03 | R24 | V3 | 2026-06-03 | R24 | V3 | 2026-06-03 | R24 | N/A | N/A | N/A | N/A | N/A | N/A | 1% | IMPROPER | OUTDATED | OUTDATED | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | 16% | OUTDATED | NEXT ROUND | 23% | OUTDATED | OUTDATED | OUTDATED | OUTDATED | NEXT ROUND | NEXT ROUND | 31% | IMPROPER | OUTDATED | OUTDATED | OUTDATED | OUTDATED | OUTDATED | 31% | 1% | IMPROPER | OUTDATED | 39.39% | NEXT ROUND | 42% | OUTDATED | OUTDATED | 42% | NEXT ROUND | 61% | NEXT ROUND | 85% | OUTDATED | OUTDATED | OUTDATED | OUTDATED | NEXT ROUND | NEXT ROUND | 85% | IMPROPER | OUTDATED | OUTDATED | OUTDATED | OUTDATED | OUTDATED | 85% | 1% | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | 77% | OUTDATED | NEXT ROUND | NEXT ROUND | NEXT ROUND | 79% | OUTDATED | OUTDATED | NEXT ROUND | NEXT ROUND | IMPROPER | IMPROPER | OUTDATED | OUTDATED | OUTDATED | OUTDATED | OUTDATED | 79% | 0% | NEXT ROUND | NEXT ROUND | 1% | OUTDATED | OUTDATED | OUTDATED | NEXT ROUND | NEXT ROUND | IMPROPER | IMPROPER | OUTDATED | OUTDATED | OUTDATED | OUTDATED | OUTDATED | 1% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
3 | CPQ11-ARCH-ARCH-SITE-R24.rvt | CPQ11-ARCH-ARCH-SITE-R22.rvt | SITE | ARE ARQUITETURA | 1130 | ARE ARQUITETURA | 1130 | V28 | 17/04/2026 | V4 | 15/07/2026 | V3 | 03/06/2026 | R24 | N/A | N/A | N/A | V3 | 2026-06-03 | R24 | N/A | N/A | N/A | V3 | 2026-06-03 | R24 | V22 | 30/01/2026 | R22 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1% | NEXT ROUND | NEXT ROUND | NEXT ROUND | 5% | OUTDATED | OUTDATED | NEXT ROUND | 71% | NEXT ROUND | NEXT ROUND | NEXT ROUND | 71% | NEXT ROUND | NEXT ROUND | 82% | IMPROPER | OUTDATED | OUTDATED | OUTDATED | OUTDATED | NEXT ROUND | 82% | NEXT ROUND | 1% | OUTDATED | 1% | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | 11% | OUTDATED | OUTDATED | NEXT ROUND | NEXT ROUND | 60% | OUTDATED | OUTDATED | OUTDATED | NEXT ROUND | NEXT ROUND | IMPROPER | IMPROPER | OUTDATED | OUTDATED | OUTDATED | OUTDATED | NEXT ROUND | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 1% | 44% | NEXT ROUND | NEXT ROUND | 83% | OUTDATED | OUTDATED | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | 83% | IMPROPER | OUTDATED | OUTDATED | OUTDATED | OUTDATED | NEXT ROUND | 83% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
8 | CPQ11-ARCH-FENC-SITE-R24.rvt | CPQ11-ARCH-FENC-SITE-R22.rvt | SITE | SERCOP | 1103 | ARE ARQUITETURA | 1130 | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | N/A | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | N/A | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED
9 | CPQ11-ARCH-METL-SITE-R24.rvt | CPQ11-ARCH-METL-SITE-R22.rvt | SITE | SERCOP | 1103 | ARE ARQUITETURA | 1130 | V12 | 05/05/2026 | V5 | 22/06/2026 | V5 | 2026-06-22 | R24 | N/A | N/A | N/A | V5 | 2026-06-22 | R24 | N/A | N/A | N/A | V5 | 07/01/2026 | R22 | V7 | 20/02/2026 | R22 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1% | NEXT ROUND | NEXT ROUND | NEXT ROUND | 23.68% | NEXT ROUND | 36.8% | NEXT ROUND | 39% | 39% | OUTDATED | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | 39% | NEXT ROUND | NEXT ROUND | NEXT ROUND | 63% | 63% | 1% | NEXT ROUND | 1% | OUTDATED | OUTDATED | NEXT ROUND | NEXT ROUND | NEXT ROUND | 31% | NEXT ROUND | 30% | NEXT ROUND | 90% | NEXT ROUND | NEXT ROUND | 90% | NEXT ROUND | NEXT ROUND | NEXT ROUND | IMPROPER | IMPROPER | 90% | NEXT ROUND | NEXT ROUND | 100% | 100% | 100% | 1% | IMPROPER | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 1% | NEXT ROUND | NEXT ROUND | NEXT ROUND | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
10 | CPQ11-ARCH-WOOD-DATA-R24.rvt | CPQ11-ARCH-WOOD-DATA-R22.rvt | DATA | MADEPISO | 0000 | MADEPISO | 0000 | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | N/A | N/A | N/A | N/A | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
11 | CPQ11-ARCH-HMET-DATA-R24.rvt | CPQ11-ARCH-HMET-DATA-R22.rvt | DATA | S-VALE | 1104 | SPBIM | 1127 | V12 | 08/04/2026 | V1 | 15/05/2026 | V10 | 26/01/2026 | R22 | V10 | 26/01/2026 | R22 | V11 | 2026-04-01 | R22 | V12 | 2026-04-08 | R22 | N/A | N/A | N/A | N/A | N/A | N/A | 1% | NEXT ROUND | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | NEXT ROUND | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
12 | CPQ11-ARCH-HMET-SITE-R24.rvt | CPQ11-ARCH-HMET-SITE-R22.rvt | SITE | S-VALE | 1104 | SPBIM | 1127 | V9 | 10/04/2026 | V1 | 15/05/2026 | V7 | 2026-03-17 | R22 | N/A | N/A | N/A | V9 | 2026-04-10 | R22 | N/A | N/A | N/A | V7 | 2026-03-17 | R22 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | NEXT ROUND | NEXT ROUND | NEXT ROUND | 0% | NEXT ROUND | NEXT ROUND | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | NEXT ROUND | 1% | OUTDATED | OUTDATED | OUTDATED | OUTDATED | OUTDATED | OUTDATED | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 1% | IMPROPER | 1% | NEXT ROUND | NEXT ROUND | NEXT ROUND | 1% | OUTDATED | OUTDATED | OUTDATED | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
13 | CPQ11-ARCH-HM90-DATA-R24.rvt | CPQ11-ARCH-HM90-DATA-R22.rvt | DATA | ZEUS/PORTEX | 1105 | SPBIM | 1127 | V9 | 27/03/2026 | V2 | 26/06/2026 | V7 | 23/01/2026 | R22 | V7 | 23/01/2026 | R22 | V8 | 18/02/2026 | R22 | V1 | 2026-05-15 | R24 | N/A | N/A | N/A | N/A | N/A | N/A | 1% | NEXT ROUND | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | NEXT ROUND | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | 100% | 100% | 100% | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
14 | CPQ11-ARCH-WMES-DATA-R24.rvt | CPQ11-ARCH-WMES-DATA-R22.rvt | DATA | S-VALE | 1104 | SPBIM | 1127 | V13 | 02/03/2026 | V3 | 24/06/2026 | V13 | 02/03/2026 | R22 | V13 | 2026-01-23 | R22 | V13 | 2026-01-23 | R22 | V24 | 2026-05-29 | R24 | N/A | N/A | N/A | N/A | N/A | N/A | 1% | NEXT ROUND | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | NEXT ROUND | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | 100% | 100% | 100% | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
15 | CPQ11-ARCH-CHAI-SITE-R24.rvt | CPQ11-ARCH-CHAI-SITE-R22.rvt | SITE | S-VALE | 1104 | SPBIM | 1127 | V12 | 06/04/2026 | V1 | 15/05/2026 | N/A | N/A | N/A | N/A | N/A | N/A | V12 | 2026-04-06 | R24 | N/A | N/A | N/A | V10 | 23/12/2025 | R24 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | NEXT ROUND | NEXT ROUND | NEXT ROUND | 0% | NEXT ROUND | NEXT ROUND | OUTDATED | 50% | OUTDATED | OUTDATED | OUTDATED | OUTDATED | OUTDATED | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | ANALYSING | 50% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1% | IMPROPER | 1% | OUTDATED | OUTDATED | OUTDATED | OUTDATED | OUTDATED | OUTDATED | OUTDATED | OUTDATED | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | ANALYSING | 1% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
16 | CPQ11-ARCH-FURN-DATA-R24.rvt | CPQ11-ARCH-FURN-DATA-R22.rvt | DATA | RACIONAL | 1106 | CONTRACTING | 0000 | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | N/A | N/A | N/A | N/A | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
18 | CPQ11-ARCH-WTRP-DATA-R24.rvt | CPQ11-ARCH-WTRP-DATA-R22.rvt | DATA | ITS | 1107 | RBV | 0000 | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | N/A | N/A | N/A | N/A | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
19 | CPQ11-ARCH-WTRP-SITE-R24.rvt | CPQ11-ARCH-WTRP-SITE-R22.rvt | SITE | ITS | 1107 | RBV | 0000 | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | N/A | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | N/A | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED
20 | CPQ11-ARCH-OHCD-DATA-R24.rvt | CPQ11-ARCH-OHCD-DATA-R22.rvt | DATA | MEGADOORS | 1108 | SPBIM | 1127 | V4 | 10/04/2026 | V2 | 04/06/2026 | V4 | 2026-04-10 | R22 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | 0% | NEXT ROUND | NEXT ROUND | NEXT ROUND | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
21 | CPQ11-ARCH-BLPR-GUAR-R24.rvt | CPQ11-ARCH-BLPR-GUAR-R22.rvt | GUAR | INOVAGLASS | 1109 | INOVAGLASS | 1109 | V9 | 04/12/2025 | V1 | 20/05/2026 | V1 | 2026-05-20 | R24 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1% | OUTDATED | OUTDATED | OUTDATED | OUTDATED | OUTDATED | OUTDATED | OUTDATED | OUTDATED | OUTDATED | OUTDATED | OUTDATED | OUTDATED | OUTDATED | OUTDATED | OUTDATED | OUTDATED | NEXT ROUND | NEXT ROUND | IMPROPER | OUTDATED | OUTDATED | OUTDATED | OUTDATED | OUTDATED | OUTDATED | 1% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
22 | CPQ11-ARCH-FACD-DATA-R24.rvt | CPQ11-ARCH-FACD-DATA-R22.rvt | DATA | OMNITRADE | 1110 | CADBIM | 1128 | V25 | 06/05/2026 | V3 | 07/07/2026 | V22 | 2026-03-19 | R22 | V22 | 2026-03-19 | R22 | V23 | 2026-03-27 | R22 | V3 | 2026-07-07 | R24 | N/A | N/A | N/A | N/A | N/A | N/A | 1% | IMPROPER | NEXT ROUND | 1% | NEXT ROUND | NEXT ROUND | 11% | NEXT ROUND | 55% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 1% | IMPROPER | 33.3% | 33.3% | 66% | OUTDATED | 66% | NEXT ROUND | 66% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 1% | OUTDATED | NEXT ROUND | IMPROPER | NEXT ROUND | 40% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 1% | NEXT ROUND | NEXT ROUND | 1% | OUTDATED | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | IMPROPER | OUTDATED | NEXT ROUND | 46% | 46% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
23 | CPQ11-ARCH-ROOF-DATA-R24.rvt | CPQ11-ARCH-ROOF-DATA-R22.rvt | DATA | OMNITRADE | 1110 | CADBIM | 1128 | V30 | 26/03/2026 | V2 | 20/05/2026 | V27 | 2026-02-02 | R22 | V26 | 2026-01-24 | R22 | V27 | 2026-02-02 | R22 | V30 | 2026-03-26 | R22 | N/A | N/A | N/A | N/A | N/A | N/A | 1% | IMPROPER | 20% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 1% | IMPROPER | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | NEXT ROUND | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
24 | CPQ11-ARCH-PART-SITE-R24.rvt | CPQ11-ARCH-PART-SITE-R22.rvt | SITE | IDEIA DRYWALL | 1101 | FCH | 1126 | V14 | 18/03/2026 | V2 | 17/06/2026 | V2 | 2026-06-17 | R24 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | V2 | 2026-06-17 | R24 | V13 | 13/11/2025 | R22 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1% | OUTDATED | OUTDATED | OUTDATED | OUTDATED | OUTDATED | OUTDATED | OUTDATED | NEXT ROUND | 1% | OUTDATED | OUTDATED | OUTDATED | OUTDATED | OUTDATED | OUTDATED | OUTDATED | IMPROPER | OUTDATED | OUTDATED | OUTDATED | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | ANALYSING | 1% | 1% | IMPROPER | IMPROPER | OUTDATED | OUTDATED | OUTDATED | 1% | OUTDATED | OUTDATED | OUTDATED | NEXT ROUND | 17% | OUTDATED | OUTDATED | OUTDATED | OUTDATED | OUTDATED | OUTDATED | OUTDATED | IMPROPER | OUTDATED | OUTDATED | OUTDATED | NEXT ROUND | IMPROPER | OUTDATED | OUTDATED | OUTDATED | 17% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
25 | CPQ11-ARCH-PART-C345-R24.rvt | CPQ11-ARCH-PART-C345-R22.rvt | C345 | IDEIA DRYWALL | 1101 | FCH | 1126 | V14 | 30/01/2026 | V1 | 19/05/2026 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | V1 | 19/05/2026 | R24 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 1% | OUTDATED | OUTDATED | OUTDATED | OUTDATED | OUTDATED | IMPROPER | OUTDATED | OUTDATED | OUTDATED | OUTDATED | OUTDATED | OUTDATED | OUTDATED | OUTDATED | 1% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
26 | CPQ11-ARCH-PART-C12A-R24.rvt | CPQ11-ARCH-PART-C12A-R22.rvt | C12A | IDEIA DRYWALL | 1101 | FCH | 1126 | V24 | 07/04/2026 | V2 | 27/05/2026 | V2 | 2026-05-27 | R24 | V2 | 2026-05-27 | R24 | V2 | 2026-05-27 | R24 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1% | IMPROPER | IMPROPER | IMPROPER | NEXT ROUND | NEXT ROUND | 13% | OUTDATED | OUTDATED | OUTDATED | OUTDATED | 22% | OUTDATED | OUTDATED | OUTDATED | OUTDATED | OUTDATED | IMPROPER | NEXT ROUND | NEXT ROUND | IMPROPER | 50% | OUTDATED | OUTDATED | OUTDATED | OUTDATED | 50% | 1% | IMPROPER | IMPROPER | IMPROPER | IMPROPER | IMPROPER | NEXT ROUND | 44.23% | OUTDATED | OUTDATED | OUTDATED | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | IMPROPER | IMPROPER | IMPROPER | 78% | OUTDATED | OUTDATED | OUTDATED | OUTDATED | 78% | 1% | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | 1% | OUTDATED | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | IMPROPER | IMPROPER | IMPROPER | OUTDATED | OUTDATED | OUTDATED | OUTDATED | OUTDATED | 1% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
27 | CPQ11-ARCH-COMN-DATA-R24.rvt | CPQ11-ARCH-COMN-DATA-R22.rvt | DATA | CONTRACTING | 0000 | CONTRACTING | 0000 | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | N/A | N/A | N/A | N/A | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
28 | CPQ11-ARCH-SGNV-SITE-R24.rvt | CPQ11-ARCH-SGNV-SITE-R22.rvt | SITE | VISUAL GEAC | 0000 | CONTRACTING | 0000 | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | N/A | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | N/A | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED
29 | CPQ11-ARCH-SGNH-SITE-R24.rvt | CPQ11-ARCH-SGNH-SITE-R22.rvt | SITE | CONTRACTING | 0000 | CONTRACTING | 0000 | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | N/A | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | N/A | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED
30 | CPQ11-ARCH-CEIL-DATA-R24.rvt | CPQ11-ARCH-CEIL-DATA-R22.rvt | DATA | IDEIA DRYWALL | 1101 | T2B | 0000 | V4 | 29/04/2026 | V1 | 04/06/2026 | V1 | 04/06/2026 | R24 | V1 | 04/06/2026 | R24 | V1 | 04/06/2026 | R24 | V1 | 04/06/2026 | R24 | N/A | N/A | N/A | N/A | N/A | N/A | IMPROPER | IMPROPER | IMPROPER | IMPROPER | OUTDATED | OUTDATED | NEXT ROUND | NEXT ROUND | 1% | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | IMPROPER | OUTDATED | OUTDATED | IMPROPER | OUTDATED | IMPROPER | OUTDATED | OUTDATED | OUTDATED | OUTDATED | OUTDATED | 1% | NEXT ROUND | 1% | OUTDATED | OUTDATED | OUTDATED | OUTDATED | IMPROPER | OUTDATED | OUTDATED | NEXT ROUND | IMPROPER | OUTDATED | OUTDATED | OUTDATED | NEXT ROUND | IMPROPER | OUTDATED | OUTDATED | IMPROPER | OUTDATED | IMPROPER | OUTDATED | OUTDATED | OUTDATED | OUTDATED | OUTDATED | 1% | 1% | OUTDATED | NEXT ROUND | NEXT ROUND | IMPROPER | NEXT ROUND | IMPROPER | OUTDATED | OUTDATED | OUTDATED | NEXT ROUND | IMPROPER | OUTDATED | OUTDATED | IMPROPER | OUTDATED | IMPROPER | OUTDATED | OUTDATED | OUTDATED | OUTDATED | OUTDATED | 1% | 0% | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | IMPROPER | OUTDATED | OUTDATED | OUTDATED | OUTDATED | OUTDATED | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
31 | CPQ11-ARCH-CEIL-SITE-R24.rvt | CPQ11-ARCH-CEIL-SITE-R22.rvt | SITE | IDEIA DRYWALL | 1101 | T2B | 0000 | V2 | 29/04/2026 | V1 | 12/06/2026 | V1 | 2026-06-12 | R24 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1% | OUTDATED | OUTDATED | OUTDATED | OUTDATED | OUTDATED | OUTDATED | OUTDATED | OUTDATED | OUTDATED | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | IMPROPER | IMPROPER | OUTDATED | OUTDATED | OUTDATED | OUTDATED | OUTDATED | 1% | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
32 | CPQ11-ARCH-SHLV-DATA-R24.rvt | CPQ11-ARCH-SHLV-DATA-R22.rvt | DATA | ALTAMIRA | 0000 | ALTAMIRA | 0000 | V9 | 28/02/2026 | V1 | 20/05/2026 | V1 | 2026-05-20 | R24 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1% | OUTDATED | OUTDATED | OUTDATED | OUTDATED | OUTDATED | 8% | OUTDATED | OUTDATED | OUTDATED | OUTDATED | OUTDATED | OUTDATED | OUTDATED | OUTDATED | OUTDATED | OUTDATED | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | IMPROPER | OUTDATED | OUTDATED | OUTDATED | OUTDATED | 8% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
33 | CPQ11-ARCH-STON-SITE-R24.rvt | CPQ11-ARCH-STON-SITE-R23.rvt | SITE | STONE | 0000 | STONE | 0000 | V10 | 11/05/2026 | V3 | 09/06/2026 | N/A | N/A | N/A | N/A | N/A | N/A | V3 | 2026-06-09 | R24 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | NEXT ROUND | NEXT ROUND | NEXT ROUND | 1% | OUTDATED | OUTDATED | 1% | OUTDATED | IMPROPER | OUTDATED | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | 1% | NEXT ROUND | 100% | 100% | 100% | 100% | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
34 | SYST-SYSTEMS ¦ INFRASTRUCTURE
35 | CPQ11-SYST-INFR-DATA-R24.rvt | CPQ11-SYST-INFR-DATA-R22.rvt | DATA | MENDES HOLLER | 1112 | MENDES HOLLER | 1112 | V40 | 10/04/2026 | V3 | 13/07/2026 | V2 | 2026-06-03 | R24 | V2 | 2026-06-03 | R24 | V2 | 2026-06-03 | R24 | V39 | 2026-03-31 | R24 | N/A | N/A | N/A | N/A | N/A | N/A | 1% | IMPROPER | OUTDATED | OUTDATED | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | 64% | OUTDATED | OUTDATED | OUTDATED | OUTDATED | NEXT ROUND | 69% | NEXT ROUND | IMPROPER | OUTDATED | OUTDATED | OUTDATED | OUTDATED | NEXT ROUND | 69% | 1% | IMPROPER | OUTDATED | OUTDATED | NEXT ROUND | NEXT ROUND | 1% | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | 1% | OUTDATED | OUTDATED | OUTDATED | OUTDATED | NEXT ROUND | 1% | NEXT ROUND | IMPROPER | OUTDATED | OUTDATED | OUTDATED | OUTDATED | NEXT ROUND | 1% | 1% | NEXT ROUND | NEXT ROUND | NEXT ROUND | 1% | OUTDATED | NEXT ROUND | NEXT ROUND | IMPROPER | OUTDATED | OUTDATED | OUTDATED | OUTDATED | NEXT ROUND | IMPROPER | NEXT ROUND | IMPROPER | OUTDATED | OUTDATED | OUTDATED | OUTDATED | NEXT ROUND | 1% | 0% | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | ANALYSING | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
36 | CPQ11-SYST-INFR-SITE-R24.rvt | CPQ11-SYST-INFR-SITE-R22.rvt | SITE | MENDES HOLLER | 1112 | MENDES HOLLER | 1112 | V39 | 12/05/2026 | V4 | 14/07/2026 | V4 | 2026-07-14 | R24 | N/A | N/A | N/A | V38 | 06/03/2026 | R24 | N/A | N/A | N/A | V46 | 2026-07-14 | R24 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1% | NEXT ROUND | NEXT ROUND | NEXT ROUND | 14% | OUTDATED | OUTDATED | OUTDATED | OUTDATED | OUTDATED | OUTDATED | OUTDATED | NEXT ROUND | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | NEXT ROUND | 1% | OUTDATED | OUTDATED | IMPROPER | NEXT ROUND | NEXT ROUND | NEXT ROUND | 1% | OUTDATED | OUTDATED | OUTDATED | OUTDATED | OUTDATED | OUTDATED | OUTDATED | NEXT ROUND | 15% | OUTDATED | OUTDATED | OUTDATED | OUTDATED | NEXT ROUND | 58% | NEXT ROUND | 100% | 100% | 1% | IMPROPER | IMPROPER | IMPROPER | OUTDATED | NEXT ROUND | IMPROPER | NEXT ROUND | 25% | NEXT ROUND | 75% | OUTDATED | OUTDATED | OUTDATED | OUTDATED | OUTDATED | OUTDATED | OUTDATED | NEXT ROUND | 75% | OUTDATED | OUTDATED | OUTDATED | OUTDATED | NEXT ROUND | 75% | NEXT ROUND | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
37 | DAS-DISTRIBUTED ANTENN/A SYSTEM ¦ DEVICES
38 | CPQ11-DASM-DEVS-DATA-R24.rvt | CPQ11-DASM-DEVS-DATA-R22.rvt | DATA | IB TECH | 1113 | IB TECH | 1113 | V28 | 16/04/2026 | V4 | 26/06/2026 | V4 | 2026-06-26 | R22 | V2 | 2026-05-22 | R24 | V2 | 22/05/2026 | R24 | V3 | 2026-06-23 | R24 | N/A | N/A | N/A | N/A | N/A | N/A | 1% | IMPROPER | 44% | NEXT ROUND | NEXT ROUND | NEXT ROUND | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 22% | 22% | 1% | IMPROPER | OUTDATED | 1% | 15.78% | OUTDATED | NEXT ROUND | 24.13% | 58% | OUTDATED | 62% | 86% | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | 86% | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | ANALYSING | 86% | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | 1% | NEXT ROUND | 76% | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | IMPROPER | OUTDATED | OUTDATED | OUTDATED | NEXT ROUND | NEXT ROUND | NEXT ROUND | ANALYSING | 76% | 0% | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | 1% | NEXT ROUND | NEXT ROUND | ANALYSING | 1% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
39 | EPMS-ELECTRICAL POWER MAN/AGEMENT SYSTEM ¦ DEVICES
40 | CPQ11-EPMS-DEVS-DATA-R24.rvt | CPQ11-EPMS-DEVS-DATA-R22.rvt | DATA | BLACKBOX | 1114 | BLACKBOX | 1114 | V15 | 27/04/2026 | V3 | 12/07/2026 | V14 | 2026-03-23 | R22 | V1 | 2026-05-15 | R24 | V1 | 15/05/2026 | R24 | V1 | 2026-05-15 | R24 | N/A | N/A | N/A | N/A | N/A | N/A | 1% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 1% | 1% | OUTDATED | OUTDATED | OUTDATED | OUTDATED | OUTDATED | OUTDATED | OUTDATED | NEXT ROUND | 1% | OUTDATED | OUTDATED | OUTDATED | NEXT ROUND | NEXT ROUND | NEXT ROUND | 1% | OUTDATED | OUTDATED | OUTDATED | OUTDATED | OUTDATED | NEXT ROUND | NEXT ROUND | ANALYSING | 1% | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | 1% | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | IMPROPER | OUTDATED | OUTDATED | OUTDATED | 1% | NEXT ROUND | NEXT ROUND | ANALYSING | 1% | 0% | 1% | OUTDATED | OUTDATED | NEXT ROUND | IMPROPER | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | 1% | OUTDATED | NEXT ROUND | 100% | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
41 | CPQ11-EPMS-DEVS-SITE-R24.rvt | CPQ11-EPMS-DEVS-SITE-R22.rvt | SITE | BLACKBOX | 1114 | BLACKBOX | 1114 | V11 | 03/02/2026 | V1 | 15/05/2026 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | V11 | 2026-02-03 | R22 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1% | IMPROPER | 1% | OUTDATED | OUTDATED | NEXT ROUND | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
42 | ROIP-RADIO OVER IP ¦ DEVICES
43 | CPQ11-ROIP-DEVS-GUAR-R24.rvt | CPQ11-ROIP-DEVS-GUAR-R22.rvt | GUAR | IB TECH | 1113 | IB TECH | 1113 | V12 | 13/05/2026 | V2 | 01/06/2026 | V2 | 2026-06-01 | R24 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | NEXT ROUND | 1% | OUTDATED | OUTDATED | OUTDATED | NEXT ROUND | NEXT ROUND | NEXT ROUND | 1% | OUTDATED | NEXT ROUND | NEXT ROUND | 1% | OUTDATED | OUTDATED | OUTDATED | NEXT ROUND | 33% | OUTDATED | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
44 | CPQ11-ROIP-DEVS-DATA-R24.rvt | CPQ11-ROIP-DEVS-DATA-R22.rvt | DATA | IB TECH | 1113 | IB TECH | 1113 | V36 | 08/05/2026 | V2 | 03/06/2026 | V1 | 19/05/2026 | R24 | V2 | 2026-06-03 | R24 | V2 | 2026-06-03 | R24 | V3 | 2026-06-03 | R24 | N/A | N/A | N/A | N/A | N/A | N/A | 1% | IMPROPER | 1% | OUTDATED | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | 20% | NEXT ROUND | 44% | NEXT ROUND | 88% | NEXT ROUND | NEXT ROUND | NEXT ROUND | IMPROPER | IMPROPER | OUTDATED | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | ANALYSING | 88% | 1% | IMPROPER | OUTDATED | OUTDATED | NEXT ROUND | 1% | OUTDATED | NEXT ROUND | 1% | NEXT ROUND | 17% | NEXT ROUND | IMPROPER | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | 16% | OUTDATED | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | 66% | OUTDATED | 66% | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | 1% | 1% | NEXT ROUND | NEXT ROUND | IMPROPER | IMPROPER | NEXT ROUND | NEXT ROUND | NEXT ROUND | IMPROPER | NEXT ROUND | IMPROPER | OUTDATED | OUTDATED | OUTDATED | OUTDATED | OUTDATED | 1% | 0% | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | 1% | 1% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
45 | TELECOM ¦ DEVICES
46 | CPQ11-TCOM-DEVS-SITE-R24.rvt | CPQ11-TCOM-DEVS-SITE-R22.rvt | SITE | BLACKBOX | 1114 | BLACKBOX | 1114 | V14 | 29/04/2026 | V2 | 07/07/2026 | V13 | 2026-03-25 | R22 | N/A | N/A | N/A | V1 | 15/05/2026 | R24 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1% | OUTDATED | OUTDATED | OUTDATED | OUTDATED | NEXT ROUND | 64.7% | OUTDATED | OUTDATED | OUTDATED | NEXT ROUND | NEXT ROUND | 82% | IMPROPER | OUTDATED | OUTDATED | OUTDATED | OUTDATED | OUTDATED | OUTDATED | NEXT ROUND | ANALYSING | 82% | NEXT ROUND | 1% | OUTDATED | OUTDATED | 62.5% | OUTDATED | OUTDATED | OUTDATED | OUTDATED | NEXT ROUND | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
47 | CPQ11-TCOM-DEVS-DATA-R24.rvt | CPQ11-TCOM-DEVS-DATA-R22.rvt | DATA | BLACKBOX | 1114 | BLACKBOX | 1114 | V18 | 30/04/2026 | V3 | 29/06/2026 | V3 | 2026-06-29 | R24 | V2 | 2026-05-18 | R24 | V3 | 2026-06-29 | R24 | V3 | 2026-06-29 | R24 | N/A | N/A | N/A | N/A | N/A | N/A | 1% | 13.95% | OUTDATED | OUTDATED | OUTDATED | NEXT ROUND | NEXT ROUND | NEXT ROUND | 72% | OUTDATED | OUTDATED | NEXT ROUND | NEXT ROUND | 79% | NEXT ROUND | 84% | OUTDATED | NEXT ROUND | NEXT ROUND | NEXT ROUND | 93% | OUTDATED | OUTDATED | NEXT ROUND | NEXT ROUND | 98% | 98% | 1% | 36% | OUTDATED | OUTDATED | OUTDATED | NEXT ROUND | 53.4% | OUTDATED | OUTDATED | OUTDATED | OUTDATED | NEXT ROUND | 79% | OUTDATED | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | 79% | OUTDATED | NEXT ROUND | NEXT ROUND | ANALYSING | 79% | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | 1% | OUTDATED | OUTDATED | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | IMPROPER | OUTDATED | IMPROPER | OUTDATED | IMPROPER | OUTDATED | OUTDATED | OUTDATED | NEXT ROUND | IMPROPER | OUTDATED | 1% | 0% | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | 1% | OUTDATED | NEXT ROUND | IMPROPER | OUTDATED | 1% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
48 | BAS-BUILDING AUTOMATION SYSTEM ¦ INFRASTRUCTURE
49 | CPQ11-BASM-INFR-DATA-R24.rvt | CPQ11-BASM-INFR-DATA-R22.rvt | DATA | MENDES HOLLER | 1112 | MENDES HOLLER | 1112 | V33 | 04/03/2026 | V2 | 13/07/2026 | V1 | 2026-05-19 | R24 | V1 | 19/05/2026 | R24 | V1 | 2026-05-19 | R24 | V1 | 2026-05-19 | R24 | N/A | N/A | N/A | N/A | N/A | N/A | 1% | IMPROPER | OUTDATED | OUTDATED | OUTDATED | OUTDATED | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | 22% | OUTDATED | OUTDATED | OUTDATED | OUTDATED | NEXT ROUND | NEXT ROUND | NEXT ROUND | 33% | OUTDATED | OUTDATED | OUTDATED | OUTDATED | NEXT ROUND | 33% | 1% | OUTDATED | OUTDATED | OUTDATED | OUTDATED | OUTDATED | NEXT ROUND | NEXT ROUND | NEXT ROUND | IMPROPER | OUTDATED | OUTDATED | OUTDATED | OUTDATED | OUTDATED | OUTDATED | OUTDATED | NEXT ROUND | 4% | OUTDATED | OUTDATED | OUTDATED | OUTDATED | OUTDATED | OUTDATED | NEXT ROUND | 4% | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | 0% | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | 1% | OUTDATED | OUTDATED | NEXT ROUND | NEXT ROUND | IMPROPER | OUTDATED | OUTDATED | OUTDATED | OUTDATED | OUTDATED | NEXT ROUND | 1% | 0% | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | 1% | 1% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
50 | CPQ11-BASM-INFR-PUMP-R24.rvt | CPQ11-BASM-INFR-PUMP-R22.rvt | PUMP | MENDES HOLLER | 1112 | MENDES HOLLER | 1112 | V32 | 24/04/2026 | V3 | 03/07/2026 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | V3 | 2026-07-03 | R24 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1% | IMPROPER | IMPROPER | OUTDATED | OUTDATED | OUTDATED | OUTDATED | 1% | NEXT ROUND | 1% | NEXT ROUND | 33% | OUTDATED | OUTDATED | OUTDATED | NEXT ROUND | 67% | OUTDATED | OUTDATED | NEXT ROUND | IMPROPER | OUTDATED | OUTDATED | OUTDATED | NEXT ROUND | 67% | 100% | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
51 | BAS ¦ DEVICES
52 | CPQ11-BASM-DEVS-PUMP-R24.rvt | CPQ11-BASM-DEVS-PUMP-R22.rvt | PUMP | BLACKBOX | 1114 | BLACKBOX | 1114 | V14 | 03/02/2026 | V1 | 15/05/2026 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | V14 | 2026-02-03 | R22 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1% | 75% | 75% | OUTDATED | OUTDATED | NEXT ROUND | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
53 | CPQ11-BASM-DEVS-DATA-R24.rvt | CPQ11-BASM-DEVS-DATA-R22.rvt | DATA | BLACKBOX | 1114 | BLACKBOX | 1114 | V20 | 05/05/2026 | V2 | 12/07/2026 | V18 | 2026-03-26 | R22 | V1 | 15/05/2026 | R24 | V1 | 2026-05-15 | R24 | V1 | 2026-05-15 | R24 | N/A | N/A | N/A | N/A | N/A | N/A | 1% | NEXT ROUND | 12.5% | OUTDATED | OUTDATED | OUTDATED | 25% | OUTDATED | OUTDATED | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 1% | 42% | OUTDATED | OUTDATED | OUTDATED | OUTDATED | 50.87% | OUTDATED | OUTDATED | NEXT ROUND | 50.87% | OUTDATED | OUTDATED | OUTDATED | NEXT ROUND | NEXT ROUND | 98% | IMPROPER | OUTDATED | OUTDATED | OUTDATED | OUTDATED | OUTDATED | OUTDATED | NEXT ROUND | ANALYSING | 98% | NEXT ROUND | NEXT ROUND | NEXT ROUND | 1% | OUTDATED | IMPROPER | IMPROPER | OUTDATED | OUTDATED | OUTDATED | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | 13% | OUTDATED | OUTDATED | OUTDATED | NEXT ROUND | ANALYSING | 13% | 0% | 1% | OUTDATED | OUTDATED | NEXT ROUND | IMPROPER | NEXT ROUND | NEXT ROUND | NEXT ROUND | IMPROPER | OUTDATED | OUTDATED | OUTDATED | OUTDATED | NEXT ROUND | ANALYSING | 1% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
54 | SCTY-SECURITY ¦ INFRASTRUCTURE
55 | CPQ11-SCTY-INFR-DATA-R24.rvt | CPQ11-SCTY-INFR-DATA-R22.rvt | DATA | MENDES HOLLER | 1112 | MENDES HOLLER | 1112 | V39 | 19/03/2026 | V5 | 10/07/2026 | V4 | 2026-06-26 | R24 | V4 | 2026-06-26 | R24 | V4 | 2026-06-26 | R24 | V5 | 2026-07-10 | R24 | N/A | N/A | N/A | N/A | N/A | N/A | 1% | IMPROPER | OUTDATED | OUTDATED | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | IMPROPER | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | 1% | OUTDATED | OUTDATED | OUTDATED | NEXT ROUND | NEXT ROUND | NEXT ROUND | 1% | OUTDATED | OUTDATED | OUTDATED | NEXT ROUND | ANALYSING | 1% | 1% | OUTDATED | OUTDATED | OUTDATED | OUTDATED | IMPROPER | OUTDATED | NEXT ROUND | NEXT ROUND | 1% | OUTDATED | OUTDATED | OUTDATED | OUTDATED | OUTDATED | OUTDATED | OUTDATED | NEXT ROUND | 5% | OUTDATED | NEXT ROUND | IMPROPER | OUTDATED | IMPROPER | NEXT ROUND | ANALYSING | 5% | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | 0% | NEXT ROUND | NEXT ROUND | 1% | OUTDATED | OUTDATED | OUTDATED | OUTDATED | NEXT ROUND | NEXT ROUND | IMPROPER | NEXT ROUND | IMPROPER | IMPROPER | IMPROPER | NEXT ROUND | ANALYSING | 1% | 0% | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | 1% | 1% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
56 | CPQ11-SCTY-INFR-SITE-R24.rvt | CPQ11-SCTY-INFR-SITE-R22.rvt | SITE | MENDES HOLLER | 1112 | MENDES HOLLER | 1112 | V34 | 05/05/2026 | V3 | 03/07/2026 | V3 | 2026-07-03 | R24 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | V2 | 2026-05-21 | R24 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | NEXT ROUND | 1% | IMPROPER | IMPROPER | IMPROPER | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | 1% | NEXT ROUND | NEXT ROUND | 40% | NEXT ROUND | 40% | NEXT ROUND | ANALYSING | 40% | OUTDATED | OUTDATED | NEXT ROUND | NEXT ROUND | 47% | 47% | 1% | IMPROPER | IMPROPER | NEXT ROUND | 11% | NEXT ROUND | IMPROPER | 20% | NEXT ROUND | NEXT ROUND | REPROVED | OUTDATED | OUTDATED | OUTDATED | OUTDATED | NEXT ROUND | 40% | NEXT ROUND | 50% | NEXT ROUND | NEXT ROUND | 70% | OUTDATED | OUTDATED | OUTDATED | NEXT ROUND | NEXT ROUND | ANALYSING | 70% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
57 | SCTY ¦ DEVICES
58 | CPQ11-SCTY-DEVS-SITE-R24.rvt | CPQ11-SCTY-DEVS-SITE-R22.rvt | SITE | SEGURPRO | 1115 | SEGURPRO | 1115 | V37 | 10/04/2026 | V1 | 20/05/2026 | V37 | 10/04/2026 | R22 | N/A | N/A | N/A | V37 | 2026-04-10 | R22 | N/A | N/A | N/A | V30 | 21/11/2025 | R22 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1% | OUTDATED | NEXT ROUND | NEXT ROUND | 7.51% | NEXT ROUND | 85% | NEXT ROUND | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | NEXT ROUND | 1% | OUTDATED | NEXT ROUND | 11.11% | NEXT ROUND | NEXT ROUND | NEXT ROUND | 44% | NEXT ROUND | 77.7% | NEXT ROUND | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 1% | IMPROPER | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
59 | CPQ11-SCTY-DEVS-DATA-R24.rvt | CPQ11-SCTY-DEVS-DATA-R22.rvt | DATA | SEGURPRO | 1115 | SEGURPRO | 1115 | V40 | 06/05/2026 | V3 | 13/07/2026 | V1 | 20/05/2026 | R24 | V1 | 2026-05-20 | R24 | V1 | 2026-05-20 | R24 | V2 | 2026-07-06 | R24 | N/A | N/A | N/A | N/A | N/A | N/A | 1% | NEXT ROUND | IMPROPER | IMPROPER | NEXT ROUND | NEXT ROUND | 26% | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | 47% | OUTDATED | OUTDATED | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | 55% | OUTDATED | OUTDATED | OUTDATED | NEXT ROUND | ANALYSING | 55% | 1% | IMPROPER | OUTDATED | IMPROPER | NEXT ROUND | 1% | 20% | NEXT ROUND | NEXT ROUND | 28% | IMPROPER | NEXT ROUND | 80% | OUTDATED | OUTDATED | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | IMPROPER | OUTDATED | OUTDATED | OUTDATED | NEXT ROUND | ANALYSING | 80% | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | 1% | NEXT ROUND | 2% | NEXT ROUND | IMPROPER | OUTDATED | OUTDATED | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | IMPROPER | OUTDATED | OUTDATED | OUTDATED | NEXT ROUND | ANALYSING | 2% | 0% | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | 1% | NEXT ROUND | IMPROPER | 1% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
60 | CPQ11-SCTY-GATE-SITE-R24.rvt | CPQ11-SCTY-GATE-SITE-R24.rvt | SITE | FM SECURITY | 0000 | FM SECURITY | 0000 | V2 | 07/05/2026 | V5 | 08/07/2026 | N/A | N/A | R24 | N/A | N/A | N/A | V4 | 2026-07-02 | R24 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | 1% | OUTDATED | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | 25% | OUTDATED | NEXT ROUND | 25% | NEXT ROUND | 25% | ANALYSING | 25% | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | 0% | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | ANALYSING | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
61 | ELEC-ELETRICAL
62 | CPQ11-ELEC-ELEC-SITE-R24.rvt | CPQ11-ELEC-ELEC-SITE-R22.rvt | SITE | MENDES HOLLER | 1112 | MENDES HOLLER | 1112 | V33 | 05/03/2026 | V1 | 19/05/2026 | V1 | 2026-05-19 | R24 | N/A | N/A | N/A | V1 | 2026-05-19 | R24 | N/A | N/A | N/A | V1 | 2026-05-19 | R24 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | NEXT ROUND | 1% | 1% | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | 1% | OUTDATED | OUTDATED | OUTDATED | OUTDATED | OUTDATED | 1% | NEXT ROUND | 1% | OUTDATED | OUTDATED | IMPROPER | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | 1% | OUTDATED | OUTDATED | OUTDATED | OUTDATED | OUTDATED | OUTDATED | 1% | 1% | IMPROPER | IMPROPER | OUTDATED | OUTDATED | OUTDATED | IMPROPER | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | IMPROPER | OUTDATED | OUTDATED | OUTDATED | OUTDATED | OUTDATED | 1% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
63 | CPQ11-ELEC-ELEC-DATA-R24.rvt | CPQ11-ELEC-ELEC-DATA-R22.rvt | DATA | MENDES HOLLER | 1112 | MENDES HOLLER | 1112 | V52 | 30/04/2026 | V4 | 06/07/2026 | V4 | 2026-07-06 | R24 | V4 | 2026-07-06 | R24 | V4 | 2026-07-06 | R24 | N/A | N/A | R24 | N/A | N/A | N/A | N/A | N/A | N/A | 1% | IMPROPER | OUTDATED | OUTDATED | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | IMPROPER | NEXT ROUND | NEXT ROUND | NEXT ROUND | IMPROPER | OUTDATED | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | IMPROPER | OUTDATED | NEXT ROUND | NEXT ROUND | IMPROPER | 1% | 1% | OUTDATED | OUTDATED | OUTDATED | IMPROPER | NEXT ROUND | IMPROPER | NEXT ROUND | IMPROPER | NEXT ROUND | NEXT ROUND | NEXT ROUND | IMPROPER | OUTDATED | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | IMPROPER | OUTDATED | NEXT ROUND | NEXT ROUND | IMPROPER | 1% | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | 0% | NEXT ROUND | NEXT ROUND | 1% | OUTDATED | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | IMPROPER | OUTDATED | NEXT ROUND | NEXT ROUND | IMPROPER | 1% | 0% | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | ANALYSING | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
64 | SPDA ¦ PROTECTION SYSTEM ATMOSPHERIC DISCHARGE
65 | CPQ11-ELEC-SPDA-DATA-R24.rvt | CPQ11-ELEC-SPDA-DATA-R22.rvt | DATA | MENDES HOLLER | 1112 | MENDES HOLLER | 1112 | V13 | 12/05/2026 | V5 | 13/07/2026 | V13 | 12/05/2026 | R22 | V3 | 2026-06-25 | R24 | V3 | 2026-06-25 | R24 | V4 | 2026-07-03 | R24 | N/A | N/A | N/A | N/A | N/A | N/A | 1% | IMPROPER | 1% | OUTDATED | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | 57% | NEXT ROUND | NEXT ROUND | 92% | NEXT ROUND | 93% | NEXT ROUND | NEXT ROUND | NEXT ROUND | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 1% | OUTDATED | OUTDATED | 1% | NEXT ROUND | 1% | NEXT ROUND | NEXT ROUND | IMPROPER | NEXT ROUND | NEXT ROUND | NEXT ROUND | 17% | 23% | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | 31% | NEXT ROUND | 45% | OUTDATED | IMPROPER | NEXT ROUND | ANALYSING | 45% | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | 0% | NEXT ROUND | 1% | NEXT ROUND | IMPROPER | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | IMPROPER | NEXT ROUND | IMPROPER | OUTDATED | IMPROPER | NEXT ROUND | IMPROPER | 1% | 0% | NEXT ROUND | 1% | IMPROPER | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | IMPROPER | NEXT ROUND | IMPROPER | OUTDATED | IMPROPER | NEXT ROUND | IMPROPER | 1% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
66 | CPQ11-ELEC-SPDA-SITE-R24.rvt | CPQ11-ELEC-SPDA-SITE-R22.rvt | SITE | MENDES HOLLER | 1112 | MENDES HOLLER | 1112 | V7 | 08/12/2025 | V2 | 03/07/2026 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | V7 | 08/12/2025 | R22 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | NEXT ROUND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1% | 51% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
67 | DALI-DIGITAL ADDRESSABLE LIGHTING INTERFACE-DEVICES
68 | CPQ11-DALI-DEVS-DATA-R24.rvt | CPQ11-DALI-DEVS-DATA-R22.rvt | DATA | AUTOBRÁS | 1116 | AUTOBRÁS | 1116 | V15 | 15/04/2026 | V2 | 02/06/2026 | V2 | 2026-06-02 | R24 | V2 | 2026-06-02 | R24 | V2 | 2026-06-02 | R24 | V2 | 2026-06-02 | R24 | N/A | N/A | N/A | N/A | N/A | N/A | IMPROPER | OUTDATED | 1% | OUTDATED | OUTDATED | OUTDATED | OUTDATED | OUTDATED | OUTDATED | NEXT ROUND | NEXT ROUND | IMPROPER | NEXT ROUND | NEXT ROUND | 14% | OUTDATED | OUTDATED | OUTDATED | OUTDATED | NEXT ROUND | IMPROPER | OUTDATED | OUTDATED | OUTDATED | OUTDATED | OUTDATED | 14% | IMPROPER | 1% | OUTDATED | OUTDATED | OUTDATED | OUTDATED | OUTDATED | OUTDATED | OUTDATED | NEXT ROUND | IMPROPER | OUTDATED | NEXT ROUND | 1% | OUTDATED | OUTDATED | OUTDATED | OUTDATED | OUTDATED | NEXT ROUND | IMPROPER | OUTDATED | OUTDATED | OUTDATED | OUTDATED | OUTDATED | 1% | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | 1% | NEXT ROUND | IMPROPER | OUTDATED | NEXT ROUND | 1% | OUTDATED | OUTDATED | OUTDATED | OUTDATED | OUTDATED | NEXT ROUND | IMPROPER | OUTDATED | OUTDATED | OUTDATED | OUTDATED | OUTDATED | 1% | 0% | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | 1% | OUTDATED | OUTDATED | 1% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
69 | FALM-FIRE ALARM
70 | CPQ11-FALM-FALM-SITE-R24.rvt | CPQ11-FALM-FALM-SITE-R22.rvt | SITE | MENDES HOLLER | 1112 | MENDES HOLLER | 1112 | V11 | 08/05/2026 | V3 | 10/07/2026 | V2 | 2026-06-23 | R24 | N/A | N/A | N/A | V7 | 03/03/2026 | R22 | N/A | N/A | N/A | V2 | 2026-06-23 | R24 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | NEXT ROUND | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | NEXT ROUND | 1% | OUTDATED | NEXT ROUND | IMPROPER | OUTDATED | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | IMPROPER | OUTDATED | OUTDATED | OUTDATED | IMPROPER | IMPROPER | NEXT ROUND | ANALYSING | 1% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 1% | NEXT ROUND | NEXT ROUND | IMPROPER | OUTDATED | OUTDATED | OUTDATED | NEXT ROUND | IMPROPER | NEXT ROUND | ANALYSING | 1% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
71 | CPQ11-FALM-FALM-DATA-R24.rvt | CPQ11-FALM-FALM-DATA-R22.rvt | DATA | MENDES HOLLER | 1112 | MENDES HOLLER | 1112 | V24 | 15/05/2026 | V2 | 06/07/2026 | V2 | 2026-07-06 | R24 | V2 | 2026-07-06 | R24 | V2 | 2026-07-06 | R24 | N/A | N/A | R24 | N/A | N/A | N/A | N/A | N/A | N/A | 0% | IMPROPER | OUTDATED | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | 1% | NEXT ROUND | NEXT ROUND | IMPROPER | NEXT ROUND | NEXT ROUND | IMPROPER | OUTDATED | OUTDATED | OUTDATED | OUTDATED | OUTDATED | NEXT ROUND | IMPROPER | 1% | IMPROPER | IMPROPER | OUTDATED | NEXT ROUND | NEXT ROUND | 1% | NEXT ROUND | NEXT ROUND | NEXT ROUND | IMPROPER | NEXT ROUND | NEXT ROUND | IMPROPER | IMPROPER | NEXT ROUND | IMPROPER | NEXT ROUND | NEXT ROUND | IMPROPER | OUTDATED | OUTDATED | OUTDATED | OUTDATED | OUTDATED | NEXT ROUND | IMPROPER | 1% | NEXT ROUND | NEXT ROUND | NEXT ROUND | 1% | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | IMPROPER | NEXT ROUND | NEXT ROUND | IMPROPER | OUTDATED | OUTDATED | OUTDATED | OUTDATED | OUTDATED | NEXT ROUND | IMPROPER | 1% | N/A | N/A | N/A | 0% | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | ANALYSING | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
72 | FPRT-FIRE PROTECTION
73 | CPQ11-FPRT-FPRT-SITE-R24.rvt | CPQ11-FPRT-FPRT-SITE-R22.rvt | SITE | MENDES HOLLER | 1112 | MENDES HOLLER | 1112 | V16 | 14/05/2026 | V4 | 13/07/2026 | V3 | 2026-06-24 | R24 | N/A | N/A | N/A | V3 | 2026-06-24 | R24 | N/A | N/A | N/A | V3 | 2026-06-24 | R24 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | NEXT ROUND | NEXT ROUND | NEXT ROUND | 1% | OUTDATED | NEXT ROUND | NEXT ROUND | IMPROPER | IMPROPER | OUTDATED | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | IMPROPER | OUTDATED | NEXT ROUND | NEXT ROUND | IMPROPER | OUTDATED | NEXT ROUND | 1% | NEXT ROUND | 1% | OUTDATED | NEXT ROUND | IMPROPER | OUTDATED | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | IMPROPER | OUTDATED | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | IMPROPER | OUTDATED | NEXT ROUND | NEXT ROUND | IMPROPER | OUTDATED | NEXT ROUND | 1% | 1% | IMPROPER | IMPROPER | OUTDATED | OUTDATED | NEXT ROUND | IMPROPER | OUTDATED | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | IMPROPER | OUTDATED | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | IMPROPER | OUTDATED | NEXT ROUND | NEXT ROUND | IMPROPER | OUTDATED | NEXT ROUND | 1% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
74 | CPQ11-FPRT-FPRT-DATA-R24.rvt | CPQ11-FPRT-FPRT-DATA-R22.rvt | DATA | MENDES HOLLER | 1112 | MENDES HOLLER | 1112 | V17 | 14/05/2026 | V4 | 25/06/2026 | V4 | 2026-06-25 | R24 | V4 | 2026-06-25 | R24 | V4 | 2026-06-25 | R24 | N/A | N/A | R24 | N/A | N/A | N/A | N/A | N/A | N/A | 1% | IMPROPER | OUTDATED | NEXT ROUND | NEXT ROUND | IMPROPER | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | IMPROPER | NEXT ROUND | NEXT ROUND | NEXT ROUND | IMPROPER | IMPROPER | NEXT ROUND | IMPROPER | OUTDATED | OUTDATED | OUTDATED | 1% | 1% | OUTDATED | OUTDATED | NEXT ROUND | IMPROPER | OUTDATED | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | IMPROPER | OUTDATED | NEXT ROUND | IMPROPER | NEXT ROUND | NEXT ROUND | NEXT ROUND | IMPROPER | IMPROPER | NEXT ROUND | IMPROPER | OUTDATED | OUTDATED | OUTDATED | 1% | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | 1% | NEXT ROUND | NEXT ROUND | IMPROPER | OUTDATED | NEXT ROUND | IMPROPER | NEXT ROUND | NEXT ROUND | NEXT ROUND | IMPROPER | IMPROPER | NEXT ROUND | IMPROPER | OUTDATED | OUTDATED | OUTDATED | 1% | 0% | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | ANALYSING | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
75 | CPQ11-FPRT-METK-UTLS-R24.rvt | CPQ11-FPRT-METK-UTLS-R22.rvt | UTLS | PETROTANQUE | 1117 | CADBIM | 1128 | V16 | 06/03/2026 | V5 | 08/07/2026 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | V15 | 15/01/2026 | R22 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
76 | PLMB-PLUMBING
77 | CPQ11-PLMB-PLMB-SITE-R24.rvt | CPQ11-PLMB-PLMB-SITE-R22.rvt | SITE | MENDES HOLLER | 1112 | MENDES HOLLER | 1112 | V27 | 08/04/2026 | V2 | 23/06/2026 | V2 | 2026-06-23 | R24 | N/A | N/A | N/A | V1 | 2026-05-19 | R24 | N/A | N/A | N/A | V2 | 2026-06-23 | R24 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | 1% | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | 3% | OUTDATED | NEXT ROUND | NEXT ROUND | NEXT ROUND | ANALYSING | 3% | NEXT ROUND | 1% | OUTDATED | OUTDATED | IMPROPER | OUTDATED | OUTDATED | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | IMPROPER | OUTDATED | OUTDATED | OUTDATED | OUTDATED | OUTDATED | NEXT ROUND | NEXT ROUND | IMPROPER | OUTDATED | OUTDATED | NEXT ROUND | 1% | OUTDATED | OUTDATED | 1% | 1% | IMPROPER | IMPROPER | IMPROPER | OUTDATED | OUTDATED | IMPROPER | OUTDATED | OUTDATED | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | IMPROPER | NEXT ROUND | 1% | OUTDATED | OUTDATED | 1% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
78 | CPQ11-PLMB-PLMB-DATA-R24.rvt | CPQ11-PLMB-PLMB-DATA-R22.rvt | DATA | MENDES HOLLER | 1112 | MENDES HOLLER | 1112 | V30 | 24/03/2026 | V2 | 13/07/2026 | V1 | 2026-05-19 | R24 | V1 | 2026-05-19 | R24 | V1 | 2026-05-19 | R24 | N/A | N/A | R24 | N/A | N/A | N/A | N/A | N/A | N/A | 1% | IMPROPER | IMPROPER | OUTDATED | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | IMPROPER | OUTDATED | OUTDATED | OUTDATED | OUTDATED | OUTDATED | NEXT ROUND | NEXT ROUND | IMPROPER | OUTDATED | OUTDATED | OUTDATED | OUTDATED | OUTDATED | NEXT ROUND | 1% | 1% | 1% | 1% | OUTDATED | IMPROPER | OUTDATED | OUTDATED | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | IMPROPER | OUTDATED | OUTDATED | OUTDATED | OUTDATED | NEXT ROUND | NEXT ROUND | IMPROPER | OUTDATED | OUTDATED | OUTDATED | OUTDATED | OUTDATED | NEXT ROUND | 1% | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | 1% | NEXT ROUND | NEXT ROUND | IMPROPER | OUTDATED | OUTDATED | OUTDATED | OUTDATED | OUTDATED | NEXT ROUND | NEXT ROUND | IMPROPER | OUTDATED | OUTDATED | OUTDATED | OUTDATED | OUTDATED | NEXT ROUND | 1% | 0% | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | ANALYSING | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
79 | CPQ11-PLMB-DIES-SITE-R24.rvt | CPQ11-PLMB-DIES-SITE-R22.rvt | SITE | MENDES HOLLER | 1112 | MENDES HOLLER | 1112 | V14 | 03/03/2026 | V4 | 13/07/2026 | N/A | N/A | N/A | N/A | N/A | N/A | V3 | 2026-06-19 | R24 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | NEXT ROUND | NEXT ROUND | NEXT ROUND | 1% | OUTDATED | OUTDATED | OUTDATED | OUTDATED | OUTDATED | OUTDATED | OUTDATED | OUTDATED | OUTDATED | IMPROPER | OUTDATED | 14% | NEXT ROUND | 53% | NEXT ROUND | 57% | 100% | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
80 | CPQ11-PLMB-NPWT-SITE-R24.rvt | CPQ11-PLMB-NPWT-SITE-R22.rvt | SITE | STARCENTER | 1118 | STARCENTER | 1118 | V46 | 24/04/2026 | V2 | 15/06/2026 | N/A | N/A | N/A | N/A | N/A | N/A | V43 | 2026-03-20 | R22 | N/A | N/A | N/A | V46 | 2026-04-24 | R22 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1% | OUTDATED | NEXT ROUND | NEXT ROUND | NEXT ROUND | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1% | IMPROPER | 1% | 1% | OUTDATED | NEXT ROUND | NEXT ROUND | 1% | NEXT ROUND | 1% | NEXT ROUND | NEXT ROUND | 83% | NEXT ROUND | 83% | NEXT ROUND | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
81 | CPQ11-PLMB-NPWT-DATA-R24.rvt | CPQ11-PLMB-NPWT-DATA-R22.rvt | DATA | STARCENTER | 1118 | STARCENTER | 1118 | V39 | 30/04/2026 | V3 | 01/07/2026 | V2 | 2026-05-22 | R24 | V3 | 2026-07-01 | R24 | V3 | 2026-07-01 | R24 | V3 | 2026-07-01 | R24 | N/A | N/A | N/A | N/A | N/A | N/A | 1% | 1% | IMPROPER | IMPROPER | OUTDATED | OUTDATED | NEXT ROUND | NEXT ROUND | NEXT ROUND | IMPROPER | OUTDATED | OUTDATED | NEXT ROUND | 1% | NEXT ROUND | NEXT ROUND | NEXT ROUND | 1% | NEXT ROUND | NEXT ROUND | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 1% | IMPROPER | 1% | IMPROPER | OUTDATED | OUTDATED | NEXT ROUND | NEXT ROUND | NEXT ROUND | 47.17% | OUTDATED | OUTDATED | NEXT ROUND | NEXT ROUND | 66% | NEXT ROUND | NEXT ROUND | IMPROPER | NEXT ROUND | 69% | OUTDATED | OUTDATED | OUTDATED | NEXT ROUND | 88% | OUTDATED | 88% | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | 1% | OUTDATED | OUTDATED | NEXT ROUND | IMPROPER | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | IMPROPER | OUTDATED | OUTDATED | OUTDATED | OUTDATED | NEXT ROUND | IMPROPER | OUTDATED | 1% | 0% | 1% | NEXT ROUND | NEXT ROUND | NEXT ROUND | IMPROPER | NEXT ROUND | NEXT ROUND | NEXT ROUND | IMPROPER | OUTDATED | OUTDATED | OUTDATED | NEXT ROUND | IMPROPER | OUTDATED | 1% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
82 | CPQ11-PLMB-METK-UTLS-R24.rvt | CPQ11-PLMB-METK-UTLS-R22.rvt | UTLS | STARCENTER | 1118 | STARCENTER | 1118 | V28 | 26/02/2026 | V1 | 19/05/2026 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | V28 | 2026-02-26 | R22 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1% | IMPROPER | 1% | 1% | OUTDATED | NEXT ROUND | NEXT ROUND | 66% | NEXT ROUND | 66% | OUTDATED | OUTDATED | OUTDATED | OUTDATED | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
83 | MECH-MECHANICAL
84 | CPQ11-MECH-MECH-DATA-R24.rvt | CPQ11-MECH-MECH-DATA-R22.rvt | DATA | STARCENTER | 1118 | STARCENTER | 1118 | V59 | 17/04/2026 | V5 | 06/07/2026 | V5 | 2026-07-06 | R24 | V2 | 2026-05-22 | R24 | V4 | 2026-07-02 | R24 | V5 | 2026-07-06 | R24 | N/A | N/A | N/A | N/A | N/A | N/A | 1% | OUTDATED | OUTDATED | OUTDATED | OUTDATED | OUTDATED | OUTDATED | NEXT ROUND | 5% | NEXT ROUND | NEXT ROUND | NEXT ROUND | 24% | OUTDATED | OUTDATED | OUTDATED | OUTDATED | IMPROPER | NEXT ROUND | 43% | OUTDATED | OUTDATED | OUTDATED | NEXT ROUND | 73% | IMPROPER | 73% | 1% | OUTDATED | OUTDATED | OUTDATED | OUTDATED | OUTDATED | OUTDATED | NEXT ROUND | 0% | NEXT ROUND | 12% | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | 22% | NEXT ROUND | NEXT ROUND | NEXT ROUND | 25% | OUTDATED | NEXT ROUND | NEXT ROUND | ANALYSING | 25% | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | 1% | IMPROPER | NEXT ROUND | IMPROPER | NEXT ROUND | NEXT ROUND | IMPROPER | OUTDATED | IMPROPER | NEXT ROUND | NEXT ROUND | IMPROPER | OUTDATED | OUTDATED | NEXT ROUND | IMPROPER | ANALYSING | 1% | 0% | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | 1% | NEXT ROUND | IMPROPER | 1% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
85 | CPQ11-MECH-MECH-GUAR-R24.rvt | CPQ11-MECH-MECH-GUAR-R22.rvt | GUAR | STARCENTER | 1118 | STARCENTER | 1118 | V23 | 16/04/2026 | V1 | 19/05/2026 | V23 | 2026-04-16 | R22 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | NEXT ROUND | 1% | OUTDATED | OUTDATED | OUTDATED | OUTDATED | NEXT ROUND | NEXT ROUND | 14% | 42% | NEXT ROUND | 42% | 86% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
86 | LAND-LANDSCAPE
87 | CPQ11-LAND-LAND-SITE-R24.rvt | CPQ11-LAND-LAND-SITE-R22.rvt | SITE | ORGANISMO VIVO | 0000 | CONTRACTING | 0000 | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | N/A | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | N/A | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED
88 | CIVIL
89 | CPQ11-CIVL-DRNG-SITE-R24.rvt | CPQ11-CIVL-DRNG-SITE-R22.rvt | SITE | GARCIA | 1119 | CADBIM | 1128 | V20 | 06/05/2026 | V4 | 11/06/2026 | N/A | N/A | N/A | N/A | N/A | N/A | V20 | 2026-05-06 | R22 | N/A | N/A | N/A | V11 | 2026-02-02 | R22 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | NEXT ROUND | 1% | 1% | NEXT ROUND | NEXT ROUND | 22% | NEXT ROUND | 59% | NEXT ROUND | NEXT ROUND | 59% | NEXT ROUND | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | IMPROPER | 1% | NEXT ROUND | 1% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
90 | CPQ11-CIVL-ERTH-SITE-R24.rvt | CPQ11-CIVL-ERTH-SITE-R22.rvt | SITE | GARCIA | 1119 | CADBIM | 1128 | V18 | 08/04/2026 | V6 | 24/06/2026 | V2 | 2026-05-20 | R24 | N/A | N/A | N/A | V18 | 2026-04-08 | R22 | N/A | N/A | N/A | V13 | 2026-03-06 | R24 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1% | OUTDATED | NEXT ROUND | NEXT ROUND | 1% | 62% | 69.23% | NEXT ROUND | NEXT ROUND | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NEXT ROUND | 1% | NEXT ROUND | NEXT ROUND | 1% | 1% | 1% | NEXT ROUND | NEXT ROUND | NEXT ROUND | 1% | OUTDATED | OUTDATED | NEXT ROUND | NEXT ROUND | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | NEXT ROUND | 1% | NEXT ROUND | NEXT ROUND | 1% | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | 100% | 100% | 100% | 100% | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
91 | CPQ11-CIVL-PAVM-SITE-R24.rvt | CPQ11-CIVL-PAVM-SITE-R22.rvt | SITE | GARCIA | 1119 | CADBIM | 1128 | V18 | 30/04/2026 | V2 |  | N/A | N/A | N/A | N/A | N/A | N/A | V18 | 2026-04-30 | R22 | N/A | N/A | N/A | V1 | 2025-09-14 | R22 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1% | OUTDATED | NEXT ROUND | NEXT ROUND | 25.61% | NEXT ROUND | 57% | NEXT ROUND | NEXT ROUND | 68% | 87% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
92 | CPQ11-CIVL-SIGN-SITE-R24.rvt | CPQ11-CIVL-SIGN-SITE-R22.rvt | SITE | CONTRACTING | 0000 | CONTRACTING | 0000 | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | N/A | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | N/A | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED
93 | CPQ11-CIVL-LOCK-SITE-R24.rvt | CPQ11-CIVL-LOCK-SITE-R22.rvt | SITE | STEINER | 0000 | PMD | 0000 | V11 | 21/03/2026 | V1 | 18/05/2026 | N/A | N/A | N/A | N/A | N/A | N/A | V11 | 2026-03-21 | R22 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | NEXT ROUND | NEXT ROUND | NEXT ROUND | 1% | NEXT ROUND | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
94 | STRC-STRUCTURE
95 | CPQ11-STRC-CONC-DATA-R24.rvt | CPQ11-STRC-CONC-DATA-R22.rvt | DATA | SERV OBRAS | 1120 | TENAX | 0000 | V10 | 22/04/2026 | V1 | 15/05/2026 | V7 | 10/12/2025 | R22 | V7 | 10/12/2025 | R22 | V9 | 13/03/2026 | R22 | V9 | 2026-03-13 | R22 | N/A | N/A | N/A | N/A | N/A | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
96 | CPQ11-STRC-CONC-SITE-R24.rvt | CPQ11-STRC-CONC-SITE-R22.rvt | SITE | SERV OBRAS | 1120 | TENAX | 0000 | V17 | 12/05/2026 | V1 | 15/05/2026 | V14 | 2026-03-13 | R22 | N/A | N/A | N/A | V1 | 2026-05-15 | R24 | N/A | N/A | N/A | V1 | 2026-05-15 | R24 | V1 | 15/05/2026 | R24 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | 1% | OUTDATED | OUTDATED | OUTDATED | NEXT ROUND | 9% | OUTDATED | NEXT ROUND | NEXT ROUND | NEXT ROUND | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | NEXT ROUND | 100% | 100% | 100% | 1% | NEXT ROUND | NEXT ROUND | NEXT ROUND | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 1% | IMPROPER | 100% | 100% | 100% | 100% | 100% | 75% | NEXT ROUND | 61% | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | 86% | NEXT ROUND | NEXT ROUND | NEXT ROUND | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 1% | NEXT ROUND | NEXT ROUND | NEXT ROUND | 100% | 1% | NEXT ROUND | NEXT ROUND | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
97 | CPQ11-STRC-DPFN-DATA-R24.rvt | CPQ11-STRC-DPFN-DATA-R22.rvt | DATA | GEOFIX/TECNOGEO | 0000 | TENAX | 0000 | V11 | 28/04/2026 | V1 | 15/05/2026 | V8 | 2026-01-16 | R22 | V8 | 2026-01-16 | R22 | V10 | 13/03/2026 | R22 | V10 | 2026-03-13 | R22 | N/A | N/A | N/A | N/A | N/A | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | NEXT ROUND | NEXT ROUND | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
98 | CPQ11-STRC-DPFN-SITE-R24.rvt | CPQ11-STRC-DPFN-SITE-R22.rvt | SITE | GEOFIX/TECNOGEO | 0000 | TENAX | 0000 | V13 | 12/05/2026 | V1 | 15/05/2026 | V7 | 2025-12-10 | R22 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | V1 | 2026-05-15 | R24 | V1 | 15/05/2026 | R24 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 1% | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | 100% | 100% | 100% | 100% | 100% | 1% | NEXT ROUND | NEXT ROUND | NEXT ROUND | 100% | 1% | NEXT ROUND | NEXT ROUND | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
99 | CPQ11-STRC-FLOO-DATA-R24.rvt | CPQ11-STRC-FLOO-DATA-R22.rvt | DATA | MODAX | 1121 | MODAX | 1121 | V1 | 05/05/2026 | V3 | 20/06/2026 | V3 | 2026-06-20 | R24 | V3 | 2026-06-20 | R24 | V3 | 2026-06-20 | R24 | V3 | 2026-06-20 | R24 | N/A | N/A | N/A | N/A | N/A | N/A | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | 0% | 0% | 0% | NEXT ROUND | NEXT ROUND | NEXT ROUND | 1% | 100% | 100% | 100% | 100% | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | 0% | 0% | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | 100% | 100% | 100% | 100% | 100% | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | 0% | 0% | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | 100% | 100% | 100% | 100% | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | 0% | 0% | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | 100% | 100% | 100% | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
100 | CPQ11-STRC-FLOO-SITE-R24.rvt | CPQ11-STRC-FLOO-SITE-R22.rvt | SITE | MODAX | 1121 | MODAX | 1121 | V1 | 05/05/2026 | V2 | 26/05/2026 | V2 | 2026-05-26 | R24 | N/A | N/A | N/A | N/A | N/A | R24 | N/A | N/A | N/A | V2 | 26/05/2026 | R24 | V2 | 26/05/2026 | R24 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | 0% | 0% | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | ANALYSING | 0% | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | 0% | 0% | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | 1% | OUTDATED | OUTDATED | OUTDATED | 1% | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | 0% | 0% | NEXT ROUND | NEXT ROUND | NEXT ROUND | NEXT ROUND | 1% | OUTDATED | OUTDATED | OUTDATED | 1% | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | 0% | 0% | IMPROPER | OUTDATED | OUTDATED | OUTDATED | OUTDATED | OUTDATED | OUTDATED | OUTDATED | 0%
101 | CPQ11-STRC-CHAI-SITE-R24.rvt | CPQ11-STRC-CHAI-SITE-R22.rvt | SITE | S-VALE | 1104 | SPBIM | 1127 | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | N/A | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | N/A | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED
102 | CPQ11-STRC-FENC-SITE-R24.rvt | CPQ11-STRC-FENC-SITE-R22.rvt | SITE | SERCOP, SERV OBRAS | 1124 | CONTRACTING | 0000 | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | N/A | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | N/A | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED
103 | CPQ11-STRC-STEE-ADMN-2X3.ifc | CPQ11-STRC-STEE-ADMN-2X3.ifc | ADMN | METASA | 1125 | METASA | 1125 | V8 | 07/11/2025 | V1 | 21/05/2026 | V8 | 2025-11-07 | R22 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
104 | CPQ11-STRC-STEE-COL1-2X3.ifc | CPQ11-STRC-STEE-COL1-2X3.ifc | COL1 | METASA | 1125 | METASA | 1125 | V7 | 07/11/2025 | V1 | 21/05/2026 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
105 | CPQ11-STRC-STEE-COL2-2X3.ifc | CPQ11-STRC-STEE-COL2-2X3.ifc | COL2 | METASA | 1125 | METASA | 1125 | V6 | 07/11/2025 | V1 | 21/05/2026 | N/A | N/A | N/A | N/A | N/A | N/A | V6 | 07/11/2025 | R22 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | NEXT ROUND | NEXT ROUND | NEXT ROUND | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
106 | CPQ11-STRC-STEE-COL3-2X3.ifc | CPQ11-STRC-STEE-COL3-2X3.ifc | COL3 | METASA | 1125 | METASA | 1125 | V6 | 07/11/2025 | V1 | 21/05/2026 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | NEXT ROUND | NEXT ROUND | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
107 | CPQ11-STRC-STEE-COL4-2X3.ifc | CPQ11-STRC-STEE-COL4-2X3.ifc | COL4 | METASA | 1125 | METASA | 1125 | V7 | 05/12/2025 | V1 | 21/05/2026 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
108 | CPQ11-STRC-STEE-COL5-2X3.ifc | CPQ11-STRC-STEE-COL5-2X3.ifc | COL5 | METASA | 1125 | METASA | 1125 | V6 | 07/11/2025 | V1 | 21/05/2026 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
109 | CPQ11-STRC-STEE-UTLS-2X3.ifc | CPQ11-STRC-STEE-UTLS-2X3.ifc | UTLS | METASA | 1125 | METASA | 1125 | V6 | 11/02/2026 | V1 | 21/05/2026 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | V5 | 27/10/2025 | R22 | V6 | 11/02/2026 | R22 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 1% | NEXT ROUND | NEXT ROUND | NEXT ROUND | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
110 | CPQ11-STRC-STEE-GUAR-2X3.ifc | CPQ11-STRC-STEE-GUAR-2X3.ifc | GUAR | METASA | 1125 | METASA | 1125 | V6 | 01/11/2025 | V1 | 21/05/2026 | V6 | 01/11/2025 | R22 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
111 | CPQ11-STRC-STEE-STIR-2X3.ifc | CPQ11-STRC-STEE-STIR-2X3.ifc | STIR | METASA | 1125 | METASA | 1125 | V3 | 31/10/2025 | V1 | 21/05/2026 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | V2 | 2025-07-18 | R22 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Formulas:
FILE DATE (ADMN/GUAR) = IF(OR([AREA]="UTLS",[AREA]="GUAR",[AREA]="STIR",[AREA]="PUMP",[AREA]="SITE"), VLOOKUP([META DO DIA 17/07],'LOD 500 - GUAR'!B:N,13,FALSE), VLOOKUP([META DO DIA 17/07],'LOD 500 - ADMN'!B:N,13,FALSE) )
FILE DATE (COLO1) = IF(OR([AREA]="C345",[AREA]="C12A",[AREA]="DATA"), VLOOKUP([META DO DIA 17/07],'LOD 500 - COLO1'!B:N,13,FALSE),"N/A")
FILE DATE (COLO2/SITE) = IF(OR([AREA]="UTLS",[AREA]="GUAR",[AREA]="STIR",[AREA]="PUMP",[AREA]="SITE"), VLOOKUP([META DO DIA 17/07],'LOD 500 - SITE'!B:Q,13,FALSE), VLOOKUP([META DO DIA 17/07],'LOD 500 - COLO2'!B:N,13,FALSE) )
FILE DATE COLO3 = IF(OR([AREA]="C345",[AREA]="C12A",[AREA]="DATA"), VLOOKUP([META DO DIA 17/07],'LOD 500 - COLO3'!B:N,13,FALSE),"N/A")
UTLS FILE DATE = IF(OR([AREA]="UTLS",[AREA]="GUAR",[AREA]="STIR",[AREA]="PUMP",[AREA]="SITE"), VLOOKUP([META DO DIA 17/07],'LOD 500 - UTLS'!B:N,13,FALSE),"N/A")
Note on GU6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: FORMULA DIFERENTE: =SEERRO( ÍNDICE( FILTER(AS6:AY6; ÉNÚM(AS6:AY6)); CONT.VALORES(FILTER(AS6:AY6; ÉNÚM(AS6:AY6))) ); AY6 )
Note on BE36: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: FÓRMULA DIFERENTE =SEERRO( ÍNDICE( FILTER(AE36:BD36; ÉNÚM(AE36:BD36)); CONT.VALORES(FILTER(AE36:BD36; ÉNÚM(AE36:BD36))) ); BD36 )
Note on GU68: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: FÓRMULA DIFERENTE =SEERRO( ÍNDICE( FILTER(DB68:DS68; ÉNÚM(DB68:DS68)); CONT.VALORES(FILTER(DB68:DS68; ÉNÚM(DB68:DS68))) ); D68 )
Note on EQ88: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: FÓRMULA DIFERENTE: =SEERRO( ÍNDICE( FILTER(BX88:CI88; ÉNÚM(BX88:CI88)); CONT.VALORES(FILTER(BX88:CI88; ÉNÚM(BX88:CI88))) ); CI88 )
Note on GU88: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: FÓRMULA DIFERENTE: =SEERRO( ÍNDICE( FILTER(DW88:EP88; ÉNÚM(DW88:EP88)); CONT.VALORES(FILTER(DW88:EP88; ÉNÚM(DW88:EP88))) ); EP88 )
Note on FR94: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: FORMULA DIFERENTE: =SEERRO( ÍNDICE( FILTER(AL92:AP92; ÉNÚM(AL92:AP92)); CONT.VALORES(FILTER(AL92:AP92; ÉNÚM(AL92:AP92))) ); AP92 )
Note on HL94: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: FÓRMULA DIFERENTE: =SEERRO( ÍNDICE( FILTER(DU94:DZ94; ÉNÚM(DU94:DZ94)); CONT.VALORES(FILTER(DU94:DZ94; ÉNÚM(DU94:DZ94))) ); DZ94 )
Note on HL96: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: FÓRMULA DIFERENTE =SEERRO( ÍNDICE( FILTER(DU96:DZ96; ÉNÚM(DU96:DZ96)); CONT.VALORES(FILTER(DU96:DZ96; ÉNÚM(DU96:DZ96))) ); DZ96 )

## LOD 500 - OVERVIEW
| FILE NAME | VERSÃO ANALISADA ADMN/GUAR | VERSÃO ANALISADA COLO1 | ADMN | COLO1 | GUAR | VERSÃO ANALISADA COLO2/SITE (R24) | COLO2 | SITE | VERSÃO ANALISADA COLO3 (R24) | COLO3 | VERSÃO ANALISADA UTLS (R24) | UTLS | VERSÃO ANALISADA WASTE SHED (R24) | WASTE SHED
1 | ARCH ¦ ARCHITECTURE
2 | CPQ11-ARCH-ARCH-DATA-R24.rvt | V3 | V3 | 31% | 85% | N/A | V3 | 79% | N/A | V3 | 1% | N/A | N/A | N/A | N/A
3 | CPQ11-ARCH-ARCH-SITE-R24.rvt | V3 | N/A | N/A | N/A | 60% | V3 | N/A | 82% | N/A | N/A | V3 | 83% | V22 | 100%
8 | CPQ11-ARCH-FENC-SITE-R24.rvt | NOT PUBLISHED | N/A | N/A | N/A | NOT PUBLISHED | NOT PUBLISHED | N/A | NOT PUBLISHED | N/A | N/A | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED
9 | CPQ11-ARCH-METL-SITE-R24.rvt | V5 | N/A | N/A | N/A | 100% | V5 | N/A | 63% | N/A | N/A | V5 | 100% | V7 | 100%
10 | CPQ11-ARCH-WOOD-DATA-R24.rvt | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | N/A | NOT PUBLISHED | NOT PUBLISHED | N/A | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | N/A | N/A
11 | CPQ11-ARCH-HMET-DATA-R24.rvt | V10 | V10 | 100% | 100% | N/A | V11 | 100% | N/A | V12 | 100% | N/A | N/A | N/A | N/A
12 | CPQ11-ARCH-HMET-SITE-R24.rvt | V7 | N/A | N/A | N/A | 100% | V9 | N/A | 100% | N/A | N/A | V7 | 100% | N/A | N/A
13 | CPQ11-ARCH-HM90-DATA-R24.rvt | V7 | V7 | 100% | 100% | N/A | V8 | 100% | N/A | V1 | 100% | N/A | N/A | N/A | N/A
14 | CPQ11-ARCH-WMES-DATA-R24.rvt | V13 | V13 | 100% | 100% | N/A | V13 | 100% | N/A | V24 | 100% | N/A | N/A | N/A | N/A
15 | CPQ11-ARCH-CHAI-SITE-R24.rvt | N/A | N/A | N/A | N/A | N/A | V12 | N/A | 50% | N/A | N/A | V10 | 1% | N/A | N/A
16 | CPQ11-ARCH-FURN-DATA-R24.rvt | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | N/A | NOT PUBLISHED | NOT PUBLISHED | N/A | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | N/A | N/A
18 | CPQ11-ARCH-WTRP-DATA-R24.rvt | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | N/A | NOT PUBLISHED | NOT PUBLISHED | N/A | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | N/A | N/A
19 | CPQ11-ARCH-WTRP-SITE-R24.rvt | NOT PUBLISHED | N/A | N/A | N/A | NOT PUBLISHED | NOT PUBLISHED | N/A | NOT PUBLISHED | N/A | N/A | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED
20 | CPQ11-ARCH-OHCD-DATA-R24.rvt | V4 | N/A | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
21 | CPQ11-ARCH-BLPR-GUAR-R24.rvt | V1 | N/A | N/A | N/A | 1% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
22 | CPQ11-ARCH-FACD-DATA-R24.rvt | V22 | V22 | 100% | 100% | N/A | V23 | 100% | N/A | V3 | 46% | N/A | N/A | N/A | N/A
23 | CPQ11-ARCH-ROOF-DATA-R24.rvt | V27 | V26 | 100% | 100% | N/A | V27 | 100% | N/A | V30 | 100% | N/A | N/A | N/A | N/A
24 | CPQ11-ARCH-PART-SITE-R24.rvt | V2 | N/A | N/A | N/A | 1% | N/A | N/A | N/A | N/A | N/A | V2 | 17% | V13 | 100%
25 | CPQ11-ARCH-PART-C345-R24.rvt | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | V1 | 1% | N/A | N/A | N/A | N/A
26 | CPQ11-ARCH-PART-C12A-R24.rvt | V2 | V2 | 50% | 78% | N/A | V2 | 1% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
27 | CPQ11-ARCH-COMN-DATA-R24.rvt | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | N/A | NOT PUBLISHED | NOT PUBLISHED | N/A | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | N/A | N/A
28 | CPQ11-ARCH-SGNV-SITE-R24.rvt | NOT PUBLISHED | N/A | N/A | N/A | NOT PUBLISHED | NOT PUBLISHED | N/A | NOT PUBLISHED | N/A | N/A | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED
29 | CPQ11-ARCH-SGNH-SITE-R24.rvt | NOT PUBLISHED | N/A | N/A | N/A | NOT PUBLISHED | NOT PUBLISHED | N/A | NOT PUBLISHED | N/A | N/A | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED
30 | CPQ11-ARCH-CEIL-DATA-R24.rvt | V1 | V1 | 1% | 1% | N/A | V1 | 1% | N/A | V1 | 0% | N/A | N/A | N/A | N/A
31 | CPQ11-ARCH-CEIL-SITE-R24.rvt | V1 | N/A | N/A | N/A | 1% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
32 | CPQ11-ARCH-SHLV-DATA-R24.rvt | V1 | N/A | 8% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
33 | CPQ11-ARCH-STON-SITE-R24.rvt | N/A | N/A | N/A | N/A | N/A | V3 | N/A | 100% | N/A | N/A | N/A | N/A | N/A | N/A
34 | SYST-SYSTEMS ¦ INFRASTRUCTURE
35 | CPQ11-SYST-INFR-DATA-R24.rvt | V2 | V2 | 69% | 1% | N/A | V2 | 1% | N/A | V39 | 0% | N/A | N/A | N/A | N/A
36 | CPQ11-SYST-INFR-SITE-R24.rvt | V4 | N/A | N/A | N/A | 100% | V38 | N/A | 100% | N/A | N/A | V46 | 100% | N/A | N/A
37 | DAS-DISTRIBUTED ANTENN/A SYSTEM ¦ DEVICES
38 | CPQ11-DASM-DEVS-DATA-R24.rvt | V4 | V2 | 22% | 86% | N/A | V2 | 76% | N/A | V3 | 1% | N/A | N/A | N/A | N/A
39 | EPMS-ELECTRICAL POWER MAN/AGEMENT SYSTEM ¦ DEVICES
40 | CPQ11-EPMS-DEVS-DATA-R24.rvt | V14 | V1 | 100% | 1% | N/A | V1 | 1% | N/A | V1 | 100% | N/A | N/A | N/A | N/A
41 | CPQ11-EPMS-DEVS-SITE-R24.rvt | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | V11 | 100% | N/A | N/A
42 | ROIP-RADIO OVER IP ¦ DEVICES
43 | CPQ11-ROIP-DEVS-GUAR-R24.rvt | V2 | N/A | N/A | N/A | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
44 | CPQ11-ROIP-DEVS-DATA-R24.rvt | V1 | V2 | 88% | 66% | N/A | V2 | 1% | N/A | V3 | 1% | N/A | N/A | N/A | N/A
45 | TELECOM ¦ DEVICES
46 | CPQ11-TCOM-DEVS-SITE-R24.rvt | V13 | N/A | N/A | N/A | 100% | V1 | N/A | 82% | N/A | N/A | N/A | N/A | N/A | N/A
47 | CPQ11-TCOM-DEVS-DATA-R24.rvt | V3 | V2 | 98% | 79% | N/A | V3 | 1% | N/A | V3 | 1% | N/A | N/A | N/A | N/A
48 | BAS-BUILDING AUTOMATION SYSTEM ¦ INFRASTRUCTURE
49 | CPQ11-BASM-INFR-DATA-R24.rvt | V1 | V1 | 33% | 4% | N/A | V1 | 1% | N/A | V1 | 1% | N/A | N/A | N/A | N/A
50 | CPQ11-BASM-INFR-PUMP-R24.rvt | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | V3 | 100% | N/A | N/A
51 | BAS ¦ DEVICES
52 | CPQ11-BASM-DEVS-PUMP-R24.rvt | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | V14 | 100% | N/A | N/A
53 | CPQ11-BASM-DEVS-DATA-R24.rvt | V18 | V1 | 100% | 98% | N/A | V1 | 13% | N/A | V1 | 1% | N/A | N/A | N/A | N/A
54 | SCTY-SECURITY ¦ INFRASTRUCTURE
55 | CPQ11-SCTY-INFR-DATA-R24.rvt | V4 | V4 | 1% | 5% | N/A | V4 | 1% | N/A | V5 | 1% | N/A | N/A | N/A | N/A
56 | CPQ11-SCTY-INFR-SITE-R24.rvt | V3 | N/A | N/A | N/A | 47% | N/A | N/A | N/A | N/A | N/A | V2 | 70% | N/A | N/A
57 | SCTY ¦ DEVICES
58 | CPQ11-SCTY-DEVS-SITE-R24.rvt | V37 | N/A | N/A | N/A | 100% | V37 | N/A | 100% | N/A | N/A | V30 | 100% | N/A | N/A
59 | CPQ11-SCTY-DEVS-DATA-R24.rvt | V1 | V1 | 55% | 80% | N/A | V1 | 2% | N/A | V2 | 1% | N/A | N/A | N/A | N/A
60 | CPQ11-SCTY-GATE-SITE-R24.rvt | N/A | N/A | N/A | N/A | 0% | V4 | N/A | 25% | N/A | N/A | N/A | N/A | N/A | N/A
61 | ELEC-ELETRICAL
62 | CPQ11-ELEC-ELEC-SITE-R24.rvt | V1 | N/A | N/A | N/A | 1% | V1 | N/A | 1% | N/A | N/A | V1 | 1% | N/A | N/A
63 | CPQ11-ELEC-ELEC-DATA-R24.rvt | V4 | V4 | 1% | 1% | N/A | V4 | 1% | N/A | N/A | 0% | N/A | N/A | N/A | N/A
64 | SPDA ¦ PROTECTION SYSTEM ATMOSPHERIC DISCHARGE
65 | CPQ11-ELEC-SPDA-DATA-R24.rvt | V13 | V3 | 100% | 45% | N/A | V3 | 1% | N/A | V4 | 1% | N/A | N/A | N/A | N/A
66 | CPQ11-ELEC-SPDA-SITE-R24.rvt | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | V7 | 100% | N/A | N/A
67 | DALI-DIGITAL ADDRESSABLE LIGHTING INTERFACE-DEVICES
68 | CPQ11-DALI-DEVS-DATA-R24.rvt | V2 | V2 | 14% | 1% | N/A | V2 | 1% | N/A | V2 | 1% | N/A | N/A | N/A | N/A
69 | FALM-FIRE ALARM
70 | CPQ11-FALM-FALM-SITE-R24.rvt | V2 | N/A | N/A | N/A | 1% | V7 | N/A | 100% | N/A | N/A | V2 | 1% | N/A | N/A
71 | CPQ11-FALM-FALM-DATA-R24.rvt | V2 | V2 | 1% | 1% | N/A | V2 | 1% | N/A | N/A | 0% | N/A | N/A | N/A | N/A
72 | FPRT-FIRE PROTECTION
73 | CPQ11-FPRT-FPRT-SITE-R24.rvt | V3 | N/A | N/A | N/A | 1% | V3 | N/A | 1% | N/A | N/A | V3 | 1% | N/A | N/A
74 | CPQ11-FPRT-FPRT-DATA-R24.rvt | V4 | V4 | 1% | 1% | N/A | V4 | 1% | N/A | N/A | 0% | N/A | N/A | N/A | N/A
75 | CPQ11-FPRT-METK-UTLS-R24.rvt | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | V15 | 100% | N/A | N/A
76 | PLMB-PLUMBING
77 | CPQ11-PLMB-PLMB-SITE-R24.rvt | V2 | N/A | N/A | N/A | 1% | V1 | N/A | 3% | N/A | N/A | V2 | 1% | N/A | N/A
78 | CPQ11-PLMB-PLMB-DATA-R24.rvt | V1 | V1 | 1% | 1% | N/A | V1 | 1% | N/A | N/A | 0% | N/A | N/A | N/A | N/A
79 | CPQ11-PLMB-DIES-SITE-R24.rvt | N/A | N/A | N/A | N/A | N/A | V3 | N/A | 100% | N/A | N/A | N/A | N/A | N/A | N/A
80 | CPQ11-PLMB-NPWT-SITE-R24.rvt | N/A | N/A | N/A | N/A | N/A | V43 | N/A | 100% | N/A | N/A | V46 | 100% | N/A | N/A
81 | CPQ11-PLMB-NPWT-DATA-R24.rvt | V2 | V3 | 100% | 88% | N/A | V3 | 1% | N/A | V3 | 1% | N/A | N/A | N/A | N/A
82 | CPQ11-PLMB-METK-UTLS-R24.rvt | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | V28 | 100% | N/A | N/A
83 | MECH-MECHANICAL
84 | CPQ11-MECH-MECH-DATA-R24.rvt | V5 | V2 | 73% | 25% | N/A | V4 | 1% | N/A | V5 | 1% | N/A | N/A | N/A | N/A
85 | CPQ11-MECH-MECH-GUAR-R24.rvt | V23 | N/A | N/A | N/A | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
86 | LAND-LANDSCAPE
87 | CPQ11-LAND-LAND-SITE-R24.rvt | NOT PUBLISHED | N/A | N/A | N/A | NOT PUBLISHED | NOT PUBLISHED | N/A | NOT PUBLISHED | N/A | N/A | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED
88 | CIVIL
89 | CPQ11-CIVL-DRNG-SITE-R24.rvt | N/A | N/A | N/A | N/A | N/A | V20 | N/A | 100% | N/A | N/A | V11 | 100% | N/A | N/A
90 | CPQ11-CIVL-ERTH-SITE-R24.rvt | V2 | N/A | N/A | N/A | 100% | V18 | N/A | 100% | N/A | N/A | V13 | 100% | N/A | N/A
91 | CPQ11-CIVL-PAVM-SITE-R24.rvt | N/A | N/A | N/A | N/A | N/A | V18 | N/A | 100% | N/A | N/A | V1 | 100% | N/A | N/A
92 | CPQ11-CIVL-SIGN-SITE-R24.rvt | NOT PUBLISHED | N/A | N/A | N/A | NOT PUBLISHED | NOT PUBLISHED | N/A | NOT PUBLISHED | N/A | N/A | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED
93 | CPQ11-CIVL-LOCK-SITE-R24.rvt | N/A | N/A | N/A | N/A | N/A | V11 | N/A | 100% | N/A | N/A | N/A | N/A | N/A | N/A
94 | STRC-STRUCTURE
95 | CPQ11-STRC-CONC-DATA-R24.rvt | V7 | V7 | 100% | 100% | N/A | V9 | 100% | N/A | V9 | 100% | N/A | N/A | N/A | N/A
96 | CPQ11-STRC-CONC-SITE-R24.rvt | V14 | N/A | N/A | N/A | 100% | V1 | N/A | 100% | N/A | N/A | V1 | 100% | V1 | 100%
97 | CPQ11-STRC-DPFN-DATA-R24.rvt | V8 | V8 | 100% | 100% | N/A | V10 | 100% | N/A | V10 | 100% | N/A | N/A | N/A | N/A
98 | CPQ11-STRC-DPFN-SITE-R24.rvt | V7 | N/A | N/A | N/A | 100% | N/A | N/A | N/A | N/A | N/A | V1 | 100% | V1 | 100%
99 | CPQ11-STRC-FLOO-DATA-R24.rvt | V3 | V3 | 100% | 100% | N/A | V3 | 100% | N/A | V3 | 100% | N/A | N/A | N/A | N/A
100 | CPQ11-STRC-FLOO-SITE-R24.rvt | V2 | N/A | N/A | N/A | 1% | N/A | N/A | 0% | N/A | N/A | V2 | 1% | V2 | 0%
101 | CPQ11-STRC-CHAI-SITE-R24.rvt | NOT PUBLISHED | N/A | N/A | N/A | NOT PUBLISHED | NOT PUBLISHED | N/A | NOT PUBLISHED | N/A | N/A | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED
102 | CPQ11-STRC-FENC-SITE-R24.rvt | NOT PUBLISHED | N/A | N/A | N/A | NOT PUBLISHED | NOT PUBLISHED | N/A | NOT PUBLISHED | N/A | N/A | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED
103 | CPQ11-STRC-STEE-ADMN-2X3.ifc | V8 | N/A | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
104 | CPQ11-STRC-STEE-COL1-2X3.ifc | N/A | N/A | N/A | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
105 | CPQ11-STRC-STEE-COL2-2X3.ifc | N/A | N/A | N/A | N/A | N/A | V6 | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
106 | CPQ11-STRC-STEE-COL3-2X3.ifc | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 100% | N/A | N/A | N/A | N/A
107 | CPQ11-STRC-STEE-COL4-2X3.ifc | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
108 | CPQ11-STRC-STEE-COL5-2X3.ifc | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
109 | CPQ11-STRC-STEE-UTLS-2X3.ifc | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | V5 | 100% | V6 | 100%
110 | CPQ11-STRC-STEE-GUAR-2X3.ifc | V6 | N/A | N/A | N/A | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
111 | CPQ11-STRC-STEE-STIR-2X3.ifc | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | V2 | 100% | N/A | N/A

## LOD 500 - ADMN
LOD 500 ¦ ADMN
| FILE NAME (R24) | FILE NAME (R22) | AREA | TRADE COMPANY | CODE | BIM COMPANY | CODE | ACC VERSION (R22) | ACC FILE DATE (R22) | ACC VERSION (R24) | ACC FILE DATE (R24) | VERSION | FILE DATE | RVT TYPE APROVAL (ADMN) | RESPONSAVEL | R0 - AUDIT STATUS | LAMPS QTDE - R0 | R0 - APPROVAL (%) | ESTIMATED DELIVERY R0(12/12/2025) | R1 - AUDIT STATUS | LAMPS QTDE RESOLVIDAS - R1 | R1 - APPROVAL (%) | R1 - NUVEM UTILIZADA | R2 - AUDIT STATUS | LAMPS QTDE RESOLVIDAS - R2 | R2 - APPROVAL (%) | NUVEM UTILIZADA | R3 - AUDIT STATUS | R3 - LAMPS QTDE RESOLVIDAS | R3 - APPROVAL (%) | R3 - NUVEM UTILIZADA | R4 - AUDIT STATUS | R4 - LAMPS QTDE RESOLVIDAS | R4 - NUVEM UTILIZADA | R4 - APPROVAL (%) | R5 - AUDIT STATUS | R5 - LAMPS QTDE RESOLVIDAS | R5 - NUVEM UTILIZADA | R5 - APPROVAL (%) | R6 - AUDIT STATUS | R6 - LAMPS QTDE RESOLVIDAS | R6 - APPROVAL (%) | R6 - NUVEM UTILIZADA | R7 - AUDIT STATUS | R7 - LAMPS QTDE RESOLVIDAS | R7 - APPROVAL (%) | R7 - NUVEM UTILIZADA | R8 - AUDIT STATUS | R8 - LAMPS QTDE RESOLVIDAS | R8 - APPROVAL (%) | R8 - NUVEM UTILIZADA | R9 - AUDIT STATUS | R9 - LAMPS QTDE RESOLVIDAS | R9 - APPROVAL (%) | R9 - NUVEM UTILIZADA | R10 - AUDIT STATUS | R10 - LAMPS QTDE RESOLVIDAS | R10 - APPROVAL (%) | R10 - NUVEM UTILIZADA | R11 - AUDIT STATUS | R11 - LAMPS QTDE RESOLVIDAS | R11 - APPROVAL (%) | R11 - NUVEM UTILIZADA | R12 - AUDIT STATUS | R12 - LAMPS QTDE RESOLVIDAS | R12 - APPROVAL (%) | R12 - NUVEM UTILIZADA | R13 - AUDIT STATUS | R13 - LAMPS QTDE RESOLVIDAS | R13 - APPROVAL (%) | R13 - NUVEM UTILIZADA | R14 - AUDIT STATUS | R14 - LAMPS QTDE RESOLVIDAS | R14 - APPROVAL (%) | R14 - NUVEM UTILIZADA | R15 - AUDIT STATUS | R15 - LAMPS QTDE RESOLVIDAS | R15 - APPROVAL (%) | R15 - NUVEM UTILIZADA | R16 - AUDIT STATUS | R16- LAMPS QTDE RESOLVIDAS | R16 - APPROVAL (%) | R16 - NUVEM UTILIZADA | R17 - AUDIT STATUS | R17- LAMPS QTDE RESOLVIDAS | R17 - APPROVAL (%) | R17 - NUVEM UTILIZADA | R18 - AUDIT STATUS | R18- LAMPS QTDE RESOLVIDAS | R18 - APPROVAL (%) | R18 - NUVEM UTILIZADA | R19 - AUDIT STATUS | R19- LAMPS QTDE RESOLVIDAS | R19 - APPROVAL (%) | R19 - NUVEM UTILIZADA | R20 - AUDIT STATUS | R20- LAMPS QTDE RESOLVIDAS | R20 - APPROVAL (%) | R20 - NUVEM UTILIZADA | R21 - AUDIT STATUS | R21- LAMPS QTDE RESOLVIDAS | R21 - APPROVAL (%) | R21 - NUVEM UTILIZADA | R22 - AUDIT STATUS | R22- LAMPS QTDE RESOLVIDAS | R22 - APPROVAL (%) | R22 - NUVEM UTILIZADA | R23 - AUDIT STATUS | R23- LAMPS QTDE RESOLVIDAS | R23 - APPROVAL (%) | R23 - NUVEM UTILIZADA | R24 - AUDIT STATUS | R24- LAMPS QTDE RESOLVIDAS | R24 - APPROVAL (%) | R24 - NUVEM UTILIZADA | R25 - AUDIT STATUS | R25- LAMPS QTDE RESOLVIDAS | R25 - APPROVAL (%) | R25 - NUVEM UTILIZADA
1 | ARCH ¦ ARCHITECTURE
27 | CPQ11-ROIP-DEVS-DATA-R24.rvt | CPQ11-ROIP-DEVS-DATA-R22.rvt | DATA | IB TECH | 1113 | IB TECH | 1113 | V36 | 08/05/2026 | V2 | 03/06/2026 | V1 | 19/05/2026 | R24 | FLAVIO | REPROVED | 34 | 1% | DONE | IMPROPER | 0 | IMPROPER |  | REPROVED | 0 | 1% | 2022-02-01 | OUTDATED | 0 | OUTDATED | 2022-02-01 | NEXT ROUND | 0 | NEXT ROUND | 2022-02-01 | NEXT ROUND | 0 | NEXT ROUND | 2022-02-01 | NEXT ROUND | 0 | NEXT ROUND | 2022-02-01 | NEXT ROUND | 0 | NEXT ROUND | 2022-02-01 | REPROVED | 7 | 20% | 2022-02-01 | NEXT ROUND | 7 | NEXT ROUND | 2022-02-01 | REPROVED | 15 | 44% | 4, 6, 22, 40 | NEXT ROUND | 15 | NEXT ROUND | 4, 6, 22, 40 | REPROVED | 30 | 88% | 4, 6, 22, 40 | NEXT ROUND | 15 | NEXT ROUND | 4, 6, 22, 40 | NEXT ROUND | 15 | NEXT ROUND | 4, 6, 22, 40 | NEXT ROUND | 15 | NEXT ROUND | 4, 6, 22, 40 | IMPROPER |  | IMPROPER | 4, 6, 22, 40 | IMPROPER |  | IMPROPER | 4, 6, 22, 40 | OUTDATED |  | OUTDATED | 4, 6, 22, 40 | NEXT ROUND |  | NEXT ROUND | 4, 6, 22, 40 | NEXT ROUND |  | NEXT ROUND | 4, 6, 22, 40 | NEXT ROUND |  | NEXT ROUND | 4, 6, 22, 40 | NEXT ROUND |  | NEXT ROUND | 4, 6, 22, 40 | NEXT ROUND |  | NEXT ROUND | 4, 6, 22, 40 | NEXT ROUND |  | NEXT ROUND | 4, 6, 22, 40 | ANALYSING |  | ANALYSING | 4, 6, 22, 40
37 | CPQ11-SCTY-DEVS-DATA-R24.rvt | CPQ11-SCTY-DEVS-DATA-R22.rvt | DATA | SEGURPRO | 1115 | SEGURPRO | 1115 | V40 | 06/05/2026 | V3 | 13/07/2026 | V1 | 20/05/2026 | R24 | FLAVIO | REPROVED | 38 | 1% | DONE | NEXT ROUND |  | NEXT ROUND |  | IMPROPER | 0 | IMPROPER |  | IMPROPER | 0 | IMPROPER |  | NEXT ROUND | 0 | NEXT ROUND |  | NEXT ROUND | 0 | NEXT ROUND |  | REPROVED | 10 | 26% | 24, 40 | NEXT ROUND |  | NEXT ROUND | 24, 40 | NEXT ROUND |  | NEXT ROUND | 24, 40 | NEXT ROUND |  | NEXT ROUND | 24, 40 | NEXT ROUND |  | NEXT ROUND | 24, 40 | NEXT ROUND |  | NEXT ROUND | 24, 40 | REPROVED | 18 | 47% | 24, 40 | OUTDATED | 18 | OUTDATED | 24, 40 | OUTDATED | 18 | OUTDATED | 24, 40 | NEXT ROUND | 18 | NEXT ROUND | 24, 40 | NEXT ROUND | 18 | NEXT ROUND | 24, 40 | NEXT ROUND | 18 | NEXT ROUND | 24, 40 | NEXT ROUND | 18 | NEXT ROUND | 24, 40 | NEXT ROUND | 18 | NEXT ROUND | 24, 40 | REPROVED | 21 | 55% | 24 FEDERADO-ADMN | OUTDATED | 21 | OUTDATED | 24 FEDERADO-ADMN | OUTDATED | 21 | OUTDATED | 24 FEDERADO-ADMN | OUTDATED | 21 | OUTDATED | 24 FEDERADO-ADMN | NEXT ROUND | 21 | NEXT ROUND | 24 FEDERADO-ADMN | ANALYSING | 21 | ANALYSING | 24 FEDERADO-ADMN
35 | CPQ11-SCTY-INFR-DATA-R24.rvt | CPQ11-SCTY-INFR-DATA-R22.rvt | DATA | MENDES HOLLER | 1112 | PGMAK | 1129 | V39 | 19/03/2026 | V5 | 10/07/2026 | V4 | 2026-06-26 | R24 | FLAVIO | REPROVED | 16 | 1% | DONE | IMPROPER | 0 | IMPROPER |  | OUTDATED | 0 | OUTDATED |  | OUTDATED | 0 | OUTDATED |  | NEXT ROUND | 0 | NEXT ROUND |  | NEXT ROUND | 0 | NEXT ROUND |  | NEXT ROUND | 0 | NEXT ROUND |  | NEXT ROUND | 0 | NEXT ROUND |  | IMPROPER |  | IMPROPER |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | REPROVED | 0 | 1% | 22, 40 | OUTDATED | 0 | OUTDATED | 22, 40 | OUTDATED | 0 | OUTDATED | 22, 40 | OUTDATED | 0 | OUTDATED | 22, 40 | NEXT ROUND | 0 | NEXT ROUND | 22, 40 | NEXT ROUND | 0 | NEXT ROUND | 22, 40 | NEXT ROUND | 0 | NEXT ROUND | 22, 40 | REPROVED | 0 | 1% | 22, 40 E FEDERADO ADMN | OUTDATED | 0 | OUTDATED | 22, 40 E FEDERADO ADMN | OUTDATED | 0 | OUTDATED | 22, 40 E FEDERADO ADMN | OUTDATED | 0 | OUTDATED | 22, 40 E FEDERADO ADMN | NEXT ROUND | 0 | NEXT ROUND | 22, 40 E FEDERADO ADMN | ANALYSING | 0 | ANALYSING | 22, 40 E FEDERADO ADMN
39 | CPQ11-ELEC-ELEC-DATA-R24.rvt | CPQ11-ELEC-ELEC-DATA-R22.rvt | DATA | MENDES HOLLER | 1112 | PGMAK | 1129 | V52 | 30/04/2026 | V4 | 06/07/2026 | V4 | 2026-07-06 | R24 | YASMIN | REPROVED | 60 | 1% | DONE | IMPROPER | 0 | IMPROPER |  | OUTDATED | 0 | OUTDATED |  | OUTDATED | 0 | OUTDATED |  | NEXT ROUND | 0 | NEXT ROUND |  | NEXT ROUND | 0 | NEXT ROUND |  | NEXT ROUND | 0 | NEXT ROUND |  | NEXT ROUND | 0 | NEXT ROUND |  | IMPROPER | 0 | IMPROPER |  | NEXT ROUND | 0 | NEXT ROUND |  | NEXT ROUND | 0 | NEXT ROUND |  | NEXT ROUND | 0 | NEXT ROUND |  | IMPROPER | 0 | IMPROPER |  | OUTDATED | 0 | OUTDATED |  | NEXT ROUND | 0 | NEXT ROUND |  | NEXT ROUND | 0 | NEXT ROUND |  | NEXT ROUND | 0 | NEXT ROUND |  | NEXT ROUND | 0 | NEXT ROUND |  | NEXT ROUND | 0 | NEXT ROUND |  | NEXT ROUND | 0 | NEXT ROUND |  | NEXT ROUND | 0 | NEXT ROUND |  | IMPROPER | 0 | IMPROPER |  | OUTDATED | 0 | OUTDATED |  | NEXT ROUND | 0 | NEXT ROUND |  | NEXT ROUND | 0 | NEXT ROUND |  | IMPROPER | 0 | IMPROPER
45 | CPQ11-FALM-FALM-DATA-R24.rvt | CPQ11-FALM-FALM-DATA-R22.rvt | DATA | MENDES HOLLER | 1112 | MENDES HOLLER | 1112 | V24 | 15/05/2026 | V2 | 06/07/2026 | V2 | 2026-07-06 | R24 | LUIZA | IMPROPER | 0 | 0% | DONE | IMPROPER |  | IMPROPER |  | OUTDATED |  | OUTDATED |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | REPROVED |  | 1% | 4, 6, 22, 24, 26, 40 | NEXT ROUND |  | NEXT ROUND | 4, 6, 22, 24, 26, 40 | NEXT ROUND |  | NEXT ROUND | 4, 6, 22, 24, 26, 40 | IMPROPER |  | IMPROPER | 4, 6, 22, 24, 26, 40 | NEXT ROUND |  | NEXT ROUND | 4, 6, 22, 24, 26, 40 | NEXT ROUND |  | NEXT ROUND | 4, 6, 22, 24, 26, 40 | IMPROPER |  | IMPROPER | 4, 6, 22, 24, 26, 40 | OUTDATED |  | OUTDATED | 4, 6, 22, 24, 26, 40 | OUTDATED |  | OUTDATED | 4, 6, 22, 24, 26, 40 | OUTDATED |  | OUTDATED | 4, 6, 22, 24, 26, 40 | OUTDATED |  | OUTDATED | 4, 6, 22, 24, 26, 40 | OUTDATED |  | OUTDATED | 4, 6, 22, 24, 26, 40 | NEXT ROUND |  | NEXT ROUND | 4, 6, 22, 24, 26, 40 | IMPROPER |  | IMPROPER
16 | CPQ11-ARCH-PART-C345-R24.rvt | CPQ11-ARCH-PART-C345-R22.rvt | C345 | IDEIA DRYWALL | 1101 | FCH | 1126 | V14 | 30/01/2026 | V1 | 19/05/2026 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A
58 | CPQ11-STRC-STEE-COL1-2X3.ifc | CPQ11-STRC-STEE-COL1-2X3.ifc | COL1 | METASA | 1125 | METASA | 1125 | V7 | 07/11/2025 | V1 | 21/05/2026 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A
59 | CPQ11-STRC-STEE-COL2-2X3.ifc | CPQ11-STRC-STEE-COL2-2X3.ifc | COL2 | METASA | 1125 | METASA | 1125 | V6 | 07/11/2025 | V1 | 21/05/2026 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A
60 | CPQ11-STRC-STEE-COL3-2X3.ifc | CPQ11-STRC-STEE-COL3-2X3.ifc | COL3 | METASA | 1125 | METASA | 1125 | V6 | 07/11/2025 | V1 | 21/05/2026 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A
61 | CPQ11-STRC-STEE-COL4-2X3.ifc | CPQ11-STRC-STEE-COL4-2X3.ifc | COL4 | METASA | 1125 | METASA | 1125 | V7 | 05/12/2025 | V1 | 21/05/2026 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A
62 | CPQ11-STRC-STEE-COL5-2X3.ifc | CPQ11-STRC-STEE-COL5-2X3.ifc | COL5 | METASA | 1125 | METASA | 1125 | V6 | 07/11/2025 | V1 | 21/05/2026 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A
21 | CPQ11-SYST-INFR-DATA-R24.rvt | CPQ11-SYST-INFR-DATA-R22.rvt | DATA | MENDES HOLLER | 1112 | PGMAK | 1129 | V40 | 10/04/2026 | V3 | 13/07/2026 | V2 | 2026-06-03 | R24 |  | REPROVED | 97 | 1% | DONE | IMPROPER | 0 | IMPROPER |  | OUTDATED | 0 | OUTDATED |  | OUTDATED | 0 | OUTDATED |  | NEXT ROUND | 0 | NEXT ROUND |  | NEXT ROUND | 0 | NEXT ROUND |  | NEXT ROUND | 0 | NEXT ROUND |  | NEXT ROUND | 0 | NEXT ROUND |  | NEXT ROUND | 0 | NEXT ROUND |  | NEXT ROUND | 0 | NEXT ROUND |  | NEXT ROUND | 0 | NEXT ROUND |  | NEXT ROUND | 0 | NEXT ROUND |  | REPROVED | 62 | 64% | 22,24, 40 | OUTDATED | 62 | OUTDATED | 22,24, 40 | OUTDATED | 62 | OUTDATED | 22,24, 40 | OUTDATED | 62 | OUTDATED | 22,24, 40 | OUTDATED | 62 | OUTDATED | 22,24, 40 | NEXT ROUND | 62 | NEXT ROUND | 22,24, 40 | REPROVED | 67 | 69% | FEDERADO - ADMIN | NEXT ROUND | 67 | NEXT ROUND | FEDERADO - ADMIN | IMPROPER | 67 | IMPROPER | FEDERADO - ADMIN | OUTDATED | 67 | OUTDATED | FEDERADO - ADMIN | OUTDATED | 67 | OUTDATED | FEDERADO - ADMIN | OUTDATED | 67 | OUTDATED | FEDERADO - ADMIN | OUTDATED | 67 | OUTDATED | FEDERADO - ADMIN | NEXT ROUND | 67 | NEXT ROUND | FEDERADO - ADMIN
31 | CPQ11-BASM-INFR-DATA-R24.rvt | CPQ11-BASM-INFR-DATA-R22.rvt | DATA | MENDES HOLLER | 1112 | PGMAK | 1129 | V33 | 04/03/2026 | V2 | 13/07/2026 | V1 | 2026-05-19 | R24 | CAROL | REPROVED | 36 | 1% | DONE | IMPROPER | 0 | IMPROPER |  | OUTDATED | 0 | OUTDATED |  | OUTDATED | 0 | OUTDATED |  | OUTDATED | 0 | OUTDATED |  | OUTDATED | 0 | OUTDATED |  | NEXT ROUND | 0 | NEXT ROUND |  | NEXT ROUND | 0 | NEXT ROUND |  | NEXT ROUND | 0 | NEXT ROUND |  | NEXT ROUND | 0 | NEXT ROUND |  | NEXT ROUND | 0 | NEXT ROUND |  | NEXT ROUND | 0 | NEXT ROUND |  | REPROVED | 8 | 22% | 4, 6, 22, 24, 40 | OUTDATED | 8 | OUTDATED | 4, 6, 22, 24, 40 | OUTDATED | 8 | OUTDATED | 4, 6, 22, 24, 40 | OUTDATED | 8 | OUTDATED | 4, 6, 22, 24, 40 | OUTDATED | 8 | OUTDATED | 4, 6, 22, 24, 40 | NEXT ROUND | 8 | NEXT ROUND | 4, 6, 22, 24, 40 | NEXT ROUND | 8 | NEXT ROUND | 4, 6, 22, 24, 40 | NEXT ROUND | 8 | NEXT ROUND | 4, 6, 22, 24, 40 | REPROVED | 12 | 33% | 4, 6, 22, 24, 40 | OUTDATED | 12 | OUTDATED | 4, 6, 22, 24, 40 | OUTDATED | 12 | OUTDATED | 4, 6, 22, 24, 40 | OUTDATED | 12 | OUTDATED | 4, 6, 22, 24, 40 | OUTDATED | 12 | OUTDATED | 4, 6, 22, 24, 40 | NEXT ROUND | 12 | NEXT ROUND | 4, 6, 22, 24, 40
49 | CPQ11-PLMB-PLMB-DATA-R24.rvt | CPQ11-PLMB-PLMB-DATA-R22.rvt | DATA | MENDES HOLLER | 1112 | PGMAK | 1129 | V30 | 24/03/2026 | V2 | 13/07/2026 | V1 | 2026-05-19 | R24 | LUIZA | REPROVED | 4 | 1% | DONE | IMPROPER | 0 | IMPROPER |  | IMPROPER | 0 | IMPROPER |  | OUTDATED | 0 | OUTDATED |  | NEXT ROUND | 0 | NEXT ROUND |  | NEXT ROUND | 0 | NEXT ROUND |  | NEXT ROUND | 0 | NEXT ROUND |  | NEXT ROUND | 0 | NEXT ROUND |  | NEXT ROUND | 0 | NEXT ROUND |  | NEXT ROUND | 0 | NEXT ROUND |  | NEXT ROUND | 0 | NEXT ROUND |  | IMPROPER |  | IMPROPER |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | IMPROPER |  | IMPROPER |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | NEXT ROUND |  | NEXT ROUND
5 | CPQ11-ARCH-WOOD-DATA-R24.rvt | CPQ11-ARCH-WOOD-DATA-R22.rvt | DATA | MADEPISO | 0000 | MADEPISO | 0000 | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | N/A | NOT PUBLISHED | N/A | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED
20 | SYST-SYSTEMS ¦ INFRASTRUCTURE
9 | CPQ11-ARCH-FURN-DATA-R24.rvt | CPQ11-ARCH-FURN-DATA-R22.rvt | DATA | RACIONAL | 1106 | CONTRACTING | 0000 | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | N/A | NOT PUBLISHED | N/A | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED
22 | DAS-DISTRIBUTED ANTENN/A SYSTEM ¦ DEVICES
10 | CPQ11-ARCH-WTRP-DATA-R24.rvt | CPQ11-ARCH-WTRP-DATA-R22.rvt | DATA | ITS | 1107 | RBV | 0000 | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | N/A | NOT PUBLISHED | N/A | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED
24 | EPMS-ELECTRICAL POWER MAN/AGEMENT SYSTEM ¦ DEVICES
17 | CPQ11-ARCH-COMN-DATA-R24.rvt | CPQ11-ARCH-COMN-DATA-R22.rvt | DATA | CONTRACTING | 0000 | CONTRACTING | 0000 | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | N/A | NOT PUBLISHED | N/A | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED
26 | ROIP-RADIO OVER IP ¦ DEVICES
47 | CPQ11-FPRT-FPRT-DATA-R24.rvt | CPQ11-FPRT-FPRT-DATA-R22.rvt | DATA | MENDES HOLLER | 1112 | MENDES HOLLER | 1112 | V17 | 14/05/2026 | V4 | 25/06/2026 | V4 | 2026-06-25 | R24 | FLAVIO | REPROVED | 24 | 1% | DONE | IMPROPER | 0 | IMPROPER |  | OUTDATED | 0 | OUTDATED |  | NEXT ROUND | 0 | NEXT ROUND |  | NEXT ROUND | 0 | NEXT ROUND |  | IMPROPER | 0 | IMPROPER |  | NEXT ROUND | 0 | NEXT ROUND |  | NEXT ROUND | 0 | NEXT ROUND |  | NEXT ROUND | 0 | NEXT ROUND |  | NEXT ROUND | 0 | NEXT ROUND |  | NEXT ROUND | 0 | NEXT ROUND |  | NEXT ROUND | 0 | NEXT ROUND |  | NEXT ROUND | 0 | NEXT ROUND |  | NEXT ROUND | 0 | NEXT ROUND |  | NEXT ROUND | 0 | NEXT ROUND |  | IMPROPER |  | IMPROPER |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | IMPROPER |  | IMPROPER |  | IMPROPER |  | IMPROPER |  | NEXT ROUND |  | NEXT ROUND |  | IMPROPER |  | IMPROPER |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED
28 | TELECOM ¦ DEVICES
19 | CPQ11-ARCH-SHLV-DATA-R24.rvt | CPQ11-ARCH-SHLV-DATA-R22.rvt | DATA | ALTAMIRA | 0000 | ALTAMIRA | 0000 | V9 | 28/02/2026 | V1 | 20/05/2026 | V1 | 2026-05-20 | R24 | CAROL | REPROVED | 13 | 1% | DONE | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | REPROVED | 1 | 8% | 22, 24, 40 | OUTDATED |  | OUTDATED | 22, 24, 40 | OUTDATED |  | OUTDATED | 22, 24, 40 | OUTDATED |  | OUTDATED | 22, 24, 40 | OUTDATED |  | OUTDATED | 22, 24, 40 | OUTDATED |  | OUTDATED | 22, 24, 40 | OUTDATED |  | OUTDATED | 22, 24, 40 | OUTDATED |  | OUTDATED | 22, 24, 40 | OUTDATED |  | OUTDATED | 22, 24, 40 | OUTDATED |  | OUTDATED | 22, 24, 40 | OUTDATED |  | OUTDATED | 22, 24, 40 | NEXT ROUND |  | NEXT ROUND | 22, 24, 40 | NEXT ROUND |  | NEXT ROUND | 22, 24, 40 | NEXT ROUND |  | NEXT ROUND | 22, 24, 40 | NEXT ROUND |  | NEXT ROUND | 22, 24, 40 | IMPROPER |  | IMPROPER | 22, 24, 40 | OUTDATED |  | OUTDATED | 22, 24, 40 | OUTDATED |  | OUTDATED | 22, 24, 40 | OUTDATED |  | OUTDATED | 22, 24, 40 | OUTDATED |  | OUTDATED | 22, 24, 40
30 | BAS-BUILDING AUTOMATION SYSTEM ¦ INFRASTRUCTURE
2 | CPQ11-ARCH-ARCH-DATA-R24.rvt | CPQ11-ARCH-ARCH-DATA-R22.rvt | DATA | ARE ARQUITETURA | 1130 | ARE ARQUITETURA | 1130 | V29 | 13/04/2026 | V3 | 03/06/2026 | V3 | 2026-06-03 | R24 | FLAVIO | REPROVED | 68 | 1% | DONE | IMPROPER | 0 | IMPROPER |  | OUTDATED | 0 | OUTDATED |  | OUTDATED | 0 | OUTDATED |  | NEXT ROUND | 0 | NEXT ROUND |  | NEXT ROUND | 0 | NEXT ROUND |  | NEXT ROUND | 0 | NEXT ROUND |  | NEXT ROUND | 0 | NEXT ROUND |  | NEXT ROUND | 0 | NEXT ROUND |  | REPROVED | 11 | 16% | 40 | OUTDATED | 11 | OUTDATED | 40 | NEXT ROUND | 11 | NEXT ROUND | 40 | REPROVED | 15 | 23% | 40 | OUTDATED | 15 | OUTDATED | 40 | OUTDATED | 15 | OUTDATED | 40 | OUTDATED | 15 | OUTDATED | 40 | OUTDATED | 15 | OUTDATED | 40 | NEXT ROUND | 15 | NEXT ROUND | 40 | NEXT ROUND | 15 | NEXT ROUND | 40 | REPROVED | 21 | 31% | FEDERADO - ADMN | IMPROPER | 21 | IMPROPER | FEDERADO - ADMN | OUTDATED | 21 | OUTDATED | FEDERADO - ADMN | OUTDATED | 21 | OUTDATED | FEDERADO - ADMN | OUTDATED | 21 | OUTDATED | FEDERADO - ADMN | OUTDATED | 21 | OUTDATED | FEDERADO - ADMN | OUTDATED | 21 | OUTDATED | FEDERADO - ADMN
32 | BAS ¦ DEVICES
18 | CPQ11-ARCH-CEIL-DATA-R24.rvt | CPQ11-ARCH-CEIL-DATA-R22.rvt | DATA | IDEIA DRYWALL | 1101 | T2B | 0000 | V4 | 29/04/2026 | V1 | 04/06/2026 | V1 | 04/06/2026 | R24 | LUIZA | IMPROPER | 40 | IMPROPER | DONE | IMPROPER | 0 | IMPROPER |  | IMPROPER | 0 | IMPROPER |  | IMPROPER | 0 | IMPROPER |  | OUTDATED | 0 | OUTDATED |  | OUTDATED | 0 | OUTDATED |  | NEXT ROUND | 0 | NEXT ROUND |  | NEXT ROUND | 0 | NEXT ROUND |  | REPROVED | 0 | 1% | 24, 40 | NEXT ROUND | 0 | NEXT ROUND | 24, 40 | NEXT ROUND | 0 | NEXT ROUND | 24, 40 | NEXT ROUND | 0 | NEXT ROUND | 24, 40 | NEXT ROUND | 0 | NEXT ROUND | 24, 40 | NEXT ROUND | 0 | NEXT ROUND | 24, 40 | NEXT ROUND | 0 | NEXT ROUND | 24, 40 | IMPROPER |  | IMPROPER |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | IMPROPER |  | IMPROPER |  | OUTDATED |  | OUTDATED |  | IMPROPER |  | IMPROPER |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED
34 | SCTY-SECURITY ¦ INFRASTRUCTURE
43 | CPQ11-DALI-DEVS-DATA-R24.rvt | CPQ11-DALI-DEVS-DATA-R22.rvt | DATA | AUTOBRÁS | 1116 | AUTOBRÁS | 1116 | V15 | 15/04/2026 | V2 | 02/06/2026 | V2 | 2026-06-02 | R24 | CAROL | IMPROPER | 0 | IMPROPER | DONE | OUTDATED |  | OUTDATED |  | REPROVED | 55 | 1% | 1, 2, 4, 6, 22, 24 | OUTDATED | 55 | OUTDATED | 1, 2, 4, 6, 22, 24 | OUTDATED | 55 | OUTDATED | 1, 2, 4, 6, 22, 24 | OUTDATED | 55 | OUTDATED | 1, 2, 4, 6, 22, 24 | OUTDATED |  | OUTDATED | 1, 2, 4, 6, 22, 24 | OUTDATED |  | OUTDATED | 1, 2, 4, 6, 22, 24 | OUTDATED |  | OUTDATED | 1, 2, 4, 6, 22, 24 | NEXT ROUND |  | NEXT ROUND | 1, 2, 4, 6, 22, 24 | NEXT ROUND |  | NEXT ROUND | 1, 2, 4, 6, 22, 24 | IMPROPER |  | IMPROPER |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | REPROVED | 8 | 14% | 4, 6, 22, 24, 26, 40 | OUTDATED | 8 | OUTDATED | 4, 6, 22, 24, 26, 40 | OUTDATED | 8 | OUTDATED | 4, 6, 22, 24, 26, 40 | OUTDATED | 8 | OUTDATED | 4, 6, 22, 24, 26, 40 | OUTDATED | 8 | OUTDATED | 4, 6, 22, 24, 26, 40 | NEXT ROUND | 8 | NEXT ROUND | 4, 6, 22, 24, 26, 40 | IMPROPER | 8 | IMPROPER | 4, 6, 22, 24, 26, 40 | OUTDATED | 8 | OUTDATED | 4, 6, 22, 24, 26, 40 | OUTDATED | 8 | OUTDATED | 4, 6, 22, 24, 26, 40 | OUTDATED | 8 | OUTDATED | 4, 6, 22, 24, 26, 40 | OUTDATED | 8 | OUTDATED | 4, 6, 22, 24, 26, 40 | OUTDATED | 8 | OUTDATED | 4, 6, 22, 24, 26, 40
36 | SCTY ¦ DEVICES
15 | CPQ11-ARCH-PART-C12A-R24.rvt | CPQ11-ARCH-PART-C12A-R22.rvt | C12A | IDEIA DRYWALL | 1101 | FCH | 1126 | V24 | 07/04/2026 | V2 | 27/05/2026 | V2 | 2026-05-27 | R24 | FLAVIO | REPROVED | 127 | 1% | DONE | IMPROPER | 0 | IMPROPER |  | IMPROPER | 0 | IMPROPER |  | IMPROPER | 0 | IMPROPER |  | NEXT ROUND | 0 | NEXT ROUND |  | NEXT ROUND | 0 | NEXT ROUND |  | REPROVED | 17 | 13% | 24, 40 | OUTDATED |  | OUTDATED | 24, 40 | OUTDATED |  | OUTDATED | 24, 40 | OUTDATED |  | OUTDATED | 24, 40 | OUTDATED |  | OUTDATED | 24, 40 | REPROVED | 29 | 22% | 24, 26, 40 | OUTDATED | 29 | OUTDATED | 24, 26, 40 | OUTDATED | 29 | OUTDATED | 24, 26, 40 | OUTDATED | 29 | OUTDATED | 24, 26, 40 | OUTDATED | 29 | OUTDATED | 24, 26, 40 | OUTDATED | 29 | OUTDATED | 24, 26, 40 | IMPROPER | 29 | IMPROPER | 24, 26, 40 | NEXT ROUND | 29 | NEXT ROUND | 24, 26, 40 | NEXT ROUND | 29 | NEXT ROUND | 24, 26, 40 | IMPROPER | 29 | IMPROPER | 24, 26, 40 | REPROVED | 64 | 50% | FEDERADO - ADMN | OUTDATED | 64 | OUTDATED | FEDERADO - ADMN | OUTDATED | 64 | OUTDATED | FEDERADO - ADMN | OUTDATED | 64 | OUTDATED | FEDERADO - ADMN | OUTDATED | 64 | OUTDATED | FEDERADO - ADMN
38 | ELEC-ELETRICAL
52 | CPQ11-MECH-MECH-DATA-R24.rvt | CPQ11-MECH-MECH-DATA-R22.rvt | DATA | STARCENTER | 1118 | STARCENTER | 1118 | V59 | 17/04/2026 | V5 | 06/07/2026 | V5 | 2026-07-06 | R24 | LUIZA | REPROVED | 37 | 1% | DONE | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | NEXT ROUND |  | NEXT ROUND |  | REPROVED | 2 | 5% |  | NEXT ROUND | 2 | NEXT ROUND |  | NEXT ROUND | 2 | NEXT ROUND |  | NEXT ROUND | 2 | NEXT ROUND |  | REPROVED | 9 | 24% | 04, 22, 26, 24, 40 | OUTDATED | 9 | OUTDATED | 04, 22, 26, 24, 40 | OUTDATED | 9 | OUTDATED | 04, 22, 26, 24, 40 | OUTDATED | 9 | OUTDATED | 04, 22, 26, 24, 40 | OUTDATED | 9 | OUTDATED | 04, 22, 26, 24, 40 | IMPROPER | 9 | IMPROPER | 04, 22, 26, 24, 40 | NEXT ROUND | 9 | NEXT ROUND | 04, 22, 26, 24, 40 | REPROVED | 16 | 43% | FEDERADO ADMN - 26 | OUTDATED | 16 | OUTDATED | FEDERADO ADMN - 26 | OUTDATED | 16 | OUTDATED | FEDERADO ADMN - 26 | OUTDATED | 16 | OUTDATED | FEDERADO ADMN - 26 | NEXT ROUND | 16 | NEXT ROUND | FEDERADO ADMN - 26 | REPROVED | 27 | 73% | FEDERADO ADMN - 26 | IMPROPER | 27 | IMPROPER | FEDERADO ADMN - 26
40 | SPDA ¦ PROTECTION SYSTEM ATMOSPHERIC DISCHARGE
56 | CPQ11-STRC-FLOO-DATA-R24.rvt | CPQ11-STRC-FLOO-DATA-R22.rvt | DATA | MODAX | 1121 | MODAX | 1121 | V1 | 05/05/2026 | V3 | 20/06/2026 | V3 | 2026-06-20 | R24 | FLAVIO | NOT PUBLISHED | N/A | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NEXT ROUND |  | 0% |  | NEXT ROUND |  | 0% |  | NEXT ROUND |  | 0% |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | REPROVED |  | 1% | FEDERADA, MODELO DE STEEL E ARCH | APPROVED | 5 | 100% | FEDERADA, MODELO DE STEEL E ARCH | PREVIOUSLY APPROVED | 5 | 100% | FEDERADA, MODELO DE STEEL E ARCH | PREVIOUSLY APPROVED | 5 | 100% | FEDERADA, MODELO DE STEEL E ARCH
42 | DALI-DIGITAL ADDRESSABLE LIGHTING INTERFACE-DEVICES
6 | CPQ11-ARCH-HMET-DATA-R24.rvt | CPQ11-ARCH-HMET-DATA-R22.rvt | DATA | S-VALE | 1104 | SPBIM | 1127 | V12 | 08/04/2026 | V1 | 15/05/2026 | V10 | 26/01/2026 | R22 |  | REPROVED | 23 | 1% | DONE | NEXT ROUND |  | NEXT ROUND |  | APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100%
44 | FALM-FIRE ALARM
7 | CPQ11-ARCH-HM90-DATA-R24.rvt | CPQ11-ARCH-HM90-DATA-R22.rvt | DATA | ZEUS/PORTEX | 1105 | SPBIM | 1127 | V9 | 27/03/2026 | V2 | 26/06/2026 | V7 | 23/01/2026 | R22 |  | REPROVED | 3 | 1% | DONE | NEXT ROUND |  | NEXT ROUND |  | APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100%
46 | FPRT-FIRE PROTECTION
8 | CPQ11-ARCH-WMES-DATA-R24.rvt | CPQ11-ARCH-WMES-DATA-R22.rvt | DATA | S-VALE | 1104 | SPBIM | 1127 | V13 | 02/03/2026 | V3 | 24/06/2026 | V13 | 02/03/2026 | R22 |  | REPROVED | 1 | 1% | DONE | NEXT ROUND |  | NEXT ROUND |  | APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100%
48 | PLMB-PLUMBING
11 | CPQ11-ARCH-OHCD-DATA-R24.rvt | CPQ11-ARCH-OHCD-DATA-R22.rvt | DATA | MEGADOORS | 1108 | SPBIM | 1127 | V4 | 10/04/2026 | V2 | 04/06/2026 | V4 | 2026-04-10 | R22 |  | NOT PUBLISHED | N/A | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NEXT ROUND |  | 0% |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | APPROVED |  | 100% | 40 | PREVIOUSLY APPROVED |  | 100% | 40 | PREVIOUSLY APPROVED |  | 100% | 40 | PREVIOUSLY APPROVED |  | 100% | 40 | PREVIOUSLY APPROVED |  | 100% | 40 | PREVIOUSLY APPROVED |  | 100% | 40 | PREVIOUSLY APPROVED |  | 100% | 40 | PREVIOUSLY APPROVED |  | 100% | 40 | PREVIOUSLY APPROVED |  | 100% | 40 | PREVIOUSLY APPROVED |  | 100% | 40 | PREVIOUSLY APPROVED |  | 100% | 40 | PREVIOUSLY APPROVED |  | 100% | 40 | PREVIOUSLY APPROVED |  | 100% | 40 | PREVIOUSLY APPROVED |  | 100% | 40 | PREVIOUSLY APPROVED |  | 100% | 40
12 | CPQ11-ARCH-FACD-DATA-R24.rvt | CPQ11-ARCH-FACD-DATA-R22.rvt | DATA | OMNITRADE | 1110 | CADBIM | 1128 | V25 | 06/05/2026 | V3 | 07/07/2026 | V22 | 2026-03-19 | R22 | LUIZA | REPROVED | 9 | 1% | DONE | IMPROPER | 0 | IMPROPER |  | NEXT ROUND | 0 | NEXT ROUND |  | REPROVED | 0 | 1% | 26 e 27 | NEXT ROUND | 0 | NEXT ROUND | 26 e 27 | NEXT ROUND | 0 | NEXT ROUND | 26 e 27 | REPROVED | 1 | 11% | 26 e 27 | NEXT ROUND | 1 | NEXT ROUND | 26 e 27 | REPROVED | 5 | 55% | 26 e 27 | APPROVED | 9 | 100% | 26 e 27 | PREVIOUSLY APPROVED | 9 | 100% | 26 e 27 | PREVIOUSLY APPROVED | 9 | 100% | 26 e 27 | PREVIOUSLY APPROVED | 9 | 100% | 26 e 27 | PREVIOUSLY APPROVED | 9 | 100% | 26 e 27 | PREVIOUSLY APPROVED | 9 | 100% | 26 e 27 | PREVIOUSLY APPROVED | 9 | 100% | 26 e 27 | PREVIOUSLY APPROVED | 9 | 100% | 26 e 27 | PREVIOUSLY APPROVED | 9 | 100% | 26 e 27 | PREVIOUSLY APPROVED | 9 | 100% | 26 e 27 | PREVIOUSLY APPROVED | 9 | 100% | 26 e 27 | PREVIOUSLY APPROVED | 9 | 100% | 26 e 27 | PREVIOUSLY APPROVED | 9 | 100% | 26 e 27 | PREVIOUSLY APPROVED | 9 | 100% | 26 e 27 | PREVIOUSLY APPROVED | 9 | 100% | 26 e 27 | PREVIOUSLY APPROVED | 9 | 100% | 26 e 27 | PREVIOUSLY APPROVED | 9 | 100% | 26 e 27
51 | MECH-MECHANICAL
13 | CPQ11-ARCH-ROOF-DATA-R24.rvt | CPQ11-ARCH-ROOF-DATA-R22.rvt | DATA | OMNITRADE | 1110 | CADBIM | 1128 | V30 | 26/03/2026 | V2 | 20/05/2026 | V27 | 2026-02-02 | R22 |  | REPROVED | 5 | 1% | DONE | IMPROPER | 0 | IMPROPER |  | REPROVED | 1 | 20% | 24 & 38 | APPROVED | 2 | 100% | 24 & 38 | PREVIOUSLY APPROVED | 2 | 100% | 24 & 38 | PREVIOUSLY APPROVED | 2 | 100% | 24 & 38 | PREVIOUSLY APPROVED | 2 | 100% | 24 & 38 | PREVIOUSLY APPROVED |  | 100% | 24 & 38 | PREVIOUSLY APPROVED |  | 100% | 24 & 38 | PREVIOUSLY APPROVED |  | 100% | 24 & 38 | PREVIOUSLY APPROVED |  | 100% | 24 & 38 | PREVIOUSLY APPROVED |  | 100% | 24 & 38 | PREVIOUSLY APPROVED |  | 100% | 24 & 38 | PREVIOUSLY APPROVED |  | 100% | 24 & 38 | PREVIOUSLY APPROVED |  | 100% | 24 & 38 | PREVIOUSLY APPROVED |  | 100% | 24 & 38 | PREVIOUSLY APPROVED |  | 100% | 24 & 38 | PREVIOUSLY APPROVED |  | 100% | 24 & 38 | PREVIOUSLY APPROVED |  | 100% | 24 & 38 | PREVIOUSLY APPROVED |  | 100% | 24 & 38 | PREVIOUSLY APPROVED |  | 100% | 24 & 38 | PREVIOUSLY APPROVED |  | 100% | 24 & 38 | PREVIOUSLY APPROVED |  | 100% | 24 & 38 | PREVIOUSLY APPROVED |  | 100% | 24 & 38 | PREVIOUSLY APPROVED |  | 100% | 24 & 38 | PREVIOUSLY APPROVED |  | 100% | 24 & 38
53 | STRC-STRUCTURE
25 | CPQ11-EPMS-DEVS-DATA-R24.rvt | CPQ11-EPMS-DEVS-DATA-R22.rvt | DATA | BLACKBOX | 1114 | BLACKBOX | 1114 | V15 | 27/04/2026 | V3 | 12/07/2026 | V14 | 2026-03-23 | R22 |  | REPROVED | 1 | 1% | DONE | APPROVED | 1 | 100% | 4 | PREVIOUSLY APPROVED | 1 | 100% | 4 | PREVIOUSLY APPROVED | 1 | 100% | 4 | PREVIOUSLY APPROVED | 1 | 100% | 4 | PREVIOUSLY APPROVED | 1 | 100% | 4 | PREVIOUSLY APPROVED | 1 | 100% | 4 | PREVIOUSLY APPROVED |  | 100% | 4 | PREVIOUSLY APPROVED |  | 100% | 4 | PREVIOUSLY APPROVED |  | 100% | 4 | PREVIOUSLY APPROVED |  | 100% | 4 | PREVIOUSLY APPROVED |  | 100% | 4 | PREVIOUSLY APPROVED |  | 100% | 4 | PREVIOUSLY APPROVED |  | 100% | 4 | PREVIOUSLY APPROVED |  | 100% | 4 | PREVIOUSLY APPROVED |  | 100% | 4 | PREVIOUSLY APPROVED |  | 100% | 4 | PREVIOUSLY APPROVED |  | 100% | 4 | PREVIOUSLY APPROVED |  | 100% | 4 | PREVIOUSLY APPROVED |  | 100% | 4 | PREVIOUSLY APPROVED |  | 100% | 4 | PREVIOUSLY APPROVED |  | 100% | 4 | PREVIOUSLY APPROVED |  | 100% | 4 | PREVIOUSLY APPROVED |  | 100% | 4 | PREVIOUSLY APPROVED |  | 100% | 4 | PREVIOUSLY APPROVED |  | 100% | 4
33 | CPQ11-BASM-DEVS-DATA-R24.rvt | CPQ11-BASM-DEVS-DATA-R22.rvt | DATA | BLACKBOX | 1114 | BLACKBOX | 1114 | V20 | 05/05/2026 | V2 | 12/07/2026 | V18 | 2026-03-26 | R22 | CAROL | REPROVED | 8 | 1% | DONE | NEXT ROUND |  | NEXT ROUND |  | REPROVED | 1 | 12.5% | 4, 6, 22, 24 | OUTDATED |  | OUTDATED | 4, 6, 22, 24 | OUTDATED |  | OUTDATED | 4, 6, 22, 24 | OUTDATED |  | OUTDATED | 4, 6, 22, 24 | REPROVED | 2 | 25% | 2024-06-04 | OUTDATED |  | OUTDATED | 2024-06-04 | OUTDATED |  | OUTDATED | 2024-06-04 | APPROVED | 17 | 100% | 4, 40 | PREVIOUSLY APPROVED | 17 | 100% | 4, 40 | PREVIOUSLY APPROVED | 17 | 100% | 4, 40 | PREVIOUSLY APPROVED | 17 | 100% | 4, 40 | PREVIOUSLY APPROVED | 17 | 100% | 4, 40 | PREVIOUSLY APPROVED | 17 | 100% | 4, 40 | PREVIOUSLY APPROVED | 17 | 100% | 4, 40 | PREVIOUSLY APPROVED | 17 | 100% | 4, 40 | PREVIOUSLY APPROVED | 17 | 100% | 4, 40 | PREVIOUSLY APPROVED | 17 | 100% | 4, 40 | PREVIOUSLY APPROVED | 17 | 100% | 4, 40 | PREVIOUSLY APPROVED | 17 | 100% | 4, 40 | PREVIOUSLY APPROVED | 17 | 100% | 4, 40 | PREVIOUSLY APPROVED | 17 | 100% | 4, 40 | PREVIOUSLY APPROVED | 17 | 100% | 4, 40 | PREVIOUSLY APPROVED | 17 | 100% | 4, 40 | PREVIOUSLY APPROVED | 17 | 100% | 4, 40
41 | CPQ11-ELEC-SPDA-DATA-R24.rvt | CPQ11-ELEC-SPDA-DATA-R22.rvt | DATA | MENDES HOLLER | 1112 | MENDES HOLLER | 1112 | V13 | 12/05/2026 | V5 | 13/07/2026 | V13 | 12/05/2026 | R22 | FLAVIO | REPROVED | 14 | 1% | DONE | IMPROPER | 0 | IMPROPER |  | REPROVED | 0 | 1% | 1,2,4,22,24 | OUTDATED | 0 | OUTDATED | 1,2,4,22,24 | NEXT ROUND | 0 | NEXT ROUND | 1,2,4,22,24 | NEXT ROUND | 0 | NEXT ROUND | 1,2,4,22,24 | NEXT ROUND | 0 | NEXT ROUND | 1,2,4,22,24 | NEXT ROUND | 0 | NEXT ROUND | 1,2,4,22,24 | REPROVED | 8 | 57% | 24, 40 | NEXT ROUND | 8 | NEXT ROUND | 24, 40 | NEXT ROUND | 8 | NEXT ROUND | 24, 40 | REPROVED | 13 | 92% | 24, 40 | NEXT ROUND | 13 | NEXT ROUND | 24, 40 | REPROVED | 13 | 93% | 24, 40 | NEXT ROUND | 13 | NEXT ROUND | 24, 40 | NEXT ROUND | 13 | NEXT ROUND | 24, 40 | NEXT ROUND | 13 | NEXT ROUND | 24, 40 | APPROVED | 13 | 100% | 24, 40 | PREVIOUSLY APPROVED | 13 | 100% | 24, 40 | PREVIOUSLY APPROVED | 13 | 100% | 24, 40 | PREVIOUSLY APPROVED | 13 | 100% | 24, 40 | PREVIOUSLY APPROVED | 13 | 100% | 24, 40 | PREVIOUSLY APPROVED | 13 | 100% | 24, 40 | PREVIOUSLY APPROVED | 13 | 100% | 24, 40 | PREVIOUSLY APPROVED | 13 | 100% | 24, 40 | PREVIOUSLY APPROVED | 13 | 100% | 24, 40
50 | CPQ11-PLMB-NPWT-DATA-R24.rvt | CPQ11-PLMB-NPWT-DATA-R22.rvt | DATA | STARCENTER | 1118 | STARCENTER | 1118 | V39 | 30/04/2026 | V3 | 01/07/2026 | V2 | 2026-05-22 | R24 | CAROL | REPROVED | 2 | 1% | DONE | REPROVED | 0 | 1% |  | IMPROPER | 0 | IMPROPER |  | IMPROPER | 0 | IMPROPER |  | OUTDATED | 0 | OUTDATED |  | OUTDATED | 0 | OUTDATED |  | NEXT ROUND | 0 | NEXT ROUND |  | NEXT ROUND | 0 | NEXT ROUND |  | NEXT ROUND | 0 | NEXT ROUND |  | IMPROPER |  | IMPROPER |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | NEXT ROUND |  | NEXT ROUND |  | REPROVED | 0 | 1% | 1940-06-04 | NEXT ROUND | 0 | NEXT ROUND | 1940-06-04 | NEXT ROUND | 0 | NEXT ROUND | 1940-06-04 | NEXT ROUND | 0 | NEXT ROUND | 1940-06-04 | REPROVED | 0 | 1% | FEDERADO ADMN | NEXT ROUND | 0 | NEXT ROUND | FEDERADO ADMN | NEXT ROUND | 0 | NEXT ROUND | FEDERADO ADMN | APPROVED | 2 | 100% | FEDERADO ADMN | PREVIOUSLY APPROVED | 2 | 100% | FEDERADO ADMN | PREVIOUSLY APPROVED | 2 | 100% | FEDERADO ADMN | PREVIOUSLY APPROVED | 2 | 100% | FEDERADO ADMN | PREVIOUSLY APPROVED | 2 | 100% | FEDERADO ADMN | PREVIOUSLY APPROVED | 2 | 100% | FEDERADO ADMN
54 | CPQ11-STRC-CONC-DATA-R24.rvt | CPQ11-STRC-CONC-DATA-R22.rvt | DATA | SERV OBRAS | 1120 | TENAX | 0000 | V10 | 22/04/2026 | V1 | 15/05/2026 | V7 | 10/12/2025 | R22 |  | APPROVED | 0 | 100% | DONE | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100%
55 | CPQ11-STRC-DPFN-DATA-R24.rvt | CPQ11-STRC-DPFN-DATA-R22.rvt | DATA | GEOFIX/TECNOGEO | 0000 | TENAX | 0000 | V11 | 28/04/2026 | V1 | 15/05/2026 | V8 | 2026-01-16 | R22 |  | APPROVED | 0 | 100% | DONE | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100%
57 | CPQ11-STRC-STEE-ADMN-2X3.ifc | CPQ11-STRC-STEE-ADMN-2X3.ifc | ADMN | METASA | 1125 | METASA | 1125 | V8 | 07/11/2025 | V1 | 21/05/2026 | V8 | 2025-11-07 | R22 |  | APPROVED | 0 | 100% | DONE | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100%
29 | CPQ11-TCOM-DEVS-DATA-R24.rvt | CPQ11-TCOM-DEVS-DATA-R22.rvt | DATA | BLACKBOX | 1114 | BLACKBOX | 1114 | V18 | 30/04/2026 | V3 | 29/06/2026 | V3 | 2026-06-29 | R24 | FLAVIO | REPROVED | 43 | 1% | DONE | REPROVED | 6 | 13.95% | 1, 2, 4, 22 e 24 | OUTDATED | 6 | OUTDATED | 1, 2, 4, 22 e 24 | OUTDATED | 6 | OUTDATED | 1, 2, 4, 22 e 24 | OUTDATED | 6 | OUTDATED | 1, 2, 4, 22 e 24 | NEXT ROUND | 6 | NEXT ROUND | 1, 2, 4, 22 e 24 | NEXT ROUND | 6 | NEXT ROUND | 1, 2, 4, 22 e 24 | NEXT ROUND |  | NEXT ROUND | 1, 2, 4, 22 e 24 | REPROVED | 31 | 72% | 24, 40 | OUTDATED | 31 | OUTDATED | 24, 40 | OUTDATED | 31 | OUTDATED | 24, 40 | NEXT ROUND | 31 | NEXT ROUND | 24, 40 | NEXT ROUND | 31 | NEXT ROUND | 24, 40 | REPROVED | 34 | 79% | 24, 40 | NEXT ROUND | 34 | NEXT ROUND | 24, 40 | REPROVED | 36 | 84% | 24, 40 | OUTDATED | 36 | OUTDATED | 24, 40 | NEXT ROUND | 36 | NEXT ROUND | 24, 40 | NEXT ROUND | 36 | NEXT ROUND | 24, 40 | NEXT ROUND | 36 | NEXT ROUND | 24, 40 | REPROVED | 40 | 93% | FEDERADA ADMN | OUTDATED | 40 | OUTDATED | FEDERADA ADMN | OUTDATED | 40 | OUTDATED | FEDERADA ADMN | NEXT ROUND | 40 | NEXT ROUND | FEDERADA ADMN | NEXT ROUND | 40 | NEXT ROUND | FEDERADA ADMN | REPROVED | 42 | 98% | FEDERADA ADMN
23 | CPQ11-DASM-DEVS-DATA-R24.rvt | CPQ11-DASM-DEVS-DATA-R22.rvt | DATA | IB TECH | 1113 | IB TECH | 1113 | V28 | 16/04/2026 | V4 | 26/06/2026 | V4 | 2026-06-26 | R22 | ALINNE | REPROVED | 9 | 1% | DONE | IMPROPER | 0 | IMPROPER |  | REPROVED | 4 | 44% | 2022-02-01 | NEXT ROUND | 4 | NEXT ROUND | 2022-02-01 | NEXT ROUND | 4 | NEXT ROUND | 2022-02-01 | NEXT ROUND | 4 | NEXT ROUND | 2022-02-01 | APPROVED | 9 | 100% | 2022-02-01 | PREVIOUSLY APPROVED |  | 100% | 2022-02-01 | PREVIOUSLY APPROVED |  | 100% | 2022-02-01 | PREVIOUSLY APPROVED |  | 100% | 2022-02-01 | PREVIOUSLY APPROVED |  | 100% | 2022-02-01 | PREVIOUSLY APPROVED |  | 100% | 2022-02-01 | PREVIOUSLY APPROVED |  | 100% | 2022-02-01 | PREVIOUSLY APPROVED |  | 100% | 2022-02-01 | PREVIOUSLY APPROVED |  | 100% | 2022-02-01 | PREVIOUSLY APPROVED |  | 100% | 2022-02-01 | PREVIOUSLY APPROVED |  | 100% | 2022-02-01 | PREVIOUSLY APPROVED |  | 100% | 2022-02-01 | PREVIOUSLY APPROVED |  | 100% | 2022-02-01 | PREVIOUSLY APPROVED |  | 100% | 2022-02-01 | PREVIOUSLY APPROVED |  | 100% | 2022-02-01 | PREVIOUSLY APPROVED |  | 100% | 2022-02-01 | PREVIOUSLY APPROVED |  | 100% | 2022-02-01 | PREVIOUSLY APPROVED |  | 100% | 2022-02-01 | PREVIOUSLY APPROVED |  | 100% | 2022-02-01 | REPROVED |  | 22% | 2022-02-01
Note on AX32: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: QUANTIDADE INICIAL DE LAMPADAS

## LOD 500 - COLO1
LOD 500 ¦ COLO1
| FILE NAME (R24) | FILE NAME (R22) | AREA | TRADE COMPANY | CODE | BIM COMPANY | CODE | ACC VERSION (R22) | ACC FILE DATE (R22) | ACC VERSION (R24) | ACC FILE DATE (R24) | VERSION | FILE DATE | RVT TYPE APROVAL (COLO1) | RESPONSAVEL | R0 - AUDIT STATUS | LAMPS QTDE | R0 - APPROVAL (%) | NUVEM UTILIZADA | ESTIMATED DELIVERY R0(12/12/2025) | R1 - AUDIT STATUS | LAMPS QTDE RESOLVIDAS - R1 | R1 - APPROVAL (%) | NUVEM UTILIZADA | R2 - AUDIT STATUS | LAMPS QTDE RESOLVIDAS - R2 | R2 - APPROVAL (%) | NUVEM UTILIZADA | R3 - AUDIT STATUS | LAMPS QTDE RESOLVIDAS - R3 | R3 - APPROVAL (%) | NUVEM UTILIZADA | R4 - AUDIT STATUS | LAMPS QTDE RESOLVIDAS - R4 | R4 - APPROVAL (%) | NUVEM UTILIZADA | R5 - AUDIT STATUS | LAMPS QTDE RESOLVIDAS - R5 | R5 - APPROVAL (%) | NUVEM UTILIZADA | R6 - AUDIT STATUS | LAMPS QTDE RESOLVIDAS - R6 | R6 - APPROVAL (%) | NUVEM UTILIZADA | R7 - AUDIT STATUS | LAMPS QTDE RESOLVIDAS - R7 | R7 - APPROVAL (%) | NUVEM UTILIZADA | R8 - AUDIT STATUS | R8 - LAMPS QTDE RESOLVIDAS | R8 - APPROVAL (%) | R8 - NUVEM UTILIZADA | R9 - AUDIT STATUS | R9 - LAMPS QTDE RESOLVIDAS | R9 - APPROVAL (%) | R9 - NUVEM UTILIZADA | R10 - AUDIT STATUS | R10 - LAMPS QTDE RESOLVIDAS | R10 - APPROVAL (%) | R10 - NUVEM UTILIZADA | R11 - AUDIT STATUS | R11 - LAMPS QTDE RESOLVIDAS | R11 - APPROVAL (%) | R11 - NUVEM UTILIZADA | R12 - AUDIT STATUS | R12 - LAMPS QTDE RESOLVIDAS | R12 - APPROVAL (%) | R12 - NUVEM UTILIZADA | R13 - AUDIT STATUS | R13 - LAMPS QTDE RESOLVIDAS | R13 - APPROVAL (%) | R13 - NUVEM UTILIZADA | R14 - AUDIT STATUS | R14 - LAMPS QTDE RESOLVIDAS | R14 - APPROVAL (%) | R14 - NUVEM UTILIZADA | R15 - AUDIT STATUS | R15 - LAMPS QTDE RESOLVIDAS | R15 - APPROVAL (%) | R15 - NUVEM UTILIZADA | R16 - AUDIT STATUS | R16 - LAMPS QTDE RESOLVIDAS | R16 - APPROVAL (%) | R16 - NUVEM UTILIZADA | R17 - AUDIT STATUS | R17- LAMPS QTDE RESOLVIDAS | R17 - APPROVAL (%) | R17 - NUVEM UTILIZADA | R18 - AUDIT STATUS | R18- LAMPS QTDE RESOLVIDAS | R18 - APPROVAL (%) | R18 - NUVEM UTILIZADA | R19 - AUDIT STATUS | R19- LAMPS QTDE RESOLVIDAS | R19 - APPROVAL (%) | R19 - NUVEM UTILIZADA | R20 - AUDIT STATUS | R20- LAMPS QTDE RESOLVIDAS | R20 - APPROVAL (%) | R20 - NUVEM UTILIZADA | R21 - AUDIT STATUS | R21- LAMPS QTDE RESOLVIDAS | R21 - APPROVAL (%) | R21 - NUVEM UTILIZADA | R22 - AUDIT STATUS | R22- LAMPS QTDE RESOLVIDAS | R22 - APPROVAL (%) | R22 - NUVEM UTILIZADA | R23 - AUDIT STATUS | R23- LAMPS QTDE RESOLVIDAS | R23 - APPROVAL (%) | R23 - NUVEM UTILIZADA | R24 - AUDIT STATUS | R24- LAMPS QTDE RESOLVIDAS | R24 - APPROVAL (%) | R24 - NUVEM UTILIZADA | R25 - AUDIT STATUS | R25- LAMPS QTDE RESOLVIDAS | R25 - APPROVAL (%) | R25 - NUVEM UTILIZADA
40 | CPQ11-ELEC-SPDA-DATA-R24.rvt | CPQ11-ELEC-SPDA-DATA-R22.rvt | DATA | MENDES HOLLER | 1112 | MENDES HOLLER | 1112 | V13 | 12/05/2026 | V5 | 13/07/2026 | V3 | 2026-06-25 | R24 | YASMIN | REPROVED | 38 | 1% |  | DONE | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | REPROVED | 0 | 1% | 15, 16, 23, 25, 31, 36, 39 | NEXT ROUND |  | NEXT ROUND |  | REPROVED | 0 | 1% | 12, 15, 16, 23, 25, 31, 36, 39 | NEXT ROUND |  | NEXT ROUND | 12, 15, 16, 23, 25, 31, 36, 39 | NEXT ROUND |  | NEXT ROUND | 12, 15, 16, 23, 25, 31, 36, 39 | IMPROPER |  | IMPROPER |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | REPROVED | 6 | 17% | 31, 36, 39, 42, 44 | REPROVED | 8 | 23% | 31, 36, 39, 42, 44 | NEXT ROUND | 8 | NEXT ROUND | 31, 36, 39, 42, 44 | NEXT ROUND | 8 | NEXT ROUND | 31, 36, 39, 42, 44 | NEXT ROUND | 8 | NEXT ROUND | 31, 36, 39, 42, 44 | NEXT ROUND | 8 | NEXT ROUND | 31, 36, 39, 42, 44 | NEXT ROUND | 8 | NEXT ROUND | 31, 36, 39, 42, 44 | REPROVED | 11 | 31% | FEDERADO COL1 | NEXT ROUND | 11 | NEXT ROUND | FEDERADO COL1 | REPROVED | 16 | 45% | FEDERADO COL1 | OUTDATED | 16 | OUTDATED | FEDERADO COL1 | IMPROPER | 16 | IMPROPER | FEDERADO COL1 | NEXT ROUND | 16 | NEXT ROUND | FEDERADO COL1 | ANALYSING | 16 | ANALYSING | FEDERADO COL1
22 | CPQ11-DASM-DEVS-DATA-R24.rvt | CPQ11-DASM-DEVS-DATA-R22.rvt | DATA | IB TECH | 1113 | IB TECH | 1113 | V28 | 16/04/2026 | V4 | 26/06/2026 | V2 | 2026-05-22 | R24 | CAROL | REPROVED | 30 | 1% |  | DONE | IMPROPER | 0 | IMPROPER |  | OUTDATED | 0 | OUTDATED |  | REPROVED | 0 | 1% | 5, 16, 22, 23, 25, 26, 31, 36, 39 | REPROVED | 3 | 15.78% | 23, 39 | OUTDATED |  | OUTDATED |  | NEXT ROUND |  | NEXT ROUND |  | REPROVED | 4 | 24.13% | 25, 26, 31, 36, 39 | REPROVED | 17 | 58% | 25, 26, 31, 36, 39, 42 | OUTDATED | 17 | OUTDATED | 25, 26, 31, 36, 39, 42 | REPROVED | 1 | 62% | 36, 39, 42 | REPROVED | 8 | 86% | 39, 42 | NEXT ROUND | 8 | NEXT ROUND | 39, 42 | NEXT ROUND | 8 | NEXT ROUND | 39, 42 | NEXT ROUND | 8 | NEXT ROUND | 39, 42 | NEXT ROUND | 8 | NEXT ROUND | 39, 42 | NEXT ROUND | 8 | NEXT ROUND | 39, 42 | REPROVED | 26 | 86% | FEDERADO COL1 | NEXT ROUND | 26 | NEXT ROUND | FEDERADO COL1 | NEXT ROUND | 26 | NEXT ROUND | FEDERADO COL1 | NEXT ROUND | 26 | NEXT ROUND | FEDERADO COL1 | NEXT ROUND | 26 | NEXT ROUND | FEDERADO COL1 | NEXT ROUND | 26 | NEXT ROUND | FEDERADO COL1 | NEXT ROUND | 26 | NEXT ROUND | FEDERADO COL1 | NEXT ROUND | 26 | NEXT ROUND | FEDERADO COL1 | ANALYSING | 26 | ANALYSING | FEDERADO COL1
24 | CPQ11-EPMS-DEVS-DATA-R24.rvt | CPQ11-EPMS-DEVS-DATA-R22.rvt | DATA | BLACKBOX | 1114 | BLACKBOX | 1114 | V15 | 27/04/2026 | V3 | 12/07/2026 | V1 | 2026-05-15 | R24 | LUIZA | REPROVED | 4 | 1% |  | DONE | REPROVED | 0 | 1% |  | OUTDATED | 0 | OUTDATED |  | OUTDATED | 0 | OUTDATED |  | OUTDATED | 0 | OUTDATED |  | OUTDATED | 0 | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | NEXT ROUND |  | NEXT ROUND |  | REPROVED | 0 | 1% | 36, 39 | OUTDATED | 0 | OUTDATED | 36, 39 | OUTDATED | 0 | OUTDATED | 36, 39 | OUTDATED | 0 | OUTDATED | 36, 39 | NEXT ROUND | 0 | NEXT ROUND | 36, 39 | NEXT ROUND | 0 | NEXT ROUND | 36, 39 | NEXT ROUND | 0 | NEXT ROUND | 36, 39 | REPROVED | 0 | 1% | FEDERADO COL1 | OUTDATED | 0 | OUTDATED | FEDERADO COL1 | OUTDATED | 0 | OUTDATED | FEDERADO COL1 | OUTDATED | 0 | OUTDATED | FEDERADO COL1 | OUTDATED | 0 | OUTDATED | FEDERADO COL1 | OUTDATED | 0 | OUTDATED | FEDERADO COL1 | NEXT ROUND | 0 | NEXT ROUND | FEDERADO COL1 | NEXT ROUND | 0 | NEXT ROUND | FEDERADO COL1 | ANALYSING | 0 | ANALYSING | FEDERADO COL1
51 | CPQ11-MECH-MECH-DATA-R24.rvt | CPQ11-MECH-MECH-DATA-R22.rvt | DATA | STARCENTER | 1118 | STARCENTER | 1118 | V59 | 17/04/2026 | V5 | 06/07/2026 | V2 | 2026-05-22 | R24 | LUIZA | REPROVED | 66 | 1% | 15, 16, 26, 27 | DONE | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | NEXT ROUND |  | NEXT ROUND | 15, 16, 26, 27 | REPROVED | 0 | 0 | 15, 16, 26, 27 | NEXT ROUND | 0 | NEXT ROUND | 15, 16, 26, 27 | REPROVED | 8 | 12% | 15, 16, 26, 27 | NEXT ROUND | 8 | NEXT ROUND | 15, 16, 26, 27 | NEXT ROUND | 8 | NEXT ROUND | 15, 16, 26, 27 | NEXT ROUND | 8 | NEXT ROUND | 15, 16, 26, 27 | NEXT ROUND | 8 | NEXT ROUND | 15, 16, 26, 27 | NEXT ROUND | 8 | NEXT ROUND | 15, 16, 26, 27 | NEXT ROUND | 8 | NEXT ROUND | 15, 16, 26, 27 | REPROVED | 15 | 22% | FEDERADO COL1 e 15 | NEXT ROUND | 15 | NEXT ROUND | FEDERADO COL1 e 15 | NEXT ROUND | 15 | NEXT ROUND | FEDERADO COL1 e 15 | NEXT ROUND | 15 | NEXT ROUND | FEDERADO COL1 e 15 | REPROVED | 17 | 25% | FEDERADO COL1 e 15 | OUTDATED | 17 | OUTDATED | FEDERADO COL1 e 15 | NEXT ROUND | 17 | NEXT ROUND | FEDERADO COL1 e 15 | NEXT ROUND | 17 | NEXT ROUND | FEDERADO COL1 e 15 | ANALYSING | 17 | ANALYSING | FEDERADO COL1 e 15
28 | CPQ11-TCOM-DEVS-DATA-R24.rvt | CPQ11-TCOM-DEVS-DATA-R22.rvt | DATA | BLACKBOX | 1114 | BLACKBOX | 1114 | V18 | 30/04/2026 | V3 | 29/06/2026 | V2 | 2026-05-18 | R24 |  | REPROVED | 88 | 1% | 16,23,36 | DONE | REPROVED | 32 | 36% | 16,23,36 | OUTDATED | 0 | OUTDATED | 16,23,36 | OUTDATED | 0 | OUTDATED | 16,23,36 | OUTDATED | 0 | OUTDATED |  | NEXT ROUND |  | NEXT ROUND |  | REPROVED | 15 | 53.4% | 16, 23, 24, 25, 26, 27, 31, 36 | OUTDATED |  | OUTDATED | 16, 23, 24, 25, 26, 27, 31, 36 | OUTDATED |  | OUTDATED | 16, 23, 24, 25, 26, 27, 31, 36 | OUTDATED |  | OUTDATED | 16, 23, 24, 25, 26, 27, 31, 36 | OUTDATED |  | OUTDATED | 16, 23, 24, 25, 26, 27, 31, 36 | NEXT ROUND |  | NEXT ROUND | 16, 23, 24, 25, 26, 27, 31, 36 | REPROVED | 69 | 79% | 25, 26, 27, 31, 36, 42, 44 | OUTDATED | 69 | OUTDATED | 25, 26, 27, 31, 36, 42, 44 | NEXT ROUND | 69 | NEXT ROUND | 25, 26, 27, 31, 36, 42, 44 | NEXT ROUND | 69 | NEXT ROUND | 25, 26, 27, 31, 36, 42, 44 | NEXT ROUND | 69 | NEXT ROUND | 25, 26, 27, 31, 36, 42, 44 | NEXT ROUND | 69 | NEXT ROUND | 25, 26, 27, 31, 36, 42, 44 | NEXT ROUND | 69 | NEXT ROUND | 25, 26, 27, 31, 36, 42, 44 | NEXT ROUND | 69 | NEXT ROUND | 25, 26, 27, 31, 36, 42, 44 | NEXT ROUND | 69 | NEXT ROUND | 25, 26, 27, 31, 36, 42, 44 | REPROVED | 69 | 79% | 39 E FEDERADO - COL1 | OUTDATED | 69 | OUTDATED | 39 E FEDERADO - COL1 | NEXT ROUND | 69 | NEXT ROUND | 39 E FEDERADO - COL1 | NEXT ROUND | 69 | NEXT ROUND | 39 E FEDERADO - COL1 | ANALYSING | 69 | ANALYSING | 39 E FEDERADO - COL1
36 | CPQ11-SCTY-DEVS-DATA-R24.rvt | CPQ11-SCTY-DEVS-DATA-R22.rvt | DATA | SEGURPRO | 1115 | SEGURPRO | 1115 | V40 | 06/05/2026 | V3 | 13/07/2026 | V1 | 2026-05-20 | R24 | LUIZA | REPROVED | 74 | 1% | 31, 36 & 23 | DONE | IMPROPER | 0 | IMPROPER |  | OUTDATED | 0 | OUTDATED |  | IMPROPER | 0 | IMPROPER | 16, 23, 31, 36 | NEXT ROUND |  | NEXT ROUND |  | REPROVED | 0 | 1% |  | REPROVED | 15 | 20% | 16, 23, 24, 26, 31, 36 | NEXT ROUND |  | NEXT ROUND | 16, 23, 24, 26, 31, 36 | NEXT ROUND |  | NEXT ROUND | 16, 23, 24, 26, 31, 36 | REPROVED | 20 | 28% | 23, 24, 26, 31, 36 | IMPROPER | 20 | IMPROPER | 23, 24, 26, 31, 36 | NEXT ROUND | 20 | NEXT ROUND | 23, 24, 26, 31, 36 | REPROVED | 56 | 80% | 23, 24, 31, 36, 39, 42, 44 | OUTDATED | 56 | OUTDATED | 23, 24, 31, 36, 39, 42, 44 | OUTDATED | 56 | OUTDATED | 23, 24, 31, 36, 39, 42, 44 | NEXT ROUND | 56 | NEXT ROUND | 23, 24, 31, 36, 39, 42, 44 | NEXT ROUND | 56 | NEXT ROUND | 23, 24, 31, 36, 39, 42, 44 | NEXT ROUND | 56 | NEXT ROUND | 23, 24, 31, 36, 39, 42, 44 | NEXT ROUND | 56 | NEXT ROUND | 23, 24, 31, 36, 39, 42, 44 | NEXT ROUND | 56 | NEXT ROUND | 23, 24, 31, 36, 39, 42, 44 | IMPROPER | 56 | IMPROPER | 23, 24, 31, 36, 39, 42, 44 | OUTDATED | 56 | OUTDATED | 23, 24, 31, 36, 39, 42, 44 | OUTDATED | 56 | OUTDATED | 23, 24, 31, 36, 39, 42, 44 | OUTDATED | 56 | OUTDATED | 23, 24, 31, 36, 39, 42, 44 | NEXT ROUND | 56 | NEXT ROUND | 23, 24, 31, 36, 39, 42, 44 | ANALYSING | 56 | ANALYSING | 23, 24, 31, 36, 39, 42, 44
34 | CPQ11-SCTY-INFR-DATA-R24.rvt | CPQ11-SCTY-INFR-DATA-R22.rvt | DATA | MENDES HOLLER | 1112 | PGMAK | 1129 | V39 | 19/03/2026 | V5 | 10/07/2026 | V4 | 2026-06-26 | R24 | LUIZA | REPROVED | 19 | 1% | 2, 6, 16, 22, 26 e 31 | DONE | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | IMPROPER | 0 | IMPROPER |  | OUTDATED |  | OUTDATED |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | REPROVED | 0 | 1% | 16, 22, 23, 31, 36 | OUTDATED | 0 | OUTDATED | 16, 22, 23, 31, 36 | OUTDATED | 0 | OUTDATED | 16, 22, 23, 31, 36 | OUTDATED | 0 | OUTDATED | 16, 22, 23, 31, 36 | OUTDATED | 0 | OUTDATED | 16, 22, 23, 31, 36 | OUTDATED | 0 | OUTDATED | 16, 22, 23, 31, 36 | OUTDATED | 0 | OUTDATED | 16, 22, 23, 31, 36 | OUTDATED | 0 | OUTDATED | 16, 22, 23, 31, 36 | NEXT ROUND | 0 | NEXT ROUND | 16, 22, 23, 31, 36 | REPROVED | 1 | 5% | 16, 22, 23, 31, 36 | OUTDATED | 1 | OUTDATED | 16, 22, 23, 31, 36 | NEXT ROUND | 1 | NEXT ROUND | 16, 22, 23, 31, 36 | IMPROPER | 1 | IMPROPER | 16, 22, 23, 31, 36 | OUTDATED | 1 | OUTDATED | 16, 22, 23, 31, 36 | IMPROPER | 1 | IMPROPER | 16, 22, 23, 31, 36 | NEXT ROUND | 1 | NEXT ROUND | 16, 22, 23, 31, 36 | ANALYSING | 1 | ANALYSING | 16, 22, 23, 31, 36
32 | CPQ11-BASM-DEVS-DATA-R24.rvt | CPQ11-BASM-DEVS-DATA-R22.rvt | DATA | BLACKBOX | 1114 | BLACKBOX | 1114 | V20 | 05/05/2026 | V2 | 12/07/2026 | V1 | 15/05/2026 | R24 | LUIZA | REPROVED | 57 | 1% | 5, 6, 12, 16, 31 | DONE | REPROVED | 24 | 42% | 5, 6, 12, 16, 31 | OUTDATED | 0 | OUTDATED | 5, 6, 12, 16, 31 | OUTDATED | 0 | OUTDATED | 5, 6, 12, 16, 31 | OUTDATED | 0 | OUTDATED |  | OUTDATED |  | OUTDATED |  | REPROVED | 5 | 50.87% | 5, 6, 12, 16, 23, 31, 36 | OUTDATED |  | OUTDATED | 5, 6, 12, 16, 23, 31, 36 | OUTDATED |  | OUTDATED | 5, 6, 12, 16, 23, 31, 36 | NEXT ROUND |  | NEXT ROUND | 5, 6, 12, 16, 23, 31, 36 | REPROVED | 29 | 50.87% | 16, 23, 31, 36, 39, 42 | OUTDATED | 29 | OUTDATED | 16, 23, 31, 36, 39, 42 | OUTDATED | 29 | OUTDATED | 16, 23, 31, 36, 39, 42 | OUTDATED | 29 | OUTDATED | 16, 23, 31, 36, 39, 42 | NEXT ROUND | 29 | NEXT ROUND | 16, 23, 31, 36, 39, 42 | NEXT ROUND | 29 | NEXT ROUND | 16, 23, 31, 36, 39, 42 | REPROVED | 51 | 98% | 16, 23, 31, 36, 39, 42 | IMPROPER | 51 | IMPROPER | 16, 23, 31, 36, 39, 42 | OUTDATED | 51 | OUTDATED | 16, 23, 31, 36, 39, 42 | OUTDATED | 51 | OUTDATED | 16, 23, 31, 36, 39, 42 | OUTDATED | 51 | OUTDATED | 16, 23, 31, 36, 39, 42 | OUTDATED | 51 | OUTDATED | 16, 23, 31, 36, 39, 42 | OUTDATED | 51 | OUTDATED | 16, 23, 31, 36, 39, 42 | OUTDATED | 51 | OUTDATED | 16, 23, 31, 36, 39, 42 | NEXT ROUND | 51 | NEXT ROUND | 16, 23, 31, 36, 39, 42 | ANALYSING | 51 | ANALYSING | 16, 23, 31, 36, 39, 42
38 | CPQ11-ELEC-ELEC-DATA-R24.rvt | CPQ11-ELEC-ELEC-DATA-R22.rvt | DATA | MENDES HOLLER | 1112 | PGMAK | 1129 | V52 | 30/04/2026 | V4 | 06/07/2026 | V4 | 2026-07-06 | R24 | LUIZA | REPROVED | 129 | 1% | NUVENS 15, 16, 22, 23, 25 e 31 | DONE | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | IMPROPER | 0 | IMPROPER |  | NEXT ROUND |  | NEXT ROUND |  | IMPROPER | 0 | IMPROPER |  | NEXT ROUND |  | NEXT ROUND |  | IMPROPER |  | IMPROPER |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | IMPROPER |  | IMPROPER |  | OUTDATED |  | OUTDATED |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | IMPROPER |  | IMPROPER |  | OUTDATED |  | OUTDATED |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | IMPROPER |  | IMPROPER
| CPQ11-FALM-FALM-DATA-R24.rvt | CPQ11-FALM-FALM-DATA-R22.rvt | DATA | MENDES HOLLER | 1112 | MENDES HOLLER | 1112 | V24 | 15/05/2026 | V2 | 06/07/2026 | V2 | 2026-07-06 | R24 | LUIZA | IMPROPER | 238 | IMPROPER |  | DONE | IMPROPER |  | IMPROPER |  | OUTDATED |  | OUTDATED |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | REPROVED |  | 1% | 12, 15, 16, 23, 25, 31, 36, 39 | NEXT ROUND |  | NEXT ROUND | 12, 15, 16, 23, 25, 31, 36, 39 | NEXT ROUND |  | NEXT ROUND | 12, 15, 16, 23, 25, 31, 36, 39 | NEXT ROUND | 0 | NEXT ROUND | 12, 15, 16, 23, 25, 31, 36, 39 | IMPROPER | 0 | IMPROPER | 12, 15, 16, 23, 25, 31, 36, 39 | NEXT ROUND | 0 | NEXT ROUND | 12, 15, 16, 23, 25, 31, 36, 39 | NEXT ROUND | 0 | NEXT ROUND | 12, 15, 16, 23, 25, 31, 36, 39 | IMPROPER | 0 | IMPROPER |  | IMPROPER | 0 | IMPROPER |  | NEXT ROUND | 0 | NEXT ROUND |  | IMPROPER | 0 | IMPROPER |  | NEXT ROUND | 0 | NEXT ROUND |  | NEXT ROUND | 0 | NEXT ROUND |  | IMPROPER | 0 | IMPROPER |  | OUTDATED | 0 | OUTDATED |  | OUTDATED | 0 | OUTDATED |  | OUTDATED | 0 | OUTDATED |  | OUTDATED | 0 | OUTDATED |  | OUTDATED | 0 | OUTDATED |  | NEXT ROUND | 0 | NEXT ROUND |  | IMPROPER | 0 | IMPROPER
11 | CPQ11-ARCH-OHCD-DATA-R24.rvt | CPQ11-ARCH-OHCD-DATA-R22.rvt | DATA | MEGADOORS | 1108 | SPBIM | 1127 | V4 | 10/04/2026 | V2 | 04/06/2026 | N/A | N/A | N/A |  | NOT PUBLISHED |  | NOT PUBLISHED |  | N/A | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A
14 | CPQ11-ARCH-PART-C345-R24.rvt | CPQ11-ARCH-PART-C345-R22.rvt | C345 | IDEIA DRYWALL | 1101 | FCH | 1126 | V14 | 30/01/2026 | V1 | 19/05/2026 | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A
18 | CPQ11-ARCH-SHLV-DATA-R24.rvt | CPQ11-ARCH-SHLV-DATA-R22.rvt | DATA | ALTAMIRA | 0000 | ALTAMIRA | 0000 | V9 | 28/02/2026 | V1 | 20/05/2026 | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A
56 | CPQ11-STRC-STEE-ADMN-2X3.ifc | CPQ11-STRC-STEE-ADMN-2X3.ifc | ADMN | METASA | 1125 | METASA | 1125 | V8 | 07/11/2025 | V1 | 21/05/2026 | N/A | N/A | N/A |  | N/A |  | N/A |  | 2025-12-30 | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A
58 | CPQ11-STRC-STEE-COL2-2X3.ifc | CPQ11-STRC-STEE-COL2-2X3.ifc | COL2 | METASA | 1125 | METASA | 1125 | V6 | 07/11/2025 | V1 | 21/05/2026 | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A
1 | ARCH ¦ ARCHITECTURE
59 | CPQ11-STRC-STEE-COL3-2X3.ifc | CPQ11-STRC-STEE-COL3-2X3.ifc | COL3 | METASA | 1125 | METASA | 1125 | V6 | 07/11/2025 | V1 | 21/05/2026 | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A
60 | CPQ11-STRC-STEE-COL4-2X3.ifc | CPQ11-STRC-STEE-COL4-2X3.ifc | COL4 | METASA | 1125 | METASA | 1125 | V7 | 05/12/2025 | V1 | 21/05/2026 | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A
61 | CPQ11-STRC-STEE-COL5-2X3.ifc | CPQ11-STRC-STEE-COL5-2X3.ifc | COL5 | METASA | 1125 | METASA | 1125 | V6 | 07/11/2025 | V1 | 21/05/2026 | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A
20 | CPQ11-SYST-INFR-DATA-R24.rvt | CPQ11-SYST-INFR-DATA-R22.rvt | DATA | MENDES HOLLER | 1112 | PGMAK | 1129 | V40 | 10/04/2026 | V3 | 13/07/2026 | V2 | 2026-06-03 | R24 | N/A | REPROVED | 188 | 1% | 2, 5, 6, 12, 15, 16, 17, 22, 23, 26, 31, 36 | DONE | IMPROPER | 0 | IMPROPER |  | OUTDATED | 0 | OUTDATED |  | OUTDATED | 0 | OUTDATED |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | REPROVED | 0 | 1% | 16, 23, 24, 31, 36, 39 | NEXT ROUND |  | NEXT ROUND | 16, 23, 24, 31, 36, 39 | NEXT ROUND |  | NEXT ROUND | 16, 23, 24, 31, 36, 39 | NEXT ROUND |  | NEXT ROUND | 16, 23, 24, 31, 36, 39 | NEXT ROUND |  | NEXT ROUND | 16, 23, 24, 31, 36, 39 | NEXT ROUND |  | NEXT ROUND | 16, 23, 24, 31, 36, 39 | REPROVED | 2 | 1% | 16, 23, 24, 31, 36, 39 | OUTDATED | 2 | OUTDATED | 16, 23, 24, 31, 36, 39 | OUTDATED | 2 | OUTDATED | 16, 23, 24, 31, 36, 39 | OUTDATED | 2 | OUTDATED | 16, 23, 24, 31, 36, 39 | OUTDATED | 2 | OUTDATED | 16, 23, 24, 31, 36, 39 | NEXT ROUND | 2 | NEXT ROUND | 16, 23, 24, 31, 36, 39 | REPROVED | 2 | 1% | FEDERADO - COL1 | NEXT ROUND | 2 | NEXT ROUND | FEDERADO - COL1 | IMPROPER | 2 | IMPROPER | FEDERADO - COL1 | OUTDATED | 2 | OUTDATED | FEDERADO - COL1 | OUTDATED | 2 | OUTDATED | FEDERADO - COL1 | OUTDATED | 2 | OUTDATED | FEDERADO - COL1 | OUTDATED | 2 | OUTDATED | FEDERADO - COL1 | NEXT ROUND | 2 | NEXT ROUND | FEDERADO - COL1
30 | CPQ11-BASM-INFR-DATA-R24.rvt | CPQ11-BASM-INFR-DATA-R22.rvt | DATA | MENDES HOLLER | 1112 | PGMAK | 1129 | V33 | 04/03/2026 | V2 | 13/07/2026 | V1 | 19/05/2026 | R24 | FLAVIO | REPROVED | 70 | 1% | 3, 2, 6,12, 16,31 | DONE | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | IMPROPER |  | IMPROPER |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | NEXT ROUND |  | NEXT ROUND |  | REPROVED | 3 | 4% | FEDERADO - COL1 | OUTDATED | 3 | OUTDATED | FEDERADO - COL1 | OUTDATED | 3 | OUTDATED | FEDERADO - COL1 | OUTDATED | 3 | OUTDATED | FEDERADO - COL1 | OUTDATED | 3 | OUTDATED | FEDERADO - COL1 | OUTDATED | 3 | OUTDATED | FEDERADO - COL1 | OUTDATED | 3 | OUTDATED | FEDERADO - COL1 | NEXT ROUND | 3 | NEXT ROUND | FEDERADO - COL1
48 | CPQ11-PLMB-PLMB-DATA-R24.rvt | CPQ11-PLMB-PLMB-DATA-R22.rvt | DATA | MENDES HOLLER | 1112 | PGMAK | 1129 | V30 | 24/03/2026 | V2 | 13/07/2026 | V1 | 2026-05-19 | R24 |  | REPROVED | 18 | 1% | 15, 16, 17, 22, 23, 25 | DONE | REPROVED | 18 | 1% | 15, 16, 17, 22, 23, 25 | REPROVED | 18 | 1% | 15, 16, 17, 22, 23, 25 | OUTDATED | 18 | OUTDATED | 15, 16, 17, 22, 23, 25 | IMPROPER | 0 | IMPROPER |  | OUTDATED | 0 | OUTDATED |  | OUTDATED |  | OUTDATED |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | IMPROPER |  | IMPROPER |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | IMPROPER |  | IMPROPER |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | NEXT ROUND |  | NEXT ROUND
5 | CPQ11-ARCH-WOOD-DATA-R24.rvt | CPQ11-ARCH-WOOD-DATA-R22.rvt | DATA | MADEPISO | 0000 | MADEPISO | 0000 | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | N/A | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED
9 | CPQ11-ARCH-FURN-DATA-R24.rvt | CPQ11-ARCH-FURN-DATA-R22.rvt | DATA | RACIONAL | 1106 | CONTRACTING | 0000 | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | N/A | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED
10 | CPQ11-ARCH-WTRP-DATA-R24.rvt | CPQ11-ARCH-WTRP-DATA-R22.rvt | DATA | ITS | 1107 | RBV | 0000 | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | N/A | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED
16 | CPQ11-ARCH-COMN-DATA-R24.rvt | CPQ11-ARCH-COMN-DATA-R22.rvt | DATA | CONTRACTING | 0000 | CONTRACTING | 0000 | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | N/A | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED
46 | CPQ11-FPRT-FPRT-DATA-R24.rvt | CPQ11-FPRT-FPRT-DATA-R22.rvt | DATA | MENDES HOLLER | 1112 | MENDES HOLLER | 1112 | V17 | 14/05/2026 | V4 | 25/06/2026 | V4 | 2026-06-25 | R24 | FLAVIO | REPROVED | 122 | 1% | 6, 16, 31 | DONE | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | NEXT ROUND |  | NEXT ROUND |  | IMPROPER | 0 | IMPROPER |  | OUTDATED | 0 | OUTDATED |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | IMPROPER |  | IMPROPER |  | OUTDATED |  | OUTDATED |  | NEXT ROUND |  | NEXT ROUND |  | IMPROPER |  | IMPROPER |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | IMPROPER |  | IMPROPER |  | IMPROPER |  | IMPROPER |  | NEXT ROUND |  | NEXT ROUND |  | IMPROPER |  | IMPROPER |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED
19 | SYST-SYSTEMS ¦ INFRASTRUCTURE
2 | CPQ11-ARCH-ARCH-DATA-R24.rvt | CPQ11-ARCH-ARCH-DATA-R22.rvt | DATA | ARE ARQUITETURA | 1130 | ARE ARQUITETURA | 1130 | V29 | 13/04/2026 | V3 | 03/06/2026 | V3 | 2026-06-03 | R24 | LUIZA | REPROVED | 33 | 1% | 2, 3, 5, 6, 12, 15, 16, 17, 22, 23, 24, 25, 26, 31, 36 | DONE | IMPROPER | 0 | IMPROPER |  | OUTDATED | 0 | OUTDATED |  | REPROVED | 13 | 39.39% | 5, 6, 12, 15, 16, 17, 22, 23, 24, 25, 26, 31, 36, 39 | NEXT ROUND |  | NEXT ROUND |  | REPROVED | 1 | 42% | 15, 16, 22, 23, 31, 36, 39 | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | REPROVED | 14 | 42% | 15, 16, 22, 23, 31, 36, 39 | NEXT ROUND | 14 | NEXT ROUND | 15, 16, 22, 23, 31, 36, 39 | REPROVED | 8 | 61% | 16, 25 ,36, 39 | NEXT ROUND | 8 | NEXT ROUND | 16, 25 ,36, 39 | REPROVED | 11 | 85% | 16, 25 ,36, 39, 42 | OUTDATED | 11 | OUTDATED | 16, 25 ,36, 39, 42 | OUTDATED | 11 | OUTDATED | 16, 25 ,36, 39, 42 | OUTDATED | 11 | OUTDATED | 16, 25 ,36, 39, 42 | OUTDATED | 11 | OUTDATED | 16, 25 ,36, 39, 42 | NEXT ROUND | 11 | NEXT ROUND | 16, 25 ,36, 39, 42 | NEXT ROUND | 11 | NEXT ROUND | 16, 25 ,36, 39, 42 | REPROVED | 11 | 85% | FEDERADA - COL1 | IMPROPER | 11 | IMPROPER | FEDERADA - COL1 | OUTDATED | 11 | OUTDATED | FEDERADA - COL1 | OUTDATED | 11 | OUTDATED | FEDERADA - COL1 | OUTDATED | 11 | OUTDATED | FEDERADA - COL1 | OUTDATED | 11 | OUTDATED | FEDERADA - COL1 | OUTDATED | 11 | OUTDATED | FEDERADA - COL1
21 | DAS-DISTRIBUTED ANTENN/A SYSTEM ¦ DEVICES
17 | CPQ11-ARCH-CEIL-DATA-R24.rvt | CPQ11-ARCH-CEIL-DATA-R22.rvt | DATA | IDEIA DRYWALL | 1101 | T2B | 0000 | V4 | 29/04/2026 | V1 | 04/06/2026 | V1 | 04/06/2026 | R24 | CAROL | NEXT ROUND |  | NEXT ROUND | 26 | NÃO FOI POSSÍVEL. HÁ AMBIENTES SEM O FORRO | REPROVED | 20 | 1% | 2, 3, 4, 5, 6, 15, 16, 22, 23, 25, 26, 27, 31, 36 | OUTDATED | 0 | OUTDATED | 2, 3, 4, 5, 6, 15, 16, 22, 23, 25, 26, 27, 31, 36 | OUTDATED | 0 | OUTDATED | 2, 3, 4, 5, 6, 15, 16, 22, 23, 25, 26, 27, 31, 36 | OUTDATED | 0 | OUTDATED |  | OUTDATED |  | OUTDATED |  | IMPROPER | 0 | IMPROPER |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | NEXT ROUND |  | NEXT ROUND |  | IMPROPER | 0 | IMPROPER |  | OUTDATED | 0 | OUTDATED |  | OUTDATED | 0 | OUTDATED |  | OUTDATED | 0 | OUTDATED |  | NEXT ROUND | 0 | NEXT ROUND |  | IMPROPER |  | IMPROPER |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | IMPROPER |  | IMPROPER |  | OUTDATED |  | OUTDATED |  | IMPROPER |  | IMPROPER |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED
23 | EPMS-ELECTRICAL POWER MAN/AGEMENT SYSTEM ¦ DEVICES | [37 empty] | 1%
42 | CPQ11-DALI-DEVS-DATA-R24.rvt | CPQ11-DALI-DEVS-DATA-R22.rvt | DATA | AUTOBRÁS | 1116 | AUTOBRÁS | 1116 | V15 | 15/04/2026 | V2 | 02/06/2026 | V2 | 2026-06-02 | R24 | LUIZA | IMPROPER | 0 | IMPROPER |  | DONE | REPROVED | 17 | 1% |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | NEXT ROUND |  | NEXT ROUND |  | IMPROPER |  | IMPROPER |  | OUTDATED |  | OUTDATED |  | NEXT ROUND |  | NEXT ROUND |  | REPROVED | 0 | 1% | 24, 25, 26, 31, 36, 39, 42, 44 | OUTDATED | 0 | OUTDATED | 24, 25, 26, 31, 36, 39, 42, 44 | OUTDATED | 0 | OUTDATED | 24, 25, 26, 31, 36, 39, 42, 44 | OUTDATED | 0 | OUTDATED | 24, 25, 26, 31, 36, 39, 42, 44 | OUTDATED | 0 | OUTDATED | 24, 25, 26, 31, 36, 39, 42, 44 | OUTDATED | 0 | OUTDATED | 24, 25, 26, 31, 36, 39, 42, 44 | NEXT ROUND | 0 | NEXT ROUND | 24, 25, 26, 31, 36, 39, 42, 44 | IMPROPER | 0 | IMPROPER | 24, 25, 26, 31, 36, 39, 42, 44 | OUTDATED | 0 | OUTDATED | 24, 25, 26, 31, 36, 39, 42, 44 | OUTDATED | 0 | OUTDATED | 24, 25, 26, 31, 36, 39, 42, 44 | OUTDATED | 0 | OUTDATED | 24, 25, 26, 31, 36, 39, 42, 44 | OUTDATED | 0 | OUTDATED | 24, 25, 26, 31, 36, 39, 42, 44 | OUTDATED | 0 | OUTDATED | 24, 25, 26, 31, 36, 39, 42, 44
25 | ROIP-RADIO OVER IP ¦ DEVICES
27 | TELECOM ¦ DEVICES
15 | CPQ11-ARCH-PART-C12A-R24.rvt | CPQ11-ARCH-PART-C12A-R22.rvt | C12A | IDEIA DRYWALL | 1101 | FCH | 1126 | V24 | 07/04/2026 | V2 | 27/05/2026 | V2 | 2026-05-27 | R24 | CAROL | REPROVED | 52 | 1% | 16, 25, 36 | DONE | IMPROPER | 0 | IMPROPER |  | IMPROPER | 0 | IMPROPER |  | IMPROPER | 0 | IMPROPER |  | IMPROPER |  | IMPROPER |  | IMPROPER |  | IMPROPER |  | NEXT ROUND |  | NEXT ROUND |  | REPROVED | 23 | 44.23% | 16, 25, 36 | OUTDATED | 23 | OUTDATED | 16, 25, 36 | OUTDATED | 23 | OUTDATED | 16, 25, 36 | OUTDATED | 23 | OUTDATED | 16, 25, 36 | NEXT ROUND | 23 | NEXT ROUND | 16, 25, 36 | NEXT ROUND | 23 | NEXT ROUND | 16, 25, 36 | NEXT ROUND | 23 | NEXT ROUND | 16, 25, 36 | NEXT ROUND | 23 | NEXT ROUND | 16, 25, 36 | NEXT ROUND | 23 | NEXT ROUND | 16, 25, 36 | NEXT ROUND | 23 | NEXT ROUND | 16, 25, 36 | NEXT ROUND | 23 | NEXT ROUND | 16, 25, 36 | IMPROPER | 23 | IMPROPER | 16, 25, 36 | IMPROPER | 23 | IMPROPER | 16, 25, 36 | IMPROPER | 23 | IMPROPER | 16, 25, 36 | REPROVED | 41 | 78% | 16, 25, 36 | OUTDATED | 41 | OUTDATED | 16, 25, 36 | OUTDATED | 41 | OUTDATED | 16, 25, 36 | OUTDATED | 41 | OUTDATED | 16, 25, 36 | OUTDATED | 41 | OUTDATED | 16, 25, 36
29 | BAS-BUILDING AUTOMATION SYSTEM ¦ INFRASTRUCTURE
| CPQ11-ROIP-DEVS-DATA-R24.rvt | CPQ11-ROIP-DEVS-DATA-R22.rvt | DATA | IB TECH | 1113 | IB TECH | 1113 | V36 | 08/05/2026 | V2 | 03/06/2026 | V2 | 2026-06-03 | R24 | FLAVIO | REPROVED | 6 | 1% | 2, 3, 6, 16, 17, 23 | DONE | IMPROPER | 0 | IMPROPER |  | OUTDATED | 0 | OUTDATED |  | OUTDATED | 0 | OUTDATED |  | NEXT ROUND |  | NEXT ROUND |  | REPROVED | 0 | 1% |  | OUTDATED |  | OUTDATED |  | NEXT ROUND |  | NEXT ROUND |  | REPROVED | 0 | 1% | 2, 3, 6, 16, 17, 23 | NEXT ROUND | 0 | NEXT ROUND | 2, 3, 6, 16, 17, 23 | REPROVED | 1 | 17% | 16, 17, 23, 36, 39 | NEXT ROUND | 1 | NEXT ROUND | 16, 17, 23, 36, 39 | IMPROPER |  | IMPROPER |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | REPROVED | 1 | 16% | FEDERADO - COL1 | OUTDATED | 1 | OUTDATED | FEDERADO - COL1 | NEXT ROUND | 1 | NEXT ROUND | FEDERADO - COL1 | NEXT ROUND | 1 | NEXT ROUND | FEDERADO - COL1 | NEXT ROUND | 1 | NEXT ROUND | FEDERADO - COL1 | NEXT ROUND | 1 | NEXT ROUND | FEDERADO - COL1 | NEXT ROUND | 1 | NEXT ROUND | FEDERADO - COL1 | REPROVED | 4 | 66% | FEDERADO - COL1 | OUTDATED | 4 | OUTDATED | FEDERADO - COL1
31 | BAS ¦ DEVICES
33 | SCTY-SECURITY ¦ INFRASTRUCTURE
35 | SCTY ¦ DEVICES
37 | ELEC-ELETRICAL
39 | SPDA ¦ PROTECTION SYSTEM ATMOSPHERIC DISCHARGE
49 | CPQ11-PLMB-NPWT-DATA-R24.rvt | CPQ11-PLMB-NPWT-DATA-R22.rvt | DATA | STARCENTER | 1118 | STARCENTER | 1118 | V39 | 30/04/2026 | V3 | 01/07/2026 | V3 | 2026-07-01 | R24 | CAROL | REPROVED | 53 | 1% | 16, 25, 26, 31 | DONE | IMPROPER | 0 | IMPROPER |  | IMPROPER | 0 | 1% |  | IMPROPER | 0 | IMPROPER |  | OUTDATED | 0 | OUTDATED |  | OUTDATED | 0 | OUTDATED |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | REPROVED | 25 | 47.17% | 16, 17, 25, 26, 31, 42 | OUTDATED | 25 | OUTDATED | 16, 17, 25, 26, 31, 42 | OUTDATED | 25 | OUTDATED | 16, 17, 25, 26, 31, 42 | NEXT ROUND | 25 | NEXT ROUND | 16, 17, 25, 26, 31, 42 | NEXT ROUND | 25 | NEXT ROUND | 16, 17, 25, 26, 31, 42 | REPROVED | 35 | 66% | 16, 17, 25, 26, 31, 42 | NEXT ROUND | 35 | NEXT ROUND | 16, 17, 25, 26, 31, 42 | NEXT ROUND | 35 | NEXT ROUND | 16, 17, 25, 26, 31, 42 | IMPROPER | 35 | IMPROPER | FEFERADO COL1 | NEXT ROUND | 35 | NEXT ROUND | FEFERADO COL1 | REPROVED | 37 | 69% | FEFERADO COL1 | OUTDATED | 37 | OUTDATED | FEFERADO COL1 | OUTDATED | 37 | OUTDATED | FEFERADO COL1 | OUTDATED | 37 | OUTDATED | FEFERADO COL1 | NEXT ROUND | 37 | NEXT ROUND | FEFERADO COL1 | REPROVED | 47 | 88% | FEFERADO COL1 | OUTDATED | 47 | OUTDATED | FEFERADO COL1
41 | DALI-DIGITAL ADDRESSABLE LIGHTING INTERFACE-DEVICES
55 | CPQ11-STRC-FLOO-DATA-R24.rvt | CPQ11-STRC-FLOO-DATA-R22.rvt | DATA | MODAX | 1121 | MODAX | 1121 | V1 | 05/05/2026 | V3 | 20/06/2026 | V3 | 2026-06-20 | R24 | FLAVIO | NOT PUBLISHED |  | NOT PUBLISHED |  | N/A | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NEXT ROUND |  | 0% |  | NEXT ROUND |  | 0% |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | APPROVED |  | 100% | FEDERADA - COL1, MODELO STRC - DEERNS | PREVIOUSLY APPROVED |  | 100% | FEDERADA - COL1, MODELO STRC - DEERNS | PREVIOUSLY APPROVED |  | 100% | FEDERADA - COL1, MODELO STRC - DEERNS | PREVIOUSLY APPROVED |  | 100% | FEDERADA - COL1, MODELO STRC - DEERNS
43 | FALM-FIRE ALARM
6 | CPQ11-ARCH-HMET-DATA-R24.rvt | CPQ11-ARCH-HMET-DATA-R22.rvt | DATA | S-VALE | 1104 | SPBIM | 1127 | V12 | 08/04/2026 | V1 | 15/05/2026 | V10 | 26/01/2026 | R22 |  | NEXT ROUND |  | NEXT ROUND |  | ON HOLD | APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100%
45 | FPRT-FIRE PROTECTION
47 | PLMB-PLUMBING
7 | CPQ11-ARCH-HM90-DATA-R24.rvt | CPQ11-ARCH-HM90-DATA-R22.rvt | DATA | ZEUS/PORTEX | 1105 | SPBIM | 1127 | V9 | 27/03/2026 | V2 | 26/06/2026 | V7 | 23/01/2026 | R22 |  | NEXT ROUND |  | NEXT ROUND |  | ON HOLD | APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100%
50 | MECH-MECHANICAL
8 | CPQ11-ARCH-WMES-DATA-R24.rvt | CPQ11-ARCH-WMES-DATA-R22.rvt | DATA | S-VALE | 1104 | SPBIM | 1127 | V13 | 02/03/2026 | V3 | 24/06/2026 | V13 | 2026-01-23 | R22 |  | NEXT ROUND |  | NEXT ROUND |  | ON HOLD | APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100%
52 | STRC-STRUCTURE
12 | CPQ11-ARCH-FACD-DATA-R24.rvt | CPQ11-ARCH-FACD-DATA-R22.rvt | DATA | OMNITRADE | 1110 | CADBIM | 1128 | V25 | 06/05/2026 | V3 | 07/07/2026 | V22 | 2026-03-19 | R22 | LUIZA | REPROVED | 3 | 1% | 16, 22 | DONE | IMPROPER | 0 | IMPROPER |  | REPROVED | 1 | 33.3% | 26 & 27 | REPROVED | 0 | 33.3% | 26 & 27 | REPROVED | 1 | 66% | 26 & 27 | OUTDATED |  | OUTDATED | 26 & 27 | REPROVED | 0 | 66% | 26 | NEXT ROUND |  | NEXT ROUND | 26 | REPROVED | 0 | 66% | 26 | APPROVED | 3 | 100% | 26 | PREVIOUSLY APPROVED | 3 | 100% | 26 | PREVIOUSLY APPROVED | 3 | 100% | 26 | PREVIOUSLY APPROVED | 3 | 100% | 26 | PREVIOUSLY APPROVED | 3 | 100% | 26 | PREVIOUSLY APPROVED | 3 | 100% | 26 | PREVIOUSLY APPROVED | 3 | 100% | 26 | PREVIOUSLY APPROVED | 3 | 100% | 26 | PREVIOUSLY APPROVED | 3 | 100% | 26 | PREVIOUSLY APPROVED | 3 | 100% | 26 | PREVIOUSLY APPROVED | 3 | 100% | 26 | PREVIOUSLY APPROVED | 3 | 100% | 26 | PREVIOUSLY APPROVED | 3 | 100% | 26 | PREVIOUSLY APPROVED | 3 | 100% | 26 | PREVIOUSLY APPROVED | 3 | 100% | 26 | PREVIOUSLY APPROVED | 3 | 100% | 26 | PREVIOUSLY APPROVED | 3 | 100% | 26
13 | CPQ11-ARCH-ROOF-DATA-R24.rvt | CPQ11-ARCH-ROOF-DATA-R22.rvt | DATA | OMNITRADE | 1110 | CADBIM | 1128 | V30 | 26/03/2026 | V2 | 20/05/2026 | V26 | 2026-01-24 | R22 | CAROL | REPROVED | 6 | 1% | 2, 3, 6, 15, 16 & 31 | DONE | IMPROPER | 0 | IMPROPER |  | APPROVED | 6 | 100% | 2, 3, 6, 15, 16 & 31. | PREVIOUSLY APPROVED |  | 100% | 2, 3, 6, 15, 16 & 31. | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100%
53 | CPQ11-STRC-CONC-DATA-R24.rvt | CPQ11-STRC-CONC-DATA-R22.rvt | DATA | SERV OBRAS | 1120 | TENAX | 0000 | V10 | 22/04/2026 | V1 | 15/05/2026 | V7 | 10/12/2025 | R22 |  | APPROVED | 0 | 100% |  | DONE | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100%
54 | CPQ11-STRC-DPFN-DATA-R24.rvt | CPQ11-STRC-DPFN-DATA-R22.rvt | DATA | GEOFIX/TECNOGEO | 0000 | TENAX | 0000 | V11 | 28/04/2026 | V1 | 15/05/2026 | V8 | 2026-01-16 | R22 |  | APPROVED | 0 | 100% |  | DONE | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100%
57 | CPQ11-STRC-STEE-COL1-2X3.ifc | CPQ11-STRC-STEE-COL1-2X3.ifc | COL1 | METASA | 1125 | METASA | 1125 | V7 | 07/11/2025 | V1 | 21/05/2026 | V7 | 07/11/2025 | R22 |  | APPROVED | 0 | 100% | nuvens 2, 3, 5, 15, 16, 17 | DONE | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100%
Note on AV4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Foram adicionadas mais 10 lâmpadas apontando clashes com ELEC-ELEC-DATA
Note on AD8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Modelo IMPROPER devido a problemas com elementos em worksets errados
Note on B38: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Modelo tem que ser analisado com o Workset1 ligado
Note on Z38: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: A issue de lod500 não foi atualizada para "pendente". O modelo foi atualizado somente para atender aos requisitos do 4D.

## LOD 500 - COLO2
LOD 500 ¦ COLO2
| FILE NAME (R24) | FILE NAME (R22) | AREA | TRADE COMPANY | CODE | BIM COMPANY | CODE | ACC VERSION (R22) | ACC FILE DATE (R22 | ACC VERSION (R24) | ACC FILE DATE (R24) | VERSION | FILE DATE | RVT TYPE APROVAL (COLO2/SITE) | RESPONSAVEL | R0 - AUDIT STATUS | R0- LAMPS QTDE | R0 - APPROVAL (%) | R0 - NUVEM UTILIZADA | R1 - AUDIT STATUS | R1 LAMPS QTDE RESOLVIDAS | R1 - APPROVAL (%) | R1 - NUVEM UTILIZADA | R2 - AUDIT STATUS | R2 LAMPS QTDE RESOLVIDAS | R2 - APPROVAL (%) | R2 - NUVEM UTILIZADA | R3 - AUDIT STATUS | R3 LAMPS QTDE RESOLVIDAS | R3 - APPROVAL (%) | R3 - NUVEM UTILIZADA | R4 - AUDIT STATUS | R4 LAMPS QTDE RESOLVIDAS | R4 - APPROVAL (%) | R4 - NUVEM UTILIZADA | R5 - AUDIT STATUS | R5 LAMPS QTDE RESOLVIDAS | R5 - APPROVAL (%) | R5 - NUVEM UTILIZADA | R6 - AUDIT STATUS | R6 LAMPS QTDE RESOLVIDAS | R6 - APPROVAL (%) | R6 - NUVEM UTILIZADA | R7 - AUDIT STATUS | R7 LAMPS QTDE RESOLVIDAS | R7 - APPROVAL (%) | R7 - NUVEM UTILIZADA | R8 - AUDIT STATUS | R8 LAMPS QTDE RESOLVIDAS | R8 - APPROVAL (%) | R8 - NUVEM UTILIZADA | R9 - AUDIT STATUS | R9 LAMPS QTDE RESOLVIDAS | R9 - APPROVAL (%) | R9 - NUVEM UTILIZADA | R10 - AUDIT STATUS | R10 LAMPS QTDE RESOLVIDAS | R10 - APPROVAL (%) | R10 - NUVEM UTILIZADA | R11 - AUDIT STATUS | R11 LAMPS QTDE RESOLVIDAS | R11 - APPROVAL (%) | R11 - NUVEM UTILIZADA | R12 - AUDIT STATUS | R12 LAMPS QTDE RESOLVIDAS | R12 - APPROVAL (%) | R12 - NUVEM UTILIZADA | R13 - AUDIT STATUS | R13 LAMPS QTDE RESOLVIDAS | R13 - APPROVAL (%) | R13- NUVEM UTILIZADA | R14 - AUDIT STATUS | R14 LAMPS QTDE RESOLVIDAS | R14 - APPROVAL (%) | R14- NUVEM UTILIZADA | R15 - AUDIT STATUS | R15 LAMPS QTDE RESOLVIDAS | R15 - APPROVAL (%) | R15- NUVEM UTILIZADA | R16 - AUDIT STATUS | R16 LAMPS QTDE RESOLVIDAS | R16 - APPROVAL (%) | R16 - NUVEM UTILIZADA | R17 - AUDIT STATUS | R17 LAMPS QTDE RESOLVIDAS | R17 - APPROVAL (%) | R17 - NUVEM UTILIZADA | R18 - AUDIT STATUS | R18 LAMPS QTDE RESOLVIDAS | R18 - APPROVAL (%) | R18 - NUVEM UTILIZADA | R19 - AUDIT STATUS | R19 LAMPS QTDE RESOLVIDAS | R19 - APPROVAL (%) | R19 - NUVEM UTILIZADA | R20 - AUDIT STATUS | R20 LAMPS QTDE RESOLVIDAS | R20 - APPROVAL (%) | R20 - NUVEM UTILIZADA | R21 - AUDIT STATUS | R21 LAMPS QTDE RESOLVIDAS | R21 - APPROVAL (%) | R21 - NUVEM UTILIZADA
51 | CPQ11-MECH-MECH-DATA-R24.rvt | CPQ11-MECH-MECH-DATA-R22.rvt | DATA | STARCENTER | 1118 | STARCENTER | 1118 | V59 | 17/04/2026 | V5 | 06/07/2026 | V4 | 2026-07-02 | R24 | LUIZA | NEXT ROUND | 24 | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND | 33, 41 | REPROVED |  | 1% | 33, 41 | IMPROPER | 0 | IMPROPER | 33, 41 | NEXT ROUND | 0 | NEXT ROUND | 33, 41 | IMPROPER |  | IMPROPER | 33, 41 | NEXT ROUND |  | NEXT ROUND | 33, 41 | NEXT ROUND |  | NEXT ROUND | 33, 41 | IMPROPER |  | IMPROPER |  | OUTDATED |  | OUTDATED |  | IMPROPER |  | IMPROPER |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | IMPROPER |  | IMPROPER |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | NEXT ROUND |  | NEXT ROUND |  | IMPROPER |  | IMPROPER |  | ANALYSING |  | ANALYSING
22 | CPQ11-DASM-DEVS-DATA-R24.rvt | CPQ11-DASM-DEVS-DATA-R22.rvt | DATA | IB TECH | 1113 | IB TECH | 1113 | V28 | 16/04/2026 | V4 | 26/06/2026 | V2 | 22/05/2026 | R24 | CAROL | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | REPROVED | 29 | 1% | 41, 43 | NEXT ROUND | 29 | NEXT ROUND | 41, 43 | REPROVED | 22 | 76% | 41, 43 | NEXT ROUND | 22 | NEXT ROUND | 41, 43 | NEXT ROUND | 22 | NEXT ROUND | 41, 43 | NEXT ROUND | 22 | NEXT ROUND | 41, 43 | NEXT ROUND | 22 | NEXT ROUND | 41, 43 | NEXT ROUND | 22 | NEXT ROUND | 41, 43 | NEXT ROUND | 22 | NEXT ROUND | 41, 43 | IMPROPER | 22 | IMPROPER | 41, 43 | OUTDATED | 22 | OUTDATED | 41, 43 | OUTDATED | 22 | OUTDATED | 41, 43 | OUTDATED | 22 | OUTDATED | 41, 43 | NEXT ROUND | 22 | NEXT ROUND | 41, 43 | NEXT ROUND | 22 | NEXT ROUND | 41, 43 | NEXT ROUND | 22 | NEXT ROUND | 41, 43 | ANALYSING | 22 | ANALYSING | 41, 43
24 | CPQ11-EPMS-DEVS-DATA-R24.rvt | CPQ11-EPMS-DEVS-DATA-R22.rvt | DATA | BLACKBOX | 1114 | BLACKBOX | 1114 | V15 | 27/04/2026 | V3 | 12/07/2026 | V1 | 15/05/2026 | R24 | CAROL | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | REPROVED | 4 | 1% | 37, 41 | NEXT ROUND | 4 | NEXT ROUND | 37, 41 | NEXT ROUND | 4 | NEXT ROUND | 37, 41 | NEXT ROUND | 4 | NEXT ROUND | 37, 41 | NEXT ROUND | 4 | NEXT ROUND | 37, 41 | NEXT ROUND | 4 | NEXT ROUND | 37, 41 | NEXT ROUND | 4 | NEXT ROUND | 37, 41 | NEXT ROUND | 4 | NEXT ROUND | 37, 41 | NEXT ROUND | 4 | NEXT ROUND | 37, 41 | NEXT ROUND | 4 | NEXT ROUND | 37, 41 | IMPROPER | 4 | IMPROPER | 37, 41 | OUTDATED | 4 | OUTDATED | 37, 41 | OUTDATED | 4 | OUTDATED | 37, 41 | OUTDATED | 4 | OUTDATED | 37, 41 | REPROVED | 0 | 1% | FEDERADA | NEXT ROUND | 0 | NEXT ROUND | FEDERADA | NEXT ROUND | 0 | NEXT ROUND | FEDERADA | ANALYSING | 0 | ANALYSING | FEDERADA
36 | CPQ11-SCTY-DEVS-DATA-R24.rvt | CPQ11-SCTY-DEVS-DATA-R22.rvt | DATA | SEGURPRO | 1115 | SEGURPRO | 1115 | V40 | 06/05/2026 | V3 | 13/07/2026 | V1 | 2026-05-20 | R24 | LUIZA | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | REPROVED | 148 | 1% | 26, 27, 28, 37 | NEXT ROUND |  | NEXT ROUND | 26, 27, 28, 37 | REPROVED | 3 | 2% | 26, 27, 28, 37 | NEXT ROUND | 3 | NEXT ROUND | 26, 27, 28, 37 | IMPROPER | 3 | IMPROPER | 26, 27, 28, 37 | OUTDATED | 3 | OUTDATED | 26, 27, 28, 37 | OUTDATED | 3 | OUTDATED | 26, 27, 28, 37 | NEXT ROUND | 3 | NEXT ROUND | 26, 27, 28, 37 | NEXT ROUND | 3 | NEXT ROUND | 26, 27, 28, 37 | NEXT ROUND | 3 | NEXT ROUND | 26, 27, 28, 37 | NEXT ROUND | 3 | NEXT ROUND | 26, 27, 28, 37 | NEXT ROUND | 3 | NEXT ROUND | 26, 27, 28, 37 | IMPROPER | 3 | IMPROPER | 26, 27, 28, 37 | OUTDATED | 3 | OUTDATED | 26, 27, 28, 37 | OUTDATED | 3 | OUTDATED | 26, 27, 28, 37 | OUTDATED | 3 | OUTDATED | 26, 27, 28, 37 | NEXT ROUND | 3 | NEXT ROUND | 26, 27, 28, 37 | ANALYSING | 3 | ANALYSING | 26, 27, 28, 37
34 | CPQ11-SCTY-INFR-DATA-R24.rvt | CPQ11-SCTY-INFR-DATA-R22.rvt | DATA | MENDES HOLLER | 1112 | PGMAK | 1129 | V39 | 19/03/2026 | V5 | 10/07/2026 | V4 | 2026-06-26 | R24 | CAROL | NEXT ROUND | 163 | NEXT ROUND | 9, 21, 22, 23, 33, 37 | NEXT ROUND |  | NEXT ROUND | 9, 21, 22, 23, 33, 37 | NEXT ROUND |  | NEXT ROUND | 9, 21, 22, 23, 33, 37 | NEXT ROUND |  | NEXT ROUND | 9, 21, 22, 23, 33, 37 | NEXT ROUND |  | NEXT ROUND | 9, 21, 22, 23, 33, 37 | NEXT ROUND |  | 0% | 9, 21, 22, 23, 33, 37 | NEXT ROUND |  | NEXT ROUND | 9, 21, 22, 23, 33, 37 | NEXT ROUND |  | NEXT ROUND | 9, 21, 22, 23, 33, 37 | REPROVED | 180 | 1% | 37, 41, 43 | OUTDATED | 180 | OUTDATED | 37, 41, 43 | OUTDATED | 180 | OUTDATED | 37, 41, 43 | OUTDATED | 180 | OUTDATED | 37, 41, 43 | OUTDATED | 180 | OUTDATED | 37, 41, 43 | NEXT ROUND | 180 | NEXT ROUND | 37, 41, 43 | NEXT ROUND | 180 | NEXT ROUND | 37, 41, 43 | IMPROPER | 180 | IMPROPER | 37, 41, 43 | NEXT ROUND | 180 | NEXT ROUND | 37, 41, 43 | IMPROPER | 180 | IMPROPER | 37, 41, 43 | IMPROPER | 180 | IMPROPER | 37, 41, 43 | IMPROPER | 180 | IMPROPER | 37, 41, 43 | NEXT ROUND | 180 | NEXT ROUND | 37, 41, 43 | ANALYSING | 180 | ANALYSING | 37, 41, 43
32 | CPQ11-BASM-DEVS-DATA-R24.rvt | CPQ11-BASM-DEVS-DATA-R22.rvt | DATA | BLACKBOX | 1114 | BLACKBOX | 1114 | V20 | 05/05/2026 | V2 | 12/07/2026 | V1 | 2026-05-15 | R24 | LUIZA | NEXT ROUND | 90 | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | REPROVED |  | 1% | 33, 41 | OUTDATED |  | OUTDATED | 33, 41 | IMPROPER | 0 | IMPROPER | 33, 41 | IMPROPER | 0 | IMPROPER | 33, 41 | OUTDATED | 0 | OUTDATED | 33, 41 | OUTDATED | 0 | OUTDATED | 33, 41 | OUTDATED | 0 | OUTDATED | 33, 41 | NEXT ROUND | 0 | NEXT ROUND | 33, 41 | NEXT ROUND | 0 | NEXT ROUND | 33, 41 | NEXT ROUND | 0 | NEXT ROUND | 33, 41 | NEXT ROUND | 0 | NEXT ROUND | 33, 41 | NEXT ROUND | 0 | NEXT ROUND | 33, 41 | NEXT ROUND | 0 | NEXT ROUND | 33, 41 | REPROVED | 12 | 13% | FEDERADA - COL2 | OUTDATED | 12 | OUTDATED | FEDERADA - COL2 | OUTDATED | 12 | OUTDATED | FEDERADA - COL2 | OUTDATED | 12 | OUTDATED | FEDERADA - COL2 | NEXT ROUND | 12 | NEXT ROUND | FEDERADA - COL2 | ANALYSING | 12 | ANALYSING | FEDERADA - COL2
40 | CPQ11-ELEC-SPDA-DATA-R24.rvt | CPQ11-ELEC-SPDA-DATA-R22.rvt | DATA | MENDES HOLLER | 1112 | MENDES HOLLER | 1112 | V13 | 12/05/2026 | V5 | 13/07/2026 | V3 | 2026-06-25 | R24 | FLAVIO | NEXT ROUND | 48 | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | 0% |  | NEXT ROUND |  | NEXT ROUND |  | REPROVED |  | 1% | 33, 37, 41, 43 | NEXT ROUND |  | NEXT ROUND | 33, 37, 41, 43 | IMPROPER |  | IMPROPER |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | IMPROPER |  | IMPROPER |  | NEXT ROUND |  | NEXT ROUND |  | IMPROPER |  | IMPROPER |  | OUTDATED |  | OUTDATED |  | IMPROPER |  | IMPROPER |  | NEXT ROUND |  | NEXT ROUND |  | IMPROPER |  | IMPROPER
38 | CPQ11-ELEC-ELEC-DATA-R24.rvt | CPQ11-ELEC-ELEC-DATA-R22.rvt | DATA | MENDES HOLLER | 1112 | PGMAK | 1129 | V52 | 30/04/2026 | V4 | 06/07/2026 | V4 | 2026-07-06 | R24 | CAROL | NEXT ROUND | ~650 | NEXT ROUND | 9, 22, 23 | NEXT ROUND |  | NEXT ROUND | 9, 22, 23 | NEXT ROUND |  | NEXT ROUND | 9, 22, 23 | NEXT ROUND |  | NEXT ROUND | 9, 22, 23 | NEXT ROUND |  | NEXT ROUND | 9, 22, 23 | NEXT ROUND |  | 0% | 9, 22, 23 | NEXT ROUND |  | NEXT ROUND | 9, 22, 23 | NEXT ROUND |  | NEXT ROUND | 9, 22, 23 | REPROVED | 734 | 1% | 41, 43 | OUTDATED | 734 | OUTDATED | 41, 43 | NEXT ROUND | 734 | NEXT ROUND | 41, 43 | NEXT ROUND | 734 | NEXT ROUND | 41, 43 | NEXT ROUND | 734 | NEXT ROUND | 41, 43 | NEXT ROUND | 734 | NEXT ROUND | 41, 43 | NEXT ROUND | 734 | NEXT ROUND | 41, 43 | NEXT ROUND | 734 | NEXT ROUND | 41, 43 | NEXT ROUND | 734 | NEXT ROUND | 41, 43 | IMPROPER | 734 | IMPROPER | 41, 43 | OUTDATED | 734 | OUTDATED | 41, 43 | NEXT ROUND | 734 | NEXT ROUND | 41, 43 | NEXT ROUND | 734 | NEXT ROUND | 41, 43 | IMPROPER | 734 | IMPROPER | 41, 43
44 | CPQ11-FALM-FALM-DATA-R24.rvt | CPQ11-FALM-FALM-DATA-R22.rvt | DATA | MENDES HOLLER | 1112 | MENDES HOLLER | 1112 | V24 | 15/05/2026 | V2 | 06/07/2026 | V2 | 2026-07-06 | R24 | CAROL | NEXT ROUND | 142 | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | REPROVED |  | 1% | 33, 41 | NEXT ROUND |  | NEXT ROUND | 33, 41 | NEXT ROUND |  | NEXT ROUND | 33, 41 | NEXT ROUND |  | NEXT ROUND | 33, 41 | NEXT ROUND |  | NEXT ROUND | 33, 41 | NEXT ROUND |  | NEXT ROUND | 33, 41 | NEXT ROUND |  | NEXT ROUND | 33, 41 | NEXT ROUND |  | NEXT ROUND | 33, 41 | IMPROPER |  | IMPROPER | 33, 41 | NEXT ROUND |  | NEXT ROUND | 33, 41 | NEXT ROUND |  | NEXT ROUND | 33, 41 | IMPROPER |  | IMPROPER | 33, 41 | OUTDATED |  | OUTDATED | 33, 41 | OUTDATED |  | OUTDATED | 33, 41 | OUTDATED |  | OUTDATED | 33, 41 | OUTDATED |  | OUTDATED | 33, 41 | OUTDATED |  | OUTDATED | 33, 41 | NEXT ROUND |  | NEXT ROUND | 33, 41 | IMPROPER |  | IMPROPER | 33, 41
11 | CPQ11-ARCH-OHCD-DATA-R24.rvt | CPQ11-ARCH-OHCD-DATA-R22.rvt | DATA | MEGADOORS | 1108 | SPBIM | 1127 | V4 | 10/04/2026 | V2 | 04/06/2026 | N/A | N/A | N/A |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A
14 | CPQ11-ARCH-PART-C345-R24.rvt | CPQ11-ARCH-PART-C345-R22.rvt | C345 | IDEIA DRYWALL | 1101 | FCH | 1126 | V14 | 30/01/2026 | V1 | 19/05/2026 | N/A | N/A | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A
18 | CPQ11-ARCH-SHLV-DATA-R24.rvt | CPQ11-ARCH-SHLV-DATA-R22.rvt | DATA | ALTAMIRA | 0000 | ALTAMIRA | 0000 | V9 | 28/02/2026 | V1 | 20/05/2026 | N/A | N/A | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A
56 | CPQ11-STRC-STEE-ADMN-2X3.ifc | CPQ11-STRC-STEE-ADMN-2X3.ifc | ADMN | METASA | 1125 | METASA | 1125 | V8 | 07/11/2025 | V1 | 21/05/2026 | N/A | N/A | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A
57 | CPQ11-STRC-STEE-COL1-2X3.ifc | CPQ11-STRC-STEE-COL1-2X3.ifc | COL1 | METASA | 1125 | METASA | 1125 | V7 | 07/11/2025 | V1 | 21/05/2026 | N/A | N/A | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A
59 | CPQ11-STRC-STEE-COL3-2X3.ifc | CPQ11-STRC-STEE-COL3-2X3.ifc | COL3 | METASA | 1125 | METASA | 1125 | V6 | 07/11/2025 | V1 | 21/05/2026 | N/A | N/A | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A
60 | CPQ11-STRC-STEE-COL4-2X3.ifc | CPQ11-STRC-STEE-COL4-2X3.ifc | COL4 | METASA | 1125 | METASA | 1125 | V7 | 05/12/2025 | V1 | 21/05/2026 | N/A | N/A | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A
61 | CPQ11-STRC-STEE-COL5-2X3.ifc | CPQ11-STRC-STEE-COL5-2X3.ifc | COL5 | METASA | 1125 | METASA | 1125 | V6 | 07/11/2025 | V1 | 21/05/2026 | N/A | N/A | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A
20 | CPQ11-SYST-INFR-DATA-R24.rvt | CPQ11-SYST-INFR-DATA-R22.rvt | DATA | MENDES HOLLER | 1112 | PGMAK | 1129 | V40 | 10/04/2026 | V3 | 13/07/2026 | V2 | 2026-06-03 | R24 | LUIZA | REPROVED | 149 | 1% | 5, 6, 9, 17, 21, 22, 23, 33, 37 | NEXT ROUND |  | NEXT ROUND | 5, 6, 9, 17, 21, 22, 23, 33, 37 | NEXT ROUND |  | NEXT ROUND | 5, 6, 9, 17, 21, 22, 23, 33, 37 | NEXT ROUND |  | NEXT ROUND | 5, 6, 9, 17, 21, 22, 23, 33, 37 | REPROVED | 0 | 1% | 5, 6, 9, 17, 21, 22, 23, 33, 37 | OUTDATED | 0 | OUTDATED | 5, 6, 9, 17, 21, 22, 23, 33, 37 | NEXT ROUND | 0 | NEXT ROUND | 5, 6, 9, 17, 21, 22, 23, 33, 37 | NEXT ROUND | 0 | NEXT ROUND | 5, 6, 9, 17, 21, 22, 23, 33, 37 | IMPROPER |  | IMPROPER | 5, 6, 9, 17, 21, 22, 23, 33, 37 | OUTDATED |  | OUTDATED | 5, 6, 9, 17, 21, 22, 23, 33, 37 | OUTDATED |  | OUTDATED | 5, 6, 9, 17, 21, 22, 23, 33, 37 | OUTDATED |  | OUTDATED | 5, 6, 9, 17, 21, 22, 23, 33, 37 | OUTDATED |  | OUTDATED | 5, 6, 9, 17, 21, 22, 23, 33, 37 | NEXT ROUND |  | NEXT ROUND | 5, 6, 9, 17, 21, 22, 23, 33, 37 | IMPROPER |  | IMPROPER | 5, 6, 9, 17, 21, 22, 23, 33, 37 | NEXT ROUND |  | NEXT ROUND | 5, 6, 9, 17, 21, 22, 23, 33, 37 | IMPROPER |  | IMPROPER | 5, 6, 9, 17, 21, 22, 23, 33, 37 | OUTDATED |  | OUTDATED | 5, 6, 9, 17, 21, 22, 23, 33, 37 | OUTDATED |  | OUTDATED | 5, 6, 9, 17, 21, 22, 23, 33, 37 | OUTDATED |  | OUTDATED | 5, 6, 9, 17, 21, 22, 23, 33, 37 | OUTDATED |  | OUTDATED | 5, 6, 9, 17, 21, 22, 23, 33, 37 | NEXT ROUND |  | NEXT ROUND | 5, 6, 9, 17, 21, 22, 23, 33, 37
30 | CPQ11-BASM-INFR-DATA-R24.rvt | CPQ11-BASM-INFR-DATA-R22.rvt | DATA | MENDES HOLLER | 1112 | PGMAK | 1129 | V33 | 04/03/2026 | V2 | 13/07/2026 | V1 | 2026-05-19 | R24 | LUIZA | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | 0% |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | REPROVED | 571 | 1% | 9, 10, 11, 33, 41, 43 | OUTDATED | 571 | OUTDATED | 9, 10, 11, 33, 41, 43 | OUTDATED | 571 | OUTDATED | 9, 10, 11, 33, 41, 43 | NEXT ROUND | 571 | NEXT ROUND | 9, 10, 11, 33, 41, 43 | NEXT ROUND | 571 | NEXT ROUND | 9, 10, 11, 33, 41, 43 | IMPROPER | 571 | IMPROPER | 9, 10, 11, 33, 41, 43 | OUTDATED | 571 | OUTDATED | 9, 10, 11, 33, 41, 43 | OUTDATED | 571 | OUTDATED | 9, 10, 11, 33, 41, 43 | OUTDATED | 571 | OUTDATED | 9, 10, 11, 33, 41, 43 | OUTDATED | 571 | OUTDATED | 9, 10, 11, 33, 41, 43 | OUTDATED | 571 | OUTDATED | 9, 10, 11, 33, 41, 43 | NEXT ROUND | 571 | NEXT ROUND | 9, 10, 11, 33, 41, 43
48 | CPQ11-PLMB-PLMB-DATA-R24.rvt | CPQ11-PLMB-PLMB-DATA-R22.rvt | DATA | MENDES HOLLER | 1112 | PGMAK | 1129 | V30 | 24/03/2026 | V2 | 13/07/2026 | V1 | 2026-05-19 | R24 | LUIZA | NEXT ROUND | 8 | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | REPROVED |  | 1% | 21, 33, 37 | NEXT ROUND |  | NEXT ROUND | 21, 33, 37 | NEXT ROUND |  | NEXT ROUND |  | IMPROPER |  | IMPROPER |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | IMPROPER |  | IMPROPER |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | NEXT ROUND |  | NEXT ROUND
5 | CPQ11-ARCH-WOOD-DATA-R24.rvt | CPQ11-ARCH-WOOD-DATA-R22.rvt | DATA | MADEPISO | 0000 | MADEPISO | 0000 | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED
9 | CPQ11-ARCH-FURN-DATA-R24.rvt | CPQ11-ARCH-FURN-DATA-R22.rvt | DATA | RACIONAL | 1106 | CONTRACTING | 0000 | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED
10 | CPQ11-ARCH-WTRP-DATA-R24.rvt | CPQ11-ARCH-WTRP-DATA-R22.rvt | DATA | ITS | 1107 | RBV | 0000 | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED
16 | CPQ11-ARCH-COMN-DATA-R24.rvt | CPQ11-ARCH-COMN-DATA-R22.rvt | DATA | CONTRACTING | 0000 | CONTRACTING | 0000 | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED
28 | CPQ11-TCOM-DEVS-DATA-R24.rvt | CPQ11-TCOM-DEVS-DATA-R22.rvt | DATA | BLACKBOX | 1114 | BLACKBOX | 1114 | V18 | 30/04/2026 | V3 | 29/06/2026 | V3 | 2026-06-29 | R24 | CAROL | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | REPROVED | 89 | 1% | 26, 28, 33, 37, 41 | OUTDATED | 89 | OUTDATED | 26, 28, 33, 37, 41 | OUTDATED | 89 | OUTDATED | 26, 28, 33, 37, 41 | NEXT ROUND | 89 | NEXT ROUND | 26, 28, 33, 37, 41 | NEXT ROUND | 89 | NEXT ROUND | 26, 28, 33, 37, 41 | NEXT ROUND | 89 | NEXT ROUND | 26, 28, 33, 37, 41 | NEXT ROUND | 89 | NEXT ROUND | 26, 28, 33, 37, 41 | IMPROPER |  | IMPROPER |  | OUTDATED |  | OUTDATED |  | IMPROPER |  | IMPROPER |  | OUTDATED |  | OUTDATED |  | IMPROPER |  | IMPROPER |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | NEXT ROUND |  | NEXT ROUND |  | IMPROPER |  | IMPROPER |  | OUTDATED |  | OUTDATED
49 | CPQ11-PLMB-NPWT-DATA-R24.rvt | CPQ11-PLMB-NPWT-DATA-R22.rvt | DATA | STARCENTER | 1118 | STARCENTER | 1118 | V39 | 30/04/2026 | V3 | 01/07/2026 | V3 | 2026-07-01 | R24 | FLAVIO | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | REPROVED | 0 | 1% | 26, 28, 33, 37, 41 | OUTDATED | 0 | OUTDATED | 26, 28, 33, 37, 41 | OUTDATED | 0 | OUTDATED | 26, 28, 33, 37, 41 | NEXT ROUND | 0 | NEXT ROUND | 26, 28, 33, 37, 41 | IMPROPER |  | IMPROPER |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | IMPROPER |  | IMPROPER |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | NEXT ROUND |  | NEXT ROUND |  | IMPROPER |  | IMPROPER |  | OUTDATED |  | OUTDATED
46 | CPQ11-FPRT-FPRT-DATA-R24.rvt | CPQ11-FPRT-FPRT-DATA-R22.rvt | DATA | MENDES HOLLER | 1112 | MENDES HOLLER | 1112 | V17 | 14/05/2026 | V4 | 25/06/2026 | V4 | 2026-06-25 | R24 | FLAVIO | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND | VISITA 5,6,9,10, 11,18, 19 | REPROVED | 50 LAMPADAS INICIAIS | 1% | VISITA 5,6,9,10, 11,18, 19 | NEXT ROUND |  | NEXT ROUND | VISITA 5,6,9,10, 11,18, 19 | NEXT ROUND |  | NEXT ROUND | VISITA 5,6,9,10, 11,18, 19 | IMPROPER |  | IMPROPER |  | OUTDATED |  | OUTDATED |  | NEXT ROUND |  | NEXT ROUND |  | IMPROPER |  | IMPROPER |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | IMPROPER |  | IMPROPER |  | IMPROPER |  | IMPROPER |  | NEXT ROUND |  | NEXT ROUND |  | IMPROPER |  | IMPROPER |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED
2 | CPQ11-ARCH-ARCH-DATA-R24.rvt | CPQ11-ARCH-ARCH-DATA-R22.rvt | DATA | ARE ARQUITETURA | 1130 | ARE ARQUITETURA | 1130 | V29 | 13/04/2026 | V3 | 03/06/2026 | V3 | 2026-06-03 | R24 | LUIZA | REPROVED | 43 | 1% | 5, 6, 9, 17, 21, 22, 23, 33, 37 | NEXT ROUND |  | NEXT ROUND | 5, 6, 9, 17, 21, 22, 23, 33, 37 | NEXT ROUND |  | NEXT ROUND | 5, 6, 9, 17, 21, 22, 23, 33, 37 | NEXT ROUND |  | NEXT ROUND | 5, 6, 9, 17, 21, 22, 23, 33, 37 | NEXT ROUND |  | NEXT ROUND | 5, 6, 9, 17, 21, 22, 23, 33, 37 | REPROVED | 33 | 77% | 22, 33, 37, 43 | OUTDATED | 33 | OUTDATED | 22, 33, 37, 43 | NEXT ROUND | 33 | NEXT ROUND | 22, 33, 37, 43 | NEXT ROUND | 33 | NEXT ROUND | 22, 33, 37, 43 | NEXT ROUND | 33 | NEXT ROUND | 22, 33, 37, 43 | REPROVED | 34 | 79% | 22, 33, 37, 41, 43 | OUTDATED | 34 | OUTDATED | 22, 33, 37, 41, 43 | OUTDATED | 34 | OUTDATED | 22, 33, 37, 41, 43 | NEXT ROUND | 34 | NEXT ROUND | 22, 33, 37, 41, 43 | NEXT ROUND | 34 | NEXT ROUND | 22, 33, 37, 41, 43 | IMPROPER | 34 | IMPROPER | 22, 33, 37, 41, 43 | IMPROPER | 34 | IMPROPER | 22, 33, 37, 41, 43 | OUTDATED | 34 | OUTDATED | 22, 33, 37, 41, 43 | OUTDATED | 34 | OUTDATED | 22, 33, 37, 41, 43 | OUTDATED | 34 | OUTDATED | 22, 33, 37, 41, 43 | OUTDATED | 34 | OUTDATED | 22, 33, 37, 41, 43 | OUTDATED | 34 | OUTDATED | 22, 33, 37, 41, 43
15 | CPQ11-ARCH-PART-C12A-R24.rvt | CPQ11-ARCH-PART-C12A-R22.rvt | C12A | IDEIA DRYWALL | 1101 | FCH | 1126 | V24 | 07/04/2026 | V2 | 27/05/2026 | V2 | 2026-05-27 | R24 | LUIZA | REPROVED | 57 | 1% | 18, 19, 23, 33 | NEXT ROUND |  | NEXT ROUND | 18, 19, 23, 33 | NEXT ROUND |  | NEXT ROUND | 18, 19, 23, 33 | NEXT ROUND |  | NEXT ROUND | 18, 19, 23, 33 | NEXT ROUND |  | NEXT ROUND | 18, 19, 23, 33 | REPROVED | 0 | 1% | 18, 19, 23, 33 | OUTDATED | 0 | OUTDATED | 18, 19, 23, 33 | NEXT ROUND | 0 | NEXT ROUND | 18, 19, 23, 33 | NEXT ROUND | 0 | NEXT ROUND | 18, 19, 23, 33 | NEXT ROUND | 0 | NEXT ROUND | 18, 19, 23, 33 | NEXT ROUND | 0 | NEXT ROUND | 18, 19, 23, 33 | NEXT ROUND | 0 | NEXT ROUND | 18, 19, 23, 33 | NEXT ROUND | 0 | NEXT ROUND | 18, 19, 23, 33 | NEXT ROUND | 0 | NEXT ROUND | 18, 19, 23, 33 | IMPROPER | 0 | IMPROPER | 18, 19, 23, 33 | IMPROPER | 0 | IMPROPER | 18, 19, 23, 33 | IMPROPER | 0 | IMPROPER | 18, 19, 23, 33 | OUTDATED | 0 | OUTDATED | 18, 19, 23, 33 | OUTDATED | 0 | OUTDATED | 18, 19, 23, 33 | OUTDATED | 0 | OUTDATED | 18, 19, 23, 33 | OUTDATED | 0 | OUTDATED | 18, 19, 23, 33 | OUTDATED | 0 | OUTDATED | 18, 19, 23, 33
17 | CPQ11-ARCH-CEIL-DATA-R24.rvt | CPQ11-ARCH-CEIL-DATA-R22.rvt | DATA | IDEIA DRYWALL | 1101 | T2B | 0000 | V4 | 29/04/2026 | V1 | 04/06/2026 | V1 | 04/06/2026 | R24 | LUIZA | REPROVED | 13 | 1% | 5, 6, 9, 17, 21, 22, 23, 33, 37 | OUTDATED |  | OUTDATED | 5, 6, 9, 17, 21, 22, 23, 33, 37 | NEXT ROUND |  | NEXT ROUND | 5, 6, 9, 17, 21, 22, 23, 33, 37 | NEXT ROUND |  | NEXT ROUND | 5, 6, 9, 17, 21, 22, 23, 33, 37 | IMPROPER |  | IMPROPER | 5, 6, 9, 17, 21, 22, 23, 33, 37 | NEXT ROUND |  | NEXT ROUND | 5, 6, 9, 17, 21, 22, 23, 33, 37 | IMPROPER |  | IMPROPER | 21, 22, 23, 33, 37 | OUTDATED |  | OUTDATED | 21, 22, 23, 33, 37 | OUTDATED |  | OUTDATED | 21, 22, 23, 33, 37 | OUTDATED |  | OUTDATED | 21, 22, 23, 33, 37 | NEXT ROUND |  | NEXT ROUND | 21, 22, 23, 33, 37 | IMPROPER |  | IMPROPER |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | IMPROPER |  | IMPROPER |  | OUTDATED |  | OUTDATED |  | IMPROPER |  | IMPROPER |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED
42 | CPQ11-DALI-DEVS-DATA-R24.rvt | CPQ11-DALI-DEVS-DATA-R22.rvt | DATA | AUTOBRÁS | 1116 | AUTOBRÁS | 1116 | V15 | 15/04/2026 | V2 | 02/06/2026 | V2 | 2026-06-02 | R24 | LUIZA | NEXT ROUND | 108 | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | REPROVED |  | 1% | 33, 41 | NEXT ROUND |  | NEXT ROUND | 33, 41 | IMPROPER |  | IMPROPER | 33, 41 | OUTDATED |  | OUTDATED | 33, 41 | NEXT ROUND |  | NEXT ROUND | 33, 41 | REPROVED | 0 | 1% | 33, 41 | OUTDATED | 0 | OUTDATED | 33, 41 | OUTDATED | 0 | OUTDATED | 33, 41 | OUTDATED | 0 | OUTDATED | 33, 41 | OUTDATED | 0 | OUTDATED | 33, 41 | OUTDATED | 0 | OUTDATED | 33, 41 | NEXT ROUND | 0 | NEXT ROUND | 33, 41 | IMPROPER | 0 | IMPROPER | 33, 41 | OUTDATED | 0 | OUTDATED | 33, 41 | OUTDATED | 0 | OUTDATED | 33, 41 | OUTDATED | 0 | OUTDATED | 33, 41 | OUTDATED | 0 | OUTDATED | 33, 41 | OUTDATED | 0 | OUTDATED | 33, 41
| CPQ11-ROIP-DEVS-DATA-R24.rvt | CPQ11-ROIP-DEVS-DATA-R22.rvt | DATA | IB TECH | 1113 | IB TECH | 1113 | V36 | 08/05/2026 | V2 | 03/06/2026 | V2 | 2026-06-03 | R24 | CAROL | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | REPROVED | 3 | 1% | 26, 28, 33, 37, 41 | REPROVED | 0 | 1% | 41, 43 | NEXT ROUND | 0 | NEXT ROUND | 41, 43 | NEXT ROUND | 0 | NEXT ROUND | 41, 43 | IMPROPER | 0 | IMPROPER | 41, 43 | IMPROPER | 0 | IMPROPER | 41, 43 | NEXT ROUND | 0 | NEXT ROUND | 41, 43 | NEXT ROUND | 0 | NEXT ROUND | 41, 43 | NEXT ROUND | 0 | NEXT ROUND | 41, 43 | IMPROPER | 0 | IMPROPER | 41, 43 | NEXT ROUND | 0 | NEXT ROUND | 41, 43 | IMPROPER | 0 | IMPROPER | 41, 43 | OUTDATED | 0 | OUTDATED | 41, 43 | OUTDATED | 0 | OUTDATED | 41, 43 | OUTDATED | 0 | OUTDATED | 41, 43 | OUTDATED | 0 | OUTDATED | 41, 43 | OUTDATED | 0 | OUTDATED | 41, 43
55 | CPQ11-STRC-FLOO-DATA-R24.rvt | CPQ11-STRC-FLOO-DATA-R22.rvt | DATA | MODAX | 1121 | MODAX | 1121 | V1 | 05/05/2026 | V3 | 20/06/2026 | V3 | 2026-06-20 | R24 | FLAVIO | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NEXT ROUND |  | 0% |  | NEXT ROUND |  | 0% |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | APPROVED |  | 100% | NUVEM FEDERADA, MODELOS DE STEEL E ARCH | PREVIOUSLY APPROVED |  | 100% | NUVEM FEDERADA, MODELOS DE STEEL E ARCH | PREVIOUSLY APPROVED |  | 100% | NUVEM FEDERADA, MODELOS DE STEEL E ARCH
6 | CPQ11-ARCH-HMET-DATA-R24.rvt | CPQ11-ARCH-HMET-DATA-R22.rvt | DATA | S-VALE | 1104 | SPBIM | 1127 | V12 | 08/04/2026 | V1 | 15/05/2026 | V11 | 2026-04-01 | R22 | ALINNE | NEXT ROUND |  | 0% | 18, 21, 23 37 | NEXT ROUND |  | NEXT ROUND | 18, 21, 23 37 | NEXT ROUND |  | NEXT ROUND | 18, 21, 23 37 | NEXT ROUND |  | NEXT ROUND | 18, 21, 23 37 | NEXT ROUND |  | NEXT ROUND | 18, 21, 23 37 | NEXT ROUND |  | NEXT ROUND | 18, 21, 23 37 | APPROVED | 15 | 100% | 18, 21, 23 37 | PREVIOUSLY APPROVED | 15 | 100% | 18, 21, 23 37 | PREVIOUSLY APPROVED | 15 | 100% | 18, 21, 23 37 | PREVIOUSLY APPROVED | 15 | 100% | 18, 21, 23 37 | PREVIOUSLY APPROVED | 15 | 100% | 18, 21, 23 37 | PREVIOUSLY APPROVED | 15 | 100% | 18, 21, 23 37 | PREVIOUSLY APPROVED | 15 | 100% | 18, 21, 23 37 | PREVIOUSLY APPROVED | 15 | 100% | 18, 21, 23 37 | PREVIOUSLY APPROVED | 15 | 100% | 18, 21, 23 37 | PREVIOUSLY APPROVED | 15 | 100% | 18, 21, 23 37 | PREVIOUSLY APPROVED | 15 | 100% | 18, 21, 23 37 | PREVIOUSLY APPROVED | 15 | 100% | 18, 21, 23 37 | PREVIOUSLY APPROVED | 15 | 100% | 18, 21, 23 37 | PREVIOUSLY APPROVED | 15 | 100% | 18, 21, 23 37 | PREVIOUSLY APPROVED | 15 | 100% | 18, 21, 23 37 | PREVIOUSLY APPROVED | 15 | 100% | 18, 21, 23 37
7 | CPQ11-ARCH-HM90-DATA-R24.rvt | CPQ11-ARCH-HM90-DATA-R22.rvt | DATA | ZEUS/PORTEX | 1105 | SPBIM | 1127 | V9 | 27/03/2026 | V2 | 26/06/2026 | V8 | 18/02/2026 | R22 | ALINNE | APPROVED |  | 100% | 9, 11, 19, 22, 33 | PREVIOUSLY APPROVED |  | 100% | 9, 11, 19, 22, 33 | PREVIOUSLY APPROVED |  | 100% | 9, 11, 19, 22, 33 | PREVIOUSLY APPROVED |  | 100% | 9, 11, 19, 22, 33 | PREVIOUSLY APPROVED |  | 100% | 9, 11, 19, 22, 33 | PREVIOUSLY APPROVED |  | 100% | 9, 11, 19, 22, 33 | PREVIOUSLY APPROVED |  | 100% | 9, 11, 19, 22, 33 | PREVIOUSLY APPROVED |  | 100% | 9, 11, 19, 22, 33 | PREVIOUSLY APPROVED |  | 100% | 9, 11, 19, 22, 33 | PREVIOUSLY APPROVED |  | 100% | 9, 11, 19, 22, 33 | PREVIOUSLY APPROVED |  | 100% | 9, 11, 19, 22, 33 | PREVIOUSLY APPROVED |  | 100% | 9, 11, 19, 22, 33 | PREVIOUSLY APPROVED |  | 100% | 9, 11, 19, 22, 33 | PREVIOUSLY APPROVED |  | 100% | 9, 11, 19, 22, 33 | PREVIOUSLY APPROVED |  | 100% | 9, 11, 19, 22, 33 | PREVIOUSLY APPROVED |  | 100% | 9, 11, 19, 22, 33 | PREVIOUSLY APPROVED |  | 100% | 9, 11, 19, 22, 33 | PREVIOUSLY APPROVED |  | 100% | 9, 11, 19, 22, 33 | PREVIOUSLY APPROVED |  | 100% | 9, 11, 19, 22, 33 | PREVIOUSLY APPROVED |  | 100% | 9, 11, 19, 22, 33 | PREVIOUSLY APPROVED |  | 100% | 9, 11, 19, 22, 33 | PREVIOUSLY APPROVED |  | 100% | 9, 11, 19, 22, 33
8 | CPQ11-ARCH-WMES-DATA-R24.rvt | CPQ11-ARCH-WMES-DATA-R22.rvt | DATA | S-VALE | 1104 | SPBIM | 1127 | V13 | 02/03/2026 | V3 | 24/06/2026 | V13 | 2026-01-23 | R22 | ALINNE | APPROVED |  | 100% | 23, 19 | PREVIOUSLY APPROVED |  | 100% | 23, 19 | PREVIOUSLY APPROVED |  | 100% | 23, 19 | PREVIOUSLY APPROVED |  | 100% | 23, 19 | PREVIOUSLY APPROVED |  | 100% | 23, 19 | PREVIOUSLY APPROVED |  | 100% | 23, 19 | PREVIOUSLY APPROVED |  | 100% | 23, 19 | PREVIOUSLY APPROVED |  | 100% | 23, 19 | PREVIOUSLY APPROVED |  | 100% | 23, 19 | PREVIOUSLY APPROVED |  | 100% | 23, 19 | PREVIOUSLY APPROVED |  | 100% | 23, 19 | PREVIOUSLY APPROVED |  | 100% | 23, 19 | PREVIOUSLY APPROVED |  | 100% | 23, 19 | PREVIOUSLY APPROVED |  | 100% | 23, 19 | PREVIOUSLY APPROVED |  | 100% | 23, 19 | PREVIOUSLY APPROVED |  | 100% | 23, 19 | PREVIOUSLY APPROVED |  | 100% | 23, 19 | PREVIOUSLY APPROVED |  | 100% | 23, 19 | PREVIOUSLY APPROVED |  | 100% | 23, 19 | PREVIOUSLY APPROVED |  | 100% | 23, 19 | PREVIOUSLY APPROVED |  | 100% | 23, 19 | PREVIOUSLY APPROVED |  | 100% | 23, 19
12 | CPQ11-ARCH-FACD-DATA-R24.rvt | CPQ11-ARCH-FACD-DATA-R22.rvt | DATA | OMNITRADE | 1110 | CADBIM | 1128 | V25 | 06/05/2026 | V3 | 07/07/2026 | V23 | 2026-03-27 | R22 | LUIZA | REPROVED | 15 | 1% | 18, 19, 23, 33 | OUTDATED |  | OUTDATED | 18, 19, 23, 33 | NEXT ROUND |  | NEXT ROUND | 18, 19, 23, 33 | IMPROPER |  | IMPROPER | 18, 19, 23, 33 | NEXT ROUND |  | NEXT ROUND | 18, 19, 23, 33 | REPROVED | 6 | 40% | 18, 19, 23, 33 | APPROVED | 15 | 100% | 18, 19, 23, 33 | PREVIOUSLY APPROVED | 15 | 100% | 18, 19, 23, 33 | PREVIOUSLY APPROVED | 15 | 100% | 18, 19, 23, 33 | PREVIOUSLY APPROVED | 15 | 100% | 18, 19, 23, 33 | PREVIOUSLY APPROVED | 15 | 100% | 18, 19, 23, 33 | PREVIOUSLY APPROVED | 15 | 100% | 18, 19, 23, 33 | PREVIOUSLY APPROVED | 15 | 100% | 18, 19, 23, 33 | PREVIOUSLY APPROVED | 15 | 100% | 18, 19, 23, 33 | PREVIOUSLY APPROVED | 15 | 100% | 18, 19, 23, 33 | PREVIOUSLY APPROVED | 15 | 100% | 18, 19, 23, 33 | PREVIOUSLY APPROVED | 15 | 100% | 18, 19, 23, 33 | PREVIOUSLY APPROVED | 15 | 100% | 18, 19, 23, 33 | PREVIOUSLY APPROVED | 15 | 100% | 18, 19, 23, 33 | PREVIOUSLY APPROVED | 15 | 100% | 18, 19, 23, 33 | PREVIOUSLY APPROVED | 15 | 100% | 18, 19, 23, 33 | PREVIOUSLY APPROVED | 15 | 100% | 18, 19, 23, 33
13 | CPQ11-ARCH-ROOF-DATA-R24.rvt | CPQ11-ARCH-ROOF-DATA-R22.rvt | DATA | OMNITRADE | 1110 | CADBIM | 1128 | V30 | 26/03/2026 | V2 | 20/05/2026 | V27 | 2026-02-02 | R22 | LUIZA | NEXT ROUND |  | NEXT ROUND |  | APPROVED |  | 100% | DRONE 30/01/2026 | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100%
53 | CPQ11-STRC-CONC-DATA-R24.rvt | CPQ11-STRC-CONC-DATA-R22.rvt | DATA | SERV OBRAS | 1120 | TENAX | 0000 | V10 | 22/04/2026 | V1 | 15/05/2026 | V9 | 13/03/2026 | R22 | YASMIN | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | APPROVED | 0 | 100% |  | PREVIOUSLY APPROVED | 0 | 100% |  | PREVIOUSLY APPROVED | 0 | 100% |  | PREVIOUSLY APPROVED | 0 | 100% |  | PREVIOUSLY APPROVED | 0 | 100% |  | PREVIOUSLY APPROVED | 0 | 100% |  | PREVIOUSLY APPROVED | 0 | 100% |  | PREVIOUSLY APPROVED | 0 | 100% |  | PREVIOUSLY APPROVED | 0 | 100% |  | PREVIOUSLY APPROVED | 0 | 100% |  | PREVIOUSLY APPROVED | 0 | 100% |  | PREVIOUSLY APPROVED | 0 | 100% |  | PREVIOUSLY APPROVED | 0 | 100% |  | PREVIOUSLY APPROVED | 0 | 100% |  | PREVIOUSLY APPROVED | 0 | 100% |  | PREVIOUSLY APPROVED | 0 | 100% |  | PREVIOUSLY APPROVED | 0 | 100%
54 | CPQ11-STRC-DPFN-DATA-R24.rvt | CPQ11-STRC-DPFN-DATA-R22.rvt | DATA | GEOFIX/TECNOGEO | 0000 | TENAX | 0000 | V11 | 28/04/2026 | V1 | 15/05/2026 | V10 | 13/03/2026 | R22 | YASMIN | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100%
58 | CPQ11-STRC-STEE-COL2-2X3.ifc | CPQ11-STRC-STEE-COL2-2X3.ifc | COL2 | METASA | 1125 | METASA | 1125 | V6 | 07/11/2025 | V6 | 21/05/2026 | V6 | 07/11/2025 | R22 | SOPHIA | NEXT ROUND |  | NEXT ROUND | AGUARDANDO VERIFICAÇÃO DA NUVEM | NEXT ROUND |  | NEXT ROUND | AGUARDANDO VERIFICAÇÃO DA NUVEM | NEXT ROUND |  | NEXT ROUND | AGUARDANDO VERIFICAÇÃO DA NUVEM | APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100%
1 | ARCH ¦ ARCHITECTURE
19 | SYST-SYSTEMS ¦ INFRASTRUCTURE
21 | DAS-DISTRIBUTED ANTENN/A SYSTEM ¦ DEVICES
23 | EPMS-ELECTRICAL POWER MAN/AGEMENT SYSTEM ¦ DEVICES
25 | ROIP-RADIO OVER IP ¦ DEVICES
27 | TELECOM ¦ DEVICES
29 | BAS-BUILDING AUTOMATION SYSTEM ¦ INFRASTRUCTURE
31 | BAS ¦ DEVICES
33 | SCTY-SECURITY ¦ INFRASTRUCTURE
35 | SCTY ¦ DEVICES
37 | ELEC-ELETRICAL
39 | SPDA ¦ PROTECTION SYSTEM ATMOSPHERIC DISCHARGE
41 | DALI-DIGITAL ADDRESSABLE LIGHTING INTERFACE-DEVICES
43 | FALM-FIRE ALARM
45 | FPRT-FIRE PROTECTION
47 | PLMB-PLUMBING
50 | MECH-MECHANICAL
52 | STRC-STRUCTURE
Note on AL4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Quantidade de lâmpadas inseridas
Note on AX10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Lâmpadas adicionadas Round equivalente ao 0

## LOD 500 - COLO3
LOD 500 ¦ COLO3
| FILE NAME (R24) | FILE NAME (R22) | AREA | TRADE COMPANY | CODE | BIM COMPANY | CODE | ACC VERSION (R22) | ACC FILE DATE (R22) | ACC VERSION (R24) | ACC FILE DATE (R24) | VERSION | FILE DATE | RVT TYPE APROVAL (COLO3) | RESPONSAVEL | R0 - AUDIT STATUS | R0- LAMPS QTDE | R0 - APPROVAL (%) | R0 - NUVEM UTILIZADA | R1 - AUDIT STATUS | R1- LAMPS QTDE | R1 - APPROVAL (%) | R1 - NUVEM UTILIZADA | R2 - AUDIT STATUS | R2- LAMPS QTDE | R2 - APPROVAL (%) | R2 - NUVEM UTILIZADA | R3 - AUDIT STATUS | R3- LAMPS QTDE | R3 - APPROVAL (%) | R3 - NUVEM UTILIZADA | R4 - AUDIT STATUS | R4- LAMPS QTDE | R4 - APPROVAL (%) | R4 - NUVEM UTILIZADA | R5 - AUDIT STATUS | R5- LAMPS QTDE | R5 - APPROVAL (%) | R5 - NUVEM UTILIZADA | R6 - AUDIT STATUS | R6- LAMPS QTDE | R6 - APPROVAL (%) | R6 - NUVEM UTILIZADA | R7 - AUDIT STATUS | R7- LAMPS QTDE | R7 - APPROVAL (%) | R7 - NUVEM UTILIZADA | R8 - AUDIT STATUS | R8- LAMPS QTDE | R8 - APPROVAL (%) | R8 - NUVEM UTILIZADA | R9 - AUDIT STATUS | R9- LAMPS QTDE | R9 - APPROVAL (%) | R9 - NUVEM UTILIZADA | R10 - AUDIT STATUS | R10- LAMPS QTDE | R10 - APPROVAL (%) | R10 - NUVEM UTILIZADA | R11 - AUDIT STATUS | R11- LAMPS QTDE | R11 - APPROVAL (%) | R11 - NUVEM UTILIZADA | R12 - AUDIT STATUS | R12- LAMPS QTDE | R12 - APPROVAL (%) | R12 - NUVEM UTILIZADA | R13 - AUDIT STATUS | R13- LAMPS QTDE | R13 - APPROVAL (%) | R13 - NUVEM UTILIZADA | R14 - AUDIT STATUS | R14- LAMPS QTDE | R14 - APPROVAL (%) | R14 - NUVEM UTILIZADA | R15 - AUDIT STATUS | R15- LAMPS QTDE | R15 - APPROVAL (%) | R15 - NUVEM UTILIZADA
1 | ARCH ¦ ARCHITECTURE
20 | CPQ11-SYST-INFR-DATA-R24.rvt | CPQ11-SYST-INFR-DATA-R22.rvt | DATA | MENDES HOLLER | 1112 | PGMAK | 1129 | V40 | 10/04/2026 | V3 | 13/07/2026 | V39 | 2026-03-31 | R24 |  | NEXT ROUND |  | 0% |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | ANALYSING |  | ANALYSING
38 | CPQ11-ELEC-ELEC-DATA-R24.rvt | CPQ11-ELEC-ELEC-DATA-R22.rvt | DATA | MENDES HOLLER | 1112 | PGMAK | 1129 | V52 | 30/04/2026 | V4 | 06/07/2026 | N/A | N/A | R24 |  | NEXT ROUND |  | 0% |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | ANALYSING |  | ANALYSING
44 | CPQ11-FALM-FALM-DATA-R24.rvt | CPQ11-FALM-FALM-DATA-R22.rvt | DATA | MENDES HOLLER | 1112 | MENDES HOLLER | 1112 | V24 | 15/05/2026 | V2 | 06/07/2026 | N/A | N/A | R24 |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | NEXT ROUND |  | 0% |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | ANALYSING |  | ANALYSING
46 | CPQ11-FPRT-FPRT-DATA-R24.rvt | CPQ11-FPRT-FPRT-DATA-R22.rvt | DATA | MENDES HOLLER | 1112 | MENDES HOLLER | 1112 | V17 | 14/05/2026 | V4 | 25/06/2026 | N/A | N/A | R24 |  | NEXT ROUND |  | 0% |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | ANALYSING |  | ANALYSING
48 | CPQ11-PLMB-PLMB-DATA-R24.rvt | CPQ11-PLMB-PLMB-DATA-R22.rvt | DATA | MENDES HOLLER | 1112 | PGMAK | 1129 | V30 | 24/03/2026 | V2 | 13/07/2026 | N/A | N/A | R24 |  | NEXT ROUND |  | 0% |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | ANALYSING |  | ANALYSING
| CPQ11-ROIP-DEVS-DATA-R24.rvt | CPQ11-ROIP-DEVS-DATA-R22.rvt | DATA | IB TECH | 1113 | IB TECH | 1113 | V36 | 08/05/2026 | V2 | 03/06/2026 | V3 | 2026-06-03 | R24 |  | NEXT ROUND |  | 0% |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND | VISITA 30 | NEXT ROUND |  | NEXT ROUND | VISITA 30 | NEXT ROUND |  | NEXT ROUND | VISITA 30 | NEXT ROUND |  | NEXT ROUND | VISITA 30 | NEXT ROUND |  | NEXT ROUND | VISITA 30 | NEXT ROUND |  | NEXT ROUND | VISITA 30 | NEXT ROUND |  | NEXT ROUND | VISITA 30 | NEXT ROUND |  | NEXT ROUND | VISITA 30 | NEXT ROUND |  | NEXT ROUND | VISITA 30 | NEXT ROUND |  | NEXT ROUND | VISITA 30 | NEXT ROUND |  | NEXT ROUND | VISITA 30 | NEXT ROUND |  | NEXT ROUND | VISITA 30 | REPROVED | 17 | 1% | FEDERADO - COL3
22 | CPQ11-DASM-DEVS-DATA-R24.rvt | CPQ11-DASM-DEVS-DATA-R22.rvt | DATA | IB TECH | 1113 | IB TECH | 1113 | V28 | 16/04/2026 | V4 | 26/06/2026 | V3 | 2026-06-23 | R24 |  | NEXT ROUND |  | 0% |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | REPROVED |  | 1% |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | ANALYSING |  | ANALYSING
51 | CPQ11-MECH-MECH-DATA-R24.rvt | CPQ11-MECH-MECH-DATA-R22.rvt | DATA | STARCENTER | 1118 | STARCENTER | 1118 | V59 | 17/04/2026 | V5 | 06/07/2026 | V5 | 2026-07-06 | R24 |  | NEXT ROUND |  | 0% |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | REPROVED | 50 (INICIAL) | 1% |  | NEXT ROUND | 50 (INICIAL) | NEXT ROUND |  | IMPROPER | 50 (INICIAL) | IMPROPER
32 | CPQ11-BASM-DEVS-DATA-R24.rvt | CPQ11-BASM-DEVS-DATA-R22.rvt | DATA | BLACKBOX | 1114 | BLACKBOX | 1114 | V20 | 05/05/2026 | V2 | 12/07/2026 | V1 | 2026-05-15 | R24 | CAROL | NEXT ROUND |  | 0% |  | REPROVED | 106 | 1% | 30, 34, 35 | OUTDATED | 106 | OUTDATED | 30, 34, 35 | OUTDATED | 106 | OUTDATED | 30, 34, 35 | NEXT ROUND | 106 | NEXT ROUND | 30, 34, 35 | IMPROPER |  | IMPROPER |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | IMPROPER |  | IMPROPER |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | NEXT ROUND |  | NEXT ROUND |  | ANALYSING |  | ANALYSING
40 | CPQ11-ELEC-SPDA-DATA-R24.rvt | CPQ11-ELEC-SPDA-DATA-R22.rvt | DATA | MENDES HOLLER | 1112 | MENDES HOLLER | 1112 | V13 | 12/05/2026 | V5 | 13/07/2026 | V4 | 2026-07-03 | R24 | CAROL | NEXT ROUND |  | 0% |  | NEXT ROUND |  | NEXT ROUND |  | REPROVED | 44 | 1% | 29, 30, 34, 44 | IMPROPER | 0 | IMPROPER |  | NEXT ROUND | 0 | NEXT ROUND |  | NEXT ROUND | 0 | NEXT ROUND |  | NEXT ROUND | 0 | NEXT ROUND |  | NEXT ROUND | 0 | NEXT ROUND |  | NEXT ROUND | 0 | NEXT ROUND |  | IMPROPER |  | IMPROPER |  | NEXT ROUND |  | NEXT ROUND |  | IMPROPER |  | IMPROPER |  | OUTDATED |  | OUTDATED |  | IMPROPER |  | IMPROPER |  | NEXT ROUND |  | NEXT ROUND |  | IMPROPER |  | IMPROPER
36 | CPQ11-SCTY-DEVS-DATA-R24.rvt | CPQ11-SCTY-DEVS-DATA-R22.rvt | DATA | SEGURPRO | 1115 | SEGURPRO | 1115 | V40 | 06/05/2026 | V3 | 13/07/2026 | V2 | 2026-07-06 | R24 |  | NEXT ROUND |  | 0% |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | REPROVED | 141 | 1% | FEDERADO - COL3 | NEXT ROUND | 141 | NEXT ROUND | FEDERADO - COL3 | IMPROPER | 141 | IMPROPER | FEDERADO - COL3
11 | CPQ11-ARCH-OHCD-DATA-R24.rvt | CPQ11-ARCH-OHCD-DATA-R22.rvt | DATA | MEGADOORS | 1108 | SPBIM | 1127 | V4 | 10/04/2026 | V2 | 04/06/2026 | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A
15 | CPQ11-ARCH-PART-C12A-R24.rvt | CPQ11-ARCH-PART-C12A-R22.rvt | C12A | IDEIA DRYWALL | 1101 | FCH | 1126 | V24 | 07/04/2026 | V2 | 27/05/2026 | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A
18 | CPQ11-ARCH-SHLV-DATA-R24.rvt | CPQ11-ARCH-SHLV-DATA-R22.rvt | DATA | ALTAMIRA | 0000 | ALTAMIRA | 0000 | V9 | 28/02/2026 | V1 | 20/05/2026 | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A
56 | CPQ11-STRC-STEE-ADMN-2X3.ifc | CPQ11-STRC-STEE-ADMN-2X3.ifc | ADMN | METASA | 1125 | METASA | 1125 | V8 | 07/11/2025 | V1 | 21/05/2026 | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A
19 | SYST-SYSTEMS ¦ INFRASTRUCTURE
57 | CPQ11-STRC-STEE-COL1-2X3.ifc | CPQ11-STRC-STEE-COL1-2X3.ifc | COL1 | METASA | 1125 | METASA | 1125 | V7 | 07/11/2025 | V1 | 21/05/2026 | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A
21 | DAS-DISTRIBUTED ANTENN/A SYSTEM ¦ DEVICES
58 | CPQ11-STRC-STEE-COL2-2X3.ifc | CPQ11-STRC-STEE-COL2-2X3.ifc | COL2 | METASA | 1125 | METASA | 1125 | V6 | 07/11/2025 | V6 | 21/05/2026 | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A
23 | EPMS-ELECTRICAL POWER MAN/AGEMENT SYSTEM ¦ DEVICES
60 | CPQ11-STRC-STEE-COL4-2X3.ifc | CPQ11-STRC-STEE-COL4-2X3.ifc | COL4 | METASA | 1125 | METASA | 1125 | V7 | 05/12/2025 | V1 | 21/05/2026 | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A
25 | ROIP-RADIO OVER IP ¦ DEVICES
27 | TELECOM ¦ DEVICES
61 | CPQ11-STRC-STEE-COL5-2X3.ifc | CPQ11-STRC-STEE-COL5-2X3.ifc | COL5 | METASA | 1125 | METASA | 1125 | V6 | 07/11/2025 | V1 | 21/05/2026 | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A
29 | BAS-BUILDING AUTOMATION SYSTEM ¦ INFRASTRUCTURE
5 | CPQ11-ARCH-WOOD-DATA-R24.rvt | CPQ11-ARCH-WOOD-DATA-R22.rvt | DATA | MADEPISO | 0000 | MADEPISO | 0000 | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED
31 | BAS ¦ DEVICES
9 | CPQ11-ARCH-FURN-DATA-R24.rvt | CPQ11-ARCH-FURN-DATA-R22.rvt | DATA | RACIONAL | 1106 | CONTRACTING | 0000 | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED
33 | SCTY-SECURITY ¦ INFRASTRUCTURE
10 | CPQ11-ARCH-WTRP-DATA-R24.rvt | CPQ11-ARCH-WTRP-DATA-R22.rvt | DATA | ITS | 1107 | RBV | 0000 | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED
35 | SCTY ¦ DEVICES
16 | CPQ11-ARCH-COMN-DATA-R24.rvt | CPQ11-ARCH-COMN-DATA-R22.rvt | DATA | CONTRACTING | 0000 | CONTRACTING | 0000 | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED
37 | ELEC-ELETRICAL
49 | CPQ11-PLMB-NPWT-DATA-R24.rvt | CPQ11-PLMB-NPWT-DATA-R22.rvt | DATA | STARCENTER | 1118 | STARCENTER | 1118 | V39 | 30/04/2026 | V3 | 01/07/2026 | V3 | 2026-07-01 | R24 | LUIZA | NEXT ROUND |  | 0% |  | REPROVED | 74 | 1% | 30, 31, 32, 34, 35 | NEXT ROUND | 74 | NEXT ROUND | 30, 31, 32, 34, 35 | NEXT ROUND | 74 | NEXT ROUND | 30, 31, 32, 34, 35 | NEXT ROUND | 74 | NEXT ROUND | 30, 31, 32, 34, 35 | IMPROPER |  | IMPROPER |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | IMPROPER |  | IMPROPER |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | NEXT ROUND |  | NEXT ROUND |  | IMPROPER |  | IMPROPER |  | OUTDATED |  | OUTDATED
39 | SPDA ¦ PROTECTION SYSTEM ATMOSPHERIC DISCHARGE
28 | CPQ11-TCOM-DEVS-DATA-R24.rvt | CPQ11-TCOM-DEVS-DATA-R22.rvt | DATA | BLACKBOX | 1114 | BLACKBOX | 1114 | V18 | 30/04/2026 | V3 | 29/06/2026 | V3 | 2026-06-29 | R24 | FLAVIO | NEXT ROUND |  | 0% |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | REPROVED | 80 | 1% | FEDERADA COLO 3 | OUTDATED | 80 | OUTDATED | FEDERADA COLO 3 | NEXT ROUND | 80 | NEXT ROUND | FEDERADA COLO 3 | IMPROPER | 80 | IMPROPER | FEDERADA COLO 3 | OUTDATED | 80 | OUTDATED | FEDERADA COLO 3
41 | DALI-DIGITAL ADDRESSABLE LIGHTING INTERFACE-DEVICES
17 | CPQ11-ARCH-CEIL-DATA-R24.rvt | CPQ11-ARCH-CEIL-DATA-R22.rvt | DATA | IDEIA DRYWALL | 1101 | T2B | 0000 | V4 | 29/04/2026 | V1 | 04/06/2026 | V1 | 04/06/2026 | R24 | FLAVIO | NEXT ROUND |  | 0% |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | IMPROPER |  | IMPROPER |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED
43 | FALM-FIRE ALARM
2 | CPQ11-ARCH-ARCH-DATA-R24.rvt | CPQ11-ARCH-ARCH-DATA-R22.rvt | DATA | ARE ARQUITETURA | 1130 | ARE ARQUITETURA | 1130 | V29 | 13/04/2026 | V3 | 03/06/2026 | V3 | 2026-06-03 | R24 | LUIZA | NEXT ROUND |  | 0% |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | REPROVED | 101 | 1% | 31, 34, 35 | OUTDATED | 101 | OUTDATED | 31, 34, 35 | OUTDATED | 101 | OUTDATED | 31, 34, 35 | OUTDATED | 101 | OUTDATED | 31, 34, 35 | NEXT ROUND | 101 | NEXT ROUND | 31, 34, 35 | NEXT ROUND | 101 | NEXT ROUND | 31, 34, 35 | IMPROPER | 101 | IMPROPER | 31, 34, 35 | IMPROPER | 101 | IMPROPER | 31, 34, 35 | OUTDATED | 101 | OUTDATED | 31, 34, 35 | OUTDATED | 101 | OUTDATED | 31, 34, 35 | OUTDATED | 101 | OUTDATED | 31, 34, 35 | OUTDATED | 101 | OUTDATED | 31, 34, 35 | OUTDATED | 101 | OUTDATED | 31, 34, 35
45 | FPRT-FIRE PROTECTION
14 | CPQ11-ARCH-PART-C345-R24.rvt | CPQ11-ARCH-PART-C345-R22.rvt | C345 | IDEIA DRYWALL | 1101 | FCH | 1126 | V14 | 30/01/2026 | V1 | 19/05/2026 | V1 | 19/05/2026 | R24 | LUIZA | NEXT ROUND |  | 0% |  | REPROVED | 88 | 1% | 30, 31, 34, 35 | OUTDATED | 88 | OUTDATED | 30, 31, 34, 35 | OUTDATED | 88 | OUTDATED | 30, 31, 34, 35 | OUTDATED | 88 | OUTDATED | 30, 31, 34, 35 | OUTDATED | 88 | OUTDATED | 30, 31, 34, 35 | OUTDATED | 88 | OUTDATED | 30, 31, 34, 35 | IMPROPER | 88 | IMPROPER | 30, 31, 34, 35 | OUTDATED | 88 | OUTDATED | 30, 31, 34, 35 | OUTDATED | 88 | OUTDATED | 30, 31, 34, 35 | OUTDATED | 88 | OUTDATED | 30, 31, 34, 35 | OUTDATED | 88 | OUTDATED | 30, 31, 34, 35 | OUTDATED | 88 | OUTDATED | 30, 31, 34, 35 | OUTDATED | 88 | OUTDATED | 30, 31, 34, 35 | OUTDATED | 88 | OUTDATED | 30, 31, 34, 35 | OUTDATED | 88 | OUTDATED | 30, 31, 34, 35
47 | PLMB-PLUMBING
42 | CPQ11-DALI-DEVS-DATA-R24.rvt | CPQ11-DALI-DEVS-DATA-R22.rvt | DATA | AUTOBRÁS | 1116 | AUTOBRÁS | 1116 | V15 | 15/04/2026 | V2 | 02/06/2026 | V2 | 2026-06-02 | R24 |  | NEXT ROUND |  | 0% |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | REPROVED | 119 | 1% | FEDERADA-COL3 | OUTDATED | 119 | OUTDATED | FEDERADA-COL3 | OUTDATED | 119 | OUTDATED | FEDERADA-COL3
24 | CPQ11-EPMS-DEVS-DATA-R24.rvt | CPQ11-EPMS-DEVS-DATA-R22.rvt | DATA | BLACKBOX | 1114 | BLACKBOX | 1114 | V15 | 27/04/2026 | V3 | 12/07/2026 | V1 | 2026-05-15 | R24 | CAROL | NEXT ROUND |  | 0% |  | REPROVED | 4 | 1% | 35 | OUTDATED | 4 | OUTDATED | 35 | OUTDATED | 4 | OUTDATED | 35 | NEXT ROUND | 4 | NEXT ROUND | 35 | IMPROPER |  | IMPROPER |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | REPROVED |  | 1% |  | OUTDATED |  | OUTDATED |  | NEXT ROUND |  | NEXT ROUND |  | APPROVED | 4 | 100% | FEDERADA COL3 | PREVIOUSLY APPROVED | 4 | 100% | FEDERADA COL3
50 | MECH-MECHANICAL
7 | CPQ11-ARCH-HM90-DATA-R24.rvt | CPQ11-ARCH-HM90-DATA-R22.rvt | DATA | ZEUS/PORTEX | 1105 | SPBIM | 1127 | V9 | 27/03/2026 | V2 | 26/06/2026 | V1 | 2026-05-15 | R24 | ALINNE | NEXT ROUND |  | 0% |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | APPROVED |  | 100% | FEDERADO - COL3 | PREVIOUSLY APPROVED |  | 100% | FEDERADO - COL3 | PREVIOUSLY APPROVED |  | 100% | FEDERADO - COL3 | PREVIOUSLY APPROVED |  | 100% | FEDERADO - COL3
52 | STRC-STRUCTURE
55 | CPQ11-STRC-FLOO-DATA-R24.rvt | CPQ11-STRC-FLOO-DATA-R22.rvt | DATA | MODAX | 1121 | MODAX | 1121 | V1 | 05/05/2026 | V3 | 20/06/2026 | V3 | 2026-06-20 | R24 | FLAVIO | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NEXT ROUND |  | 0% |  | NEXT ROUND |  | 0% |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | APPROVED |  | 100% | FEDERADA - COL1, MODELO STRC - DEERNS, MODELO STEEL | PREVIOUSLY APPROVED |  | 100% | FEDERADA - COL1, MODELO STRC - DEERNS, MODELO STEEL | PREVIOUSLY APPROVED |  | 100% | FEDERADA - COL1, MODELO STRC - DEERNS, MODELO STEEL | PREVIOUSLY APPROVED |  | 100% | FEDERADA - COL1, MODELO STRC - DEERNS, MODELO STEEL
6 | CPQ11-ARCH-HMET-DATA-R24.rvt | CPQ11-ARCH-HMET-DATA-R22.rvt | DATA | S-VALE | 1104 | SPBIM | 1127 | V12 | 08/04/2026 | V1 | 15/05/2026 | V12 | 2026-04-08 | R22 | ALINNE | NEXT ROUND |  | 0% |  | APPROVED |  | 100% | 31, 34, 35 | PREVIOUSLY APPROVED |  | 100% | 31, 34, 35 | PREVIOUSLY APPROVED |  | 100% | 31, 34, 35 | PREVIOUSLY APPROVED |  | 100% | 31, 34, 35 | PREVIOUSLY APPROVED |  | 100% | 31, 34, 35 | PREVIOUSLY APPROVED |  | 100% | 31, 34, 35 | PREVIOUSLY APPROVED |  | 100% | 31, 34, 35 | PREVIOUSLY APPROVED |  | 100% | 31, 34, 35 | PREVIOUSLY APPROVED |  | 100% | 31, 34, 35 | PREVIOUSLY APPROVED |  | 100% | 31, 34, 35 | PREVIOUSLY APPROVED |  | 100% | 31, 34, 35 | PREVIOUSLY APPROVED |  | 100% | 31, 34, 35 | PREVIOUSLY APPROVED |  | 100% | 31, 34, 35 | PREVIOUSLY APPROVED |  | 100% | 31, 34, 35 | PREVIOUSLY APPROVED |  | 100% | 31, 34, 35
13 | CPQ11-ARCH-ROOF-DATA-R24.rvt | CPQ11-ARCH-ROOF-DATA-R22.rvt | DATA | OMNITRADE | 1110 | CADBIM | 1128 | V30 | 26/03/2026 | V2 | 20/05/2026 | V30 | 2026-03-26 | R22 | FLAVIO | APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100%
53 | CPQ11-STRC-CONC-DATA-R24.rvt | CPQ11-STRC-CONC-DATA-R22.rvt | DATA | SERV OBRAS | 1120 | TENAX | 0000 | V10 | 22/04/2026 | V1 | 15/05/2026 | V9 | 2026-03-13 | R22 | LUIZA | NEXT ROUND |  | 0% |  | APPROVED |  | 100% | 35, 36 | PREVIOUSLY APPROVED |  | 100% | 35, 36 | PREVIOUSLY APPROVED |  | 100% | 35, 36 | PREVIOUSLY APPROVED |  | 100% | 35, 36 | PREVIOUSLY APPROVED |  | 100% | 35, 36 | PREVIOUSLY APPROVED |  | 100% | 35, 36 | PREVIOUSLY APPROVED |  | 100% | 35, 36 | PREVIOUSLY APPROVED |  | 100% | 35, 36 | PREVIOUSLY APPROVED |  | 100% | 35, 36 | PREVIOUSLY APPROVED |  | 100% | 35, 36 | PREVIOUSLY APPROVED |  | 100% | 35, 36 | PREVIOUSLY APPROVED |  | 100% | 35, 36 | PREVIOUSLY APPROVED |  | 100% | 35, 36 | PREVIOUSLY APPROVED |  | 100% | 35, 36 | PREVIOUSLY APPROVED |  | 100% | 35, 36
54 | CPQ11-STRC-DPFN-DATA-R24.rvt | CPQ11-STRC-DPFN-DATA-R22.rvt | DATA | GEOFIX/TECNOGEO | 0000 | TENAX | 0000 | V11 | 28/04/2026 | V1 | 15/05/2026 | V10 | 2026-03-13 | R22 | CAROL | NEXT ROUND |  | 0% |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100%
59 | CPQ11-STRC-STEE-COL3-2X3.ifc | CPQ11-STRC-STEE-COL3-2X3.ifc | COL3 | METASA | 1125 | METASA | 1125 | V6 | 07/11/2025 | V1 | 21/05/2026 | V6 | 2026-11-07 | R22 | LUIZA | NEXT ROUND |  | 0% |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | APPROVED |  | 100% | 31, 34, 35 | PREVIOUSLY APPROVED |  | 100% | 31, 34, 35 | PREVIOUSLY APPROVED |  | 100% | 31, 34, 35 | PREVIOUSLY APPROVED |  | 100% | 31, 34, 35 | PREVIOUSLY APPROVED |  | 100% | 31, 34, 35 | PREVIOUSLY APPROVED |  | 100% | 31, 34, 35 | PREVIOUSLY APPROVED |  | 100% | 31, 34, 35 | PREVIOUSLY APPROVED |  | 100% | 31, 34, 35 | PREVIOUSLY APPROVED |  | 100% | 31, 34, 35 | PREVIOUSLY APPROVED |  | 100% | 31, 34, 35 | PREVIOUSLY APPROVED |  | 100% | 31, 34, 35 | PREVIOUSLY APPROVED |  | 100% | 31, 34, 35 | PREVIOUSLY APPROVED |  | 100% | 31, 34, 35
8 | CPQ11-ARCH-WMES-DATA-R24.rvt | CPQ11-ARCH-WMES-DATA-R22.rvt | DATA | S-VALE | 1104 | SPBIM | 1127 | V13 | 02/03/2026 | V3 | 24/06/2026 | V24 | 2026-05-29 | R24 | ALINNE | NEXT ROUND |  | 0% |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100%
30 | CPQ11-BASM-INFR-DATA-R24.rvt | CPQ11-BASM-INFR-DATA-R22.rvt | DATA | MENDES HOLLER | 1112 | PGMAK | 1129 | V33 | 04/03/2026 | V2 | 13/07/2026 | V1 | 2026-05-19 | R24 |  | NEXT ROUND |  | 0% |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | REPROVED | 275 | 1% | FEDERADO - COL3
34 | CPQ11-SCTY-INFR-DATA-R24.rvt | CPQ11-SCTY-INFR-DATA-R22.rvt | DATA | MENDES HOLLER | 1112 | PGMAK | 1129 | V39 | 19/03/2026 | V5 | 10/07/2026 | V5 | 2026-07-10 | R24 | CAROL | NEXT ROUND |  | 0% |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | REPROVED | 1 | 1% | FEDERADO - COL3
12 | CPQ11-ARCH-FACD-DATA-R24.rvt | CPQ11-ARCH-FACD-DATA-R22.rvt | DATA | OMNITRADE | 1110 | CADBIM | 1128 | V25 | 06/05/2026 | V3 | 07/07/2026 | V3 | 2026-07-07 | R24 | FLAVIO | REPROVED | 39 | 1% | 28, 29, 30 | NEXT ROUND | 39 | NEXT ROUND | 28, 29, 30 | NEXT ROUND | 39 | NEXT ROUND | 28, 29, 30 | REPROVED | 39 | 1% | 28, 29, 30 | OUTDATED | 39 | OUTDATED | 28, 29, 30 | NEXT ROUND | 39 | NEXT ROUND | 28, 29, 30 | NEXT ROUND | 39 | NEXT ROUND | 28, 29, 30 | NEXT ROUND | 39 | NEXT ROUND | 28, 29, 30 | NEXT ROUND | 39 | NEXT ROUND | 28, 29, 30 | NEXT ROUND | 39 | NEXT ROUND | 28, 29, 30 | NEXT ROUND | 39 | NEXT ROUND | 28, 29, 30 | NEXT ROUND | 39 | NEXT ROUND | 28, 29, 30 | IMPROPER | 39 | IMPROPER | 28, 29, 30 | OUTDATED | 39 | OUTDATED | 28, 29, 30 | NEXT ROUND | 39 | NEXT ROUND | 28, 29, 30 | REPROVED | 39 | 46% | FEDERADO - COL3

## LOD 500 - SITE
LOD 500 ¦ SITE
| FILE NAME (R24) | FILE NAME (R22) | AREA | TRADE COMPANY | CODE | BIM COMPANY | CODE | ACC VERSION (R22) | ACC FILE DATE (R22) | ACC VERSION (R24) | ACC FILE DATE (R24) | VERSION | FILE DATE | RVT TYPE APROVAL (SITE) | RESPONSAVEL | R0 - AUDIT STATUS | LAMPS QTDE | R0 - APPROVAL (%) | NUVEM UTILIZADA | R1 - AUDIT STATUS | LAMPS QTDE RESOLVIDAS - R1 | R1 - APPROVAL (%) | NUVEM UTILIZADA | R2 - AUDIT STATUS | LAMPS QTDE RESOLVIDAS - R2 | R2 - APPROVAL (%) | NUVEM UTILIZADA | R3 - AUDIT STATUS | LAMPS QTDE RESOLVIDAS - R3 | R3 - APPROVAL (%) | NUVEM UTILIZADA | R4 - AUDIT STATUS | R4 - LAMPS QTDE RESOLVIDAS - R4 | R4 - APPROVAL (%) | R4 NUVEM UTILIZADA | R5 - AUDIT STATUS | R5 - LAMPS QTDE RESOLVIDAS - R4 | R5 - APPROVAL (%) | R5 NUVEM UTILIZADA | R6 - AUDIT STATUS | R6 - LAMPS QTDE RESOLVIDAS - R4 | R6 - APPROVAL (%) | R6 NUVEM UTILIZADA | R7 - AUDIT STATUS | R7 - LAMPS QTDE RESOLVIDAS - R4 | R7 - APPROVAL (%) | R7 NUVEM UTILIZADA | R8 - AUDIT STATUS | R8 - LAMPS QTDE RESOLVIDAS | R8 - APPROVAL (%) | R8 NUVEM UTILIZADA | R9 - AUDIT STATUS | R9 - LAMPS QTDE RESOLVIDAS | R9 - APPROVAL (%) | R9 NUVEM UTILIZADA | R10 - AUDIT STATUS | R10 - LAMPS QTDE RESOLVIDAS | R10 - APPROVAL (%) | R10 NUVEM UTILIZADA | R11 - AUDIT STATUS | R11 - LAMPS QTDE RESOLVIDAS | R11 - APPROVAL (%) | R11 NUVEM UTILIZADA | R12 - AUDIT STATUS | R12 - LAMPS QTDE RESOLVIDAS | R12 - APPROVAL (%) | R12 NUVEM UTILIZADA | R13 - AUDIT STATUS | R13 - LAMPS QTDE RESOLVIDAS | R13 - APPROVAL (%) | R13 NUVEM UTILIZADA | R14 - AUDIT STATUS | R14 - LAMPS QTDE RESOLVIDAS | R14 - APPROVAL (%) | R14 NUVEM UTILIZADA | R15 - AUDIT STATUS | R15 - LAMPS QTDE RESOLVIDAS | R15 - APPROVAL (%) | R15 NUVEM UTILIZADA | R16 - AUDIT STATUS | R16 - LAMPS QTDE RESOLVIDAS | R16 - APPROVAL (%) | R16 NUVEM UTILIZADA | R17 - AUDIT STATUS | R17 - LAMPS QTDE RESOLVIDAS | R17 - APPROVAL (%) | R17 NUVEM UTILIZADA | R18 - AUDIT STATUS | R18 - LAMPS QTDE RESOLVIDAS | R18 - APPROVAL (%) | R18 NUVEM UTILIZADA | R19 - AUDIT STATUS | R19 - LAMPS QTDE RESOLVIDAS | R19 - APPROVAL (%) | R19 NUVEM UTILIZADA | R20 - AUDIT STATUS | R20 - LAMPS QTDE RESOLVIDAS | R20 - APPROVAL (%) | R20 NUVEM UTILIZADA | R21 - AUDIT STATUS | R21 - LAMPS QTDE RESOLVIDAS | R21 - APPROVAL (%) | R21 NUVEM UTILIZADA
8 | CPQ11-ARCH-CHAI-SITE-R24.rvt | CPQ11-ARCH-CHAI-SITE-R22.rvt | SITE | S-VALE | 1104 | SPBIM | 1127 | V12 | 06/04/2026 | V1 | 15/05/2026 | V12 | 2026-04-06 | R24 | ALINNE | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | 0% |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | OUTDATED |  | OUTDATED |  | REPROVED |  | 50% |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | ANALYSING |  | ANALYSING
61 | CPQ11-STRC-FLOO-SITE-R24.rvt | CPQ11-STRC-FLOO-SITE-R22.rvt | SITE | MODAX | 1121 | MODAX | 1121 | V1 | 05/05/2026 | V2 | 26/05/2026 | N/A | N/A | R24 | N/A | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NEXT ROUND |  | 0% |  | NEXT ROUND |  | 0% |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | ANALYSING |  | ANALYSING
44 | CPQ11-PLMB-PLMB-SITE-R24.rvt | CPQ11-PLMB-PLMB-SITE-R22.rvt | SITE | MENDES HOLLER | 1112 | PGMAK | 1129 | V27 | 08/04/2026 | V2 | 23/06/2026 | V1 | 2026-05-19 | R24 | N/A | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | REPROVED | 158 | 1% | 26, 27, 28, 29, 30, 38, DRONE 26.01.2026 | NEXT ROUND | 158 | NEXT ROUND | 26, 27, 28, 29, 30, 38, DRONE 26.01.2026 | NEXT ROUND | 158 | NEXT ROUND | 26, 27, 28, 29, 30, 38, DRONE 26.01.2026 | NEXT ROUND | 158 | NEXT ROUND | 26, 27, 28, 29, 30, 38, DRONE 26.01.2026 | NEXT ROUND | 158 | NEXT ROUND | 26, 27, 28, 29, 30, 38, DRONE 26.01.2026 | NEXT ROUND | 158 | NEXT ROUND | 26, 27, 28, 29, 30, 38, DRONE 26.01.2026 | NEXT ROUND | 158 | NEXT ROUND | 26, 27, 28, 29, 30, 38, DRONE 26.01.2026 | NEXT ROUND | 158 | NEXT ROUND | 26, 27, 28, 29, 30, 38, DRONE 26.01.2026 | NEXT ROUND | 158 | NEXT ROUND | 26, 27, 28, 29, 30, 38, DRONE 26.01.2026 | NEXT ROUND | 158 | NEXT ROUND | 26, 27, 28, 29, 30, 38, DRONE 26.01.2026 | NEXT ROUND | 158 | NEXT ROUND | 26, 27, 28, 29, 30, 38, DRONE 26.01.2026 | REPROVED | 5 | 3% | 26, 27, 28, 29, 30, 38, DRONE 26.01.2026 | OUTDATED | 5 | OUTDATED | 26, 27, 28, 29, 30, 38, DRONE 26.01.2026 | NEXT ROUND | 5 | NEXT ROUND | 26, 27, 28, 29, 30, 38, DRONE 26.01.2026 | NEXT ROUND | 5 | NEXT ROUND | 26, 27, 28, 29, 30, 38, DRONE 26.01.2026 | NEXT ROUND | 5 | NEXT ROUND | 26, 27, 28, 29, 30, 38, DRONE 26.01.2026 | ANALYSING | 5 | ANALYSING | 26, 27, 28, 29, 30, 38, DRONE 26.01.2026
24 | CPQ11-TCOM-DEVS-SITE-R24.rvt | CPQ11-TCOM-DEVS-SITE-R22.rvt | SITE | BLACKBOX | 1114 | BLACKBOX | 1114 | V14 | 29/04/2026 | V2 | 07/07/2026 | V1 | 15/05/2026 | R24 | NICOLE | REPROVED | 1 | 1% | DRONE 26.01.2026 | OUTDATED |  | OUTDATED | DRONE 26.01.2026 | OUTDATED |  | OUTDATED | DRONE 26.01.2026 | OUTDATED |  | OUTDATED | DRONE 26.01.2026 | OUTDATED |  | OUTDATED | DRONE 26.01.2026 | NEXT ROUND |  | NEXT ROUND | DRONE 26.01.2026 | REPROVED | 11 | 64.7% | 38, 39, 42, DRONE 26.01.2026 | OUTDATED | 11 | OUTDATED | 38, 39, 42, DRONE 26.01.2026 | OUTDATED | 11 | OUTDATED | 38, 39, 42, DRONE 26.01.2026 | OUTDATED | 11 | OUTDATED | 38, 39, 42, DRONE 26.01.2026 | NEXT ROUND | 11 | NEXT ROUND | 38, 39, 42, DRONE 26.01.2026 | NEXT ROUND | 11 | NEXT ROUND | 38, 39, 42, DRONE 26.01.2026 | REPROVED | 14 | 82% | 38, 39, 42, DRONE 26.01.2026 | IMPROPER | 14 | IMPROPER | 38, 39, 42, DRONE 26.01.2026 | OUTDATED | 14 | OUTDATED | 38, 39, 42, DRONE 26.01.2026 | OUTDATED | 14 | OUTDATED | 38, 39, 42, DRONE 26.01.2026 | OUTDATED | 14 | OUTDATED | 38, 39, 42, DRONE 26.01.2026 | OUTDATED | 14 | OUTDATED | 38, 39, 42, DRONE 26.01.2026 | OUTDATED | 14 | OUTDATED | 38, 39, 42, DRONE 26.01.2026 | OUTDATED | 14 | OUTDATED | 38, 39, 42, DRONE 26.01.2026 | NEXT ROUND | 14 | NEXT ROUND | 38, 39, 42, DRONE 26.01.2026 | ANALYSING | 14 | ANALYSING | 38, 39, 42, DRONE 26.01.2026
| CPQ11-SCTY-GATE-SITE-R24.rvt | CPQ11-SCTY-GATE-SITE-R24.rvt | SITE | FM SECURITY | 0000 | FM SECURITY | 0000 | V2 | 07/05/2026 | V5 | 08/07/2026 | V4 | 2026-07-02 | R24 | LUIZA | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | REPROVED | 0 | 1% | 39 e DRONE 26.01.2026 | OUTDATED | 0 | OUTDATED | 39 e DRONE 26.01.2026 | NEXT ROUND | 0 | NEXT ROUND | 39 e DRONE 26.01.2026 | NEXT ROUND | 0 | NEXT ROUND | 39 e DRONE 26.01.2026 | NEXT ROUND | 0 | NEXT ROUND | 39 e DRONE 26.01.2026 | NEXT ROUND | 0 | NEXT ROUND | 39 e DRONE 26.01.2026 | REPROVED | 2 | 25% | 39 e DRONE 26.01.2026 | OUTDATED | 2 | OUTDATED | 39 e DRONE 26.01.2026 | NEXT ROUND | 2 | NEXT ROUND | 39 e DRONE 26.01.2026 | REPROVED | 2 | 25% | 39 e DRONE 26.01.2026 | NEXT ROUND | 2 | NEXT ROUND | 39 e DRONE 26.01.2026 | REPROVED | 2 | 25% | DRONE MAIO-2026 | ANALYSING | 2 | ANALYSING | DRONE MAIO-2026
11 | CPQ11-ARCH-BLPR-GUAR-R24.rvt | CPQ11-ARCH-BLPR-GUAR-R22.rvt | GUAR | INOVAGLASS | 1109 | INOVAGLASS | 1109 | V9 | 04/12/2025 | V1 | 20/05/2026 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
12 | CPQ11-ARCH-PART-SITE-R24.rvt | CPQ11-ARCH-PART-SITE-R22.rvt | SITE | IDEIA DRYWALL | 1101 | FCH | 1126 | V14 | 18/03/2026 | V2 | 17/06/2026 | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
15 | CPQ11-ARCH-CEIL-SITE-R24.rvt | CPQ11-ARCH-CEIL-SITE-R22.rvt | SITE | IDEIA DRYWALL | 1101 | T2B | 0000 | V2 | 29/04/2026 | V1 | 12/06/2026 | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
20 | CPQ11-EPMS-DEVS-SITE-R24.rvt | CPQ11-EPMS-DEVS-SITE-R22.rvt | SITE | BLACKBOX | 1114 | BLACKBOX | 1114 | V11 | 03/02/2026 | V1 | 15/05/2026 | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
22 | CPQ11-ROIP-DEVS-GUAR-R24.rvt | CPQ11-ROIP-DEVS-GUAR-R22.rvt | GUAR | IB TECH | 1113 | IB TECH | 1113 | V12 | 13/05/2026 | V2 | 01/06/2026 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
26 | CPQ11-BASM-INFR-PUMP-R24.rvt | CPQ11-BASM-INFR-PUMP-R22.rvt | PUMP | MENDES HOLLER | 1112 | PGMAK | 1129 | V32 | 24/04/2026 | V3 | 03/07/2026 | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
1 | ARCH ¦ ARCHITECTURE
28 | CPQ11-BASM-DEVS-PUMP-R24.rvt | CPQ11-BASM-DEVS-PUMP-R22.rvt | PUMP | BLACKBOX | 1114 | BLACKBOX | 1114 | V14 | 03/02/2026 | V1 | 15/05/2026 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
30 | CPQ11-SCTY-INFR-SITE-R24.rvt | CPQ11-SCTY-INFR-SITE-R22.rvt | SITE | MENDES HOLLER | 1112 | PGMAK | 1129 | V34 | 05/05/2026 | V3 | 03/07/2026 | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
37 | CPQ11-ELEC-SPDA-SITE-R24.rvt | CPQ11-ELEC-SPDA-SITE-R22.rvt | SITE | MENDES HOLLER | 1112 | MENDES HOLLER | 1112 | V7 | 08/12/2025 | V2 | 03/07/2026 | N/A | N/A | N/A | N/A | NEXT ROUND |  | NEXT ROUND |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
42 | CPQ11-FPRT-METK-UTLS-R24.rvt | CPQ11-FPRT-METK-UTLS-R22.rvt | UTLS | PETROTANQUE | 1117 | CADBIM | 1128 | V16 | 06/03/2026 | V5 | 08/07/2026 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
47 | CPQ11-PLMB-METK-UTLS-R24.RVT | CPQ11-PLMB-METK-UTLS-R22.RVT | UTLS | STARCENTER | 1118 | STARCENTER | 1118 | V28 | 26/02/2026 | V1 | 19/05/2026 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
49 | CPQ11-MECH-MECH-GUAR-R24.rvt | CPQ11-MECH-MECH-GUAR-R22.rvt | GUAR | STARCENTER | 1118 | STARCENTER | 1118 | V23 | 16/04/2026 | V1 | 19/05/2026 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
60 | CPQ11-STRC-DPFN-SITE-R24.rvt | CPQ11-STRC-DPFN-SITE-R22.rvt | SITE | GEOFIX/TECNOGEO | 0000 | TENAX | 0000 | V13 | 12/05/2026 | V1 | 15/05/2026 | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
64 | CPQ11-STRC-STEE-UTLS-2X3.ifc | CPQ11-STRC-STEE-UTLS-2X3.ifc | UTLS | METASA | 1125 | METASA | 1125 | V6 | 11/02/2026 | V1 | 21/05/2026 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
65 | CPQ11-STRC-STEE-GUAR-2X3.ifc | CPQ11-STRC-STEE-GUAR-2X3.ifc | GUAR | METASA | 1125 | METASA | 1125 | V6 | 01/11/2025 | V1 | 21/05/2026 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
66 | CPQ11-STRC-STEE-STIR-2X3.ifc | CPQ11-STRC-STEE-STIR-2X3.ifc | STIR | METASA | 1125 | METASA | 1125 | V3 | 31/10/2025 | V1 | 21/05/2026 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
41 | CPQ11-FPRT-FPRT-SITE-R24.rvt | CPQ11-FPRT-FPRT-SITE-R22.rvt | SITE | MENDES HOLLER | 1112 | MENDES HOLLER | 1112 | V16 | 14/05/2026 | V4 | 13/07/2026 | V3 | 2026-06-24 | R24 | LUIZA | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | REPROVED | 16 - LAMPADAS INICIAIS | 1% | VISITA 14, 26, 28, 29, 30, 38, DRONE 26.01.2026 | OUTDATED | 16 - LAMPADAS INICIAIS | OUTDATED | VISITA 14, 26, 28, 29, 30, 38, DRONE 26.01.2026 | NEXT ROUND | 16 - LAMPADAS INICIAIS | NEXT ROUND | VISITA 14, 26, 28, 29, 30, 38, DRONE 26.01.2026 | NEXT ROUND | 16 - LAMPADAS INICIAIS | NEXT ROUND | VISITA 14, 26, 28, 29, 30, 38, DRONE 26.01.2026 | IMPROPER | 16 - LAMPADAS INICIAIS | IMPROPER | VISITA 14, 26, 28, 29, 30, 38, DRONE 26.01.2026 | IMPROPER |  | IMPROPER |  | OUTDATED |  | OUTDATED |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | IMPROPER |  | IMPROPER |  | OUTDATED |  | OUTDATED |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | IMPROPER |  | IMPROPER |  | OUTDATED |  | OUTDATED |  | NEXT ROUND |  | NEXT ROUND
17 | SYST-SYSTEMS ¦ INFRASTRUCTURE
2 | CPQ11-ARCH-ARCH-SITE-R24.rvt | CPQ11-ARCH-ARCH-SITE-R22.rvt | SITE | ARE ARQUITETURA | 1130 | ARE ARQUITETURA | 1130 | V28 | 17/04/2026 | V4 | 15/07/2026 | V3 | 2026-06-03 | R24 | LUIZA | REPROVED | 151 | 1% | 13, 14, 15, 26, 27, 28, 29, 30, 36, 38, 39, DRONE 31/07 | NEXT ROUND |  | NEXT ROUND | 13, 14, 15, 26, 27, 28, 29, 30, 36, 38, 39, DRONE 31/07 | NEXT ROUND |  | NEXT ROUND | 13, 14, 15, 26, 27, 28, 29, 30, 36, 38, 39, DRONE 31/07 | NEXT ROUND |  | NEXT ROUND | 13, 14, 15, 26, 27, 28, 29, 30, 36, 38, 39, DRONE 31/07 | REPROVED | 8 | 5% | 26, 27, 28, 29, 30, 36, 38, 39, DRONE 26.01.26 | OUTDATED | 8 | OUTDATED | 26, 27, 28, 29, 30, 36, 38, 39, DRONE 26.01.26 | OUTDATED | 8 | OUTDATED | 26, 27, 28, 29, 30, 36, 38, 39, DRONE 26.01.26 | NEXT ROUND | 8 | NEXT ROUND | 26, 27, 28, 29, 30, 36, 38, 39, DRONE 26.01.26 | REPROVED | 12 | 71% | DRONE 26.01.26 | NEXT ROUND | 12 | NEXT ROUND | DRONE 26.01.26 | NEXT ROUND | 12 | NEXT ROUND | DRONE 26.01.26 | NEXT ROUND | 12 | NEXT ROUND | DRONE 26.01.26 | REPROVED | 12 | 71% | DRONE 26.01.26 | NEXT ROUND | 12 | NEXT ROUND | DRONE 26.01.26 | NEXT ROUND | 12 | NEXT ROUND | DRONE 26.01.26 | REPROVED | 12 | 82% | DRONE 26.01.26 | IMPROPER | 12 | IMPROPER | DRONE 26.01.26 | OUTDATED | 12 | OUTDATED | DRONE 26.01.26 | OUTDATED | 12 | OUTDATED | DRONE 26.01.26 | OUTDATED | 12 | OUTDATED | DRONE 26.01.26 | OUTDATED | 12 | OUTDATED | DRONE 26.01.26 | NEXT ROUND | 12 | NEXT ROUND | DRONE 26.01.26
19 | EPMS-ELECTRICAL POWER MAN/AGEMENT SYSTEM ¦ DEVICES
5 | CPQ11-ARCH-FENC-SITE-R24.rvt | CPQ11-ARCH-FENC-SITE-R22.rvt | SITE | SERCOP | 1103 | ARE ARQUITETURA | 1130 | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | NOT PUBLISHED | N/A | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED
21 | ROIP-RADIO OVER IP ¦ DEVICES
9 | CPQ11-ARCH-NEWJ-SITE-R24.rvt | CPQ11-ARCH-NEWJ-SITE-R22.rvt | SITE | RACIONAL | 1106 | TENAX | 0000 | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | NOT PUBLISHED | N/A | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED
23 | TELECOM ¦ DEVICES
10 | CPQ11-ARCH-WTRP-SITE-R24.rvt | CPQ11-ARCH-WTRP-SITE-R22.rvt | SITE | ITS | 1107 | RBV | 0000 | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | NOT PUBLISHED | N/A | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED
25 | BAS-BUILDING AUTOMATION SYSTEM ¦ INFRASTRUCTURE
13 | CPQ11-ARCH-SGNV-SITE-R24.rvt | CPQ11-ARCH-SGNV-SITE-R22.rvt | SITE | VISUAL GEAC | 0000 | CONTRACTING | 0000 | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | NOT PUBLISHED | N/A | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED
27 | BAS ¦ DEVICES
14 | CPQ11-ARCH-SGNH-SITE-R24.rvt | CPQ11-ARCH-SGNH-SITE-R22.rvt | SITE | CONTRACTING | 0000 | CONTRACTING | 0000 | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | NOT PUBLISHED | N/A | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED
29 | SCTY-SECURITY ¦ INFRASTRUCTURE
51 | CPQ11-LAND-LAND-SITE-R24.rvt | CPQ11-LAND-LAND-SITE-R22.rvt | SITE | ORGANISMO VIVO | 0000 | CONTRACTING | 0000 | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | NOT PUBLISHED | N/A | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED
31 | SCTY ¦ DEVICES
56 | CPQ11-CIVL-SIGN-SITE-R24.rvt | CPQ11-CIVL-SIGN-SITE-R22.rvt | SITE | CONTRACTING | 0000 | CONTRACTING | 0000 | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | NOT PUBLISHED | N/A | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED
34 | ELEC-ELETRICAL
62 | CPQ11-STRC-CHAI-SITE-R24.rvt | CPQ11-STRC-CHAI-SITE-R22.rvt | SITE | S-VALE | 1104 | SPBIM | 1127 | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED
36 | SPDA ¦ PROTECTION SYSTEM ATMOSPHERIC DISCHARGE
38 | FALM-FIRE ALARM
40 | FPRT-FIRE PROTECTION
63 | CPQ11-STRC-FENC-SITE-R24.rvt | CPQ11-STRC-FENC-SITE-R22.rvt | SITE | SERCOP, SERV OBRAS | 1124 | CONTRACTING | 0000 | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED
35 | CPQ11-ELEC-ELEC-SITE-R24.rvt | CPQ11-ELEC-ELEC-SITE-R22.rvt | SITE | MENDES HOLLER | 1112 | PGMAK | 1129 | V33 | 05/03/2026 | V1 | 19/05/2026 | V1 | 2026-05-19 | R24 | GUI | NEXT ROUND |  | NEXT ROUND |  | REPROVED | 34 | 1% | DRONE 26.01.2026 | REPROVED | 0 | 1% | DRONE 26.01.2026 | NEXT ROUND |  | NEXT ROUND | DRONE 26.01.2026 | NEXT ROUND |  | NEXT ROUND | DRONE 26.01.2026 | NEXT ROUND |  | NEXT ROUND | DRONE 26.01.2026 | NEXT ROUND |  | NEXT ROUND | DRONE 26.01.2026 | NEXT ROUND |  | NEXT ROUND | DRONE 26.01.2026 | NEXT ROUND |  | NEXT ROUND | DRONE 26.01.2026 | NEXT ROUND |  | NEXT ROUND | DRONE 26.01.2026 | NEXT ROUND |  | NEXT ROUND | DRONE 26.01.2026 | NEXT ROUND |  | NEXT ROUND | DRONE 26.01.2026 | NEXT ROUND |  | NEXT ROUND | DRONE 26.01.2026 | NEXT ROUND |  | NEXT ROUND | DRONE 26.01.2026 | NEXT ROUND |  | NEXT ROUND | DRONE 26.01.2026 | NEXT ROUND |  | NEXT ROUND | DRONE 26.01.2026 | REPROVED | 0 | 1% | DRONE 26.01.2026 | OUTDATED | 0 | OUTDATED | DRONE 26.01.2026 | OUTDATED | 0 | OUTDATED | DRONE 26.01.2026 | OUTDATED | 0 | OUTDATED | DRONE 26.01.2026 | OUTDATED | 0 | OUTDATED | DRONE 26.01.2026 | OUTDATED | 0 | OUTDATED | DRONE 26.01.2026
43 | PLMB-PLUMBING
45 | CPQ11-PLMB-DIES-SITE-R24.rvt | CPQ11-PLMB-DIES-SITE-R22.rvt | SITE | MENDES HOLLER | 1112 | MENDES HOLLER | 1112 | V14 | 03/03/2026 | V4 | 13/07/2026 | V3 | 2026-06-19 | R24 | CAROL | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | REPROVED | 28 | 1% | 14, 15, 26, 27, 28, 29, 30, 38 | OUTDATED |  | OUTDATED | 14, 15, 26, 27, 28, 29, 30, 38 | OUTDATED |  | OUTDATED | 14, 15, 26, 27, 28, 29, 30, 38 | OUTDATED |  | OUTDATED | 14, 15, 26, 27, 28, 29, 30, 38 | OUTDATED |  | OUTDATED | 14, 15, 26, 27, 28, 29, 30, 38 | OUTDATED |  | OUTDATED | 14, 15, 26, 27, 28, 29, 30, 38 | OUTDATED |  | OUTDATED | 14, 15, 26, 27, 28, 29, 30, 38 | OUTDATED |  | OUTDATED | 14, 15, 26, 27, 28, 29, 30, 38 | OUTDATED |  | OUTDATED | 14, 15, 26, 27, 28, 29, 30, 38 | OUTDATED |  | OUTDATED | 14, 15, 26, 27, 28, 29, 30, 38 | IMPROPER | 0 | IMPROPER | 14, 15, 26, 27, 28, 29, 30, 38 | OUTDATED | 0 | OUTDATED | 14, 15, 26, 27, 28, 29, 30, 38 | REPROVED | 4 | 14% | 26, 27, 28, 29, 30 | NEXT ROUND | 4 | NEXT ROUND | 26, 27, 28, 29, 30 | REPROVED | 15 | 53% | 26, 27, 28, 29, 30 | NEXT ROUND | 15 | NEXT ROUND | 26, 27, 28, 29, 30 | REPROVED | 16 | 57% | DRONE - MAIO 2026 | APPROVED | 6 | 100% | DRONE - MAIO 2026 | PREVIOUSLY APPROVED | 6 | 100% | DRONE - MAIO 2026
16 | CPQ11-ARCH-STON-SITE-R24.rvt | CPQ11-ARCH-STON-SITE-R23.rvt | SITE | STONE | 0000 | STONE | 0000 | V10 | 11/05/2026 | V3 | 09/06/2026 | V3 | 2026-06-09 | R24 | CAROL | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | REPROVED |  | 1% | DRONE 26.01.2026 | OUTDATED |  | OUTDATED | DRONE 26.01.2026 | OUTDATED |  | OUTDATED | DRONE 26.01.2026 | REPROVED | 1 | 1% | DRONE 26.01.2026 | OUTDATED | 1 | OUTDATED | DRONE 26.01.2026 | IMPROPER | 0 | IMPROPER | DRONE 26.01.2026 | OUTDATED | 0 | OUTDATED | DRONE 26.01.2026 | NEXT ROUND | 0 | NEXT ROUND | DRONE 26.01.2026 | NEXT ROUND | 0 | NEXT ROUND | DRONE 26.01.2026 | NEXT ROUND | 0 | NEXT ROUND | DRONE 26.01.2026 | NEXT ROUND | 0 | NEXT ROUND | DRONE 26.01.2026 | NEXT ROUND | 0 | NEXT ROUND | DRONE 26.01.2026 | REPROVED | 0 | 1% | DRONE 26.01.2026 | NEXT ROUND | 0 | NEXT ROUND | DRONE 26.01.2026 | APPROVED | 1 | 100% | DRONE 26.01.2026 | PREVIOUSLY APPROVED | 1 | 100% | DRONE 26.01.2026 | PREVIOUSLY APPROVED | 1 | 100% | DRONE 26.01.2026 | PREVIOUSLY APPROVED | 1 | 100% | DRONE 26.01.2026 | PREVIOUSLY APPROVED | 1 | 100% | DRONE 26.01.2026
3 | CPQ11-ARCH-HMET-SITE-R24.rvt | CPQ11-ARCH-HMET-SITE-R22.rvt | SITE | S-VALE | 1104 | SPBIM | 1127 | V9 | 10/04/2026 | V1 | 15/05/2026 | V9 | 2026-04-10 | R22 | ALINNE | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | 0% |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | APPROVED |  | 100% |  | APPROVED | Ajuste conforme atualização de CHAI-SITE | 100% |  | PREVIOUSLY APPROVED | Ajuste conforme atualização de CHAI-SITE | 100% |  | PREVIOUSLY APPROVED | Ajuste conforme atualização de CHAI-SITE | 100% |  | PREVIOUSLY APPROVED | Ajuste conforme atualização de CHAI-SITE | 100% |  | PREVIOUSLY APPROVED | Ajuste conforme atualização de CHAI-SITE | 100% |  | PREVIOUSLY APPROVED | Ajuste conforme atualização de CHAI-SITE | 100% |  | PREVIOUSLY APPROVED | Ajuste conforme atualização de CHAI-SITE | 100% |  | PREVIOUSLY APPROVED | Ajuste conforme atualização de CHAI-SITE | 100% |  | PREVIOUSLY APPROVED | Ajuste conforme atualização de CHAI-SITE | 100% |  | PREVIOUSLY APPROVED | Ajuste conforme atualização de CHAI-SITE | 100% |  | PREVIOUSLY APPROVED | Ajuste conforme atualização de CHAI-SITE | 100% |  | PREVIOUSLY APPROVED | Ajuste conforme atualização de CHAI-SITE | 100% |  | PREVIOUSLY APPROVED | Ajuste conforme atualização de CHAI-SITE | 100% |  | PREVIOUSLY APPROVED | Ajuste conforme atualização de CHAI-SITE | 100% |  | PREVIOUSLY APPROVED | Ajuste conforme atualização de CHAI-SITE | 100%
48 | MECH-MECHANICAL
50 | LAND-LANDSCAPE
18 | CPQ11-SYST-INFR-SITE-R24.rvt | CPQ11-SYST-INFR-SITE-R22.rvt | SITE | MENDES HOLLER | 1112 | PGMAK | 1129 | V39 | 12/05/2026 | V4 | 14/07/2026 | V38 | 06/03/2026 | R24 | YASMIN | REPROVED | 7 | 1% | DRONE 26.01.2026 | NEXT ROUND |  | NEXT ROUND | DRONE 26.01.2026 | NEXT ROUND |  | NEXT ROUND | DRONE 26.01.2026 | NEXT ROUND |  | NEXT ROUND | DRONE 26.01.2026 | REPROVED | 1 | 14% | DRONE 26.01.2026 | OUTDATED | 1 | OUTDATED | DRONE 26.01.2026 | OUTDATED | 1 | OUTDATED | DRONE 26.01.2026 | OUTDATED | 1 | OUTDATED | DRONE 26.01.2026 | OUTDATED | 1 | OUTDATED | DRONE 26.01.2026 | OUTDATED | 1 | OUTDATED | DRONE 26.01.2026 | OUTDATED | 1 | OUTDATED | DRONE 26.01.2026 | OUTDATED | 1 | OUTDATED | DRONE 26.01.2026 | NEXT ROUND | 1 | NEXT ROUND | DRONE 26.01.2026 | APPROVED | 7 | 100% | DRONE 26.01.2026 | APPROVED | 7 | 100% | DRONE 26.01.2026 | PREVIOUSLY APPROVED | 7 | 100% | DRONE 26.01.2026 | PREVIOUSLY APPROVED | 7 | 100% | DRONE 26.01.2026 | PREVIOUSLY APPROVED | 7 | 100% | DRONE 26.01.2026 | PREVIOUSLY APPROVED | 7 | 100% | DRONE 26.01.2026 | PREVIOUSLY APPROVED | 7 | 100% | DRONE 26.01.2026 | PREVIOUSLY APPROVED | 7 | 100% | DRONE 26.01.2026 | PREVIOUSLY APPROVED | 7 | 100% | DRONE 26.01.2026
52 | CIVIL
32 | CPQ11-SCTY-DEVS-SITE-R24.rvt | CPQ11-SCTY-DEVS-SITE-R22.rvt | SITE | SEGURPRO | 1115 | SEGURPRO | 1115 | V37 | 10/04/2026 | V1 | 20/05/2026 | V37 | 2026-04-10 | R22 | LUIZA | REPROVED | 40 | 1% | BLK 36 & DRONE 26.01.26 | OUTDATED |  | OUTDATED | BLK 36 & DRONE 26.01.26 | NEXT ROUND |  | NEXT ROUND | BLK 36 & DRONE 26.01.26 | NEXT ROUND |  | NEXT ROUND | BLK 36 & DRONE 26.01.26 | REPROVED | 3 | 7.51% | BLK 36 & DRONE 26.01.26 | NEXT ROUND | 3 | NEXT ROUND | BLK 36 & DRONE 26.01.26 | REPROVED | 34 | 85% | VISITA 38 & DRONE 26.01.26 | NEXT ROUND | 34 | NEXT ROUND | VISITA 38 & DRONE 26.01.26 | APPROVED | 40 | 100% | VISITA 38 & DRONE 26.01.26 | PREVIOUSLY APPROVED | 40 | 100% | VISITA 38 & DRONE 26.01.26 | PREVIOUSLY APPROVED | 40 | 100% | VISITA 38 & DRONE 26.01.26 | PREVIOUSLY APPROVED | 40 | 100% | VISITA 38 & DRONE 26.01.26 | PREVIOUSLY APPROVED | 40 | 100% | VISITA 38 & DRONE 26.01.26 | PREVIOUSLY APPROVED | 40 | 100% | VISITA 38 & DRONE 26.01.26 | PREVIOUSLY APPROVED | 40 | 100% | VISITA 38 & DRONE 26.01.26 | PREVIOUSLY APPROVED | 40 | 100% | VISITA 38 & DRONE 26.01.26 | PREVIOUSLY APPROVED | 40 | 100% | VISITA 38 & DRONE 26.01.26 | PREVIOUSLY APPROVED | 40 | 100% | VISITA 38 & DRONE 26.01.26 | PREVIOUSLY APPROVED | 40 | 100% | VISITA 38 & DRONE 26.01.26 | PREVIOUSLY APPROVED | 40 | 100% | VISITA 38 & DRONE 26.01.26 | PREVIOUSLY APPROVED | 40 | 100% | VISITA 38 & DRONE 26.01.26 | PREVIOUSLY APPROVED | 40 | 100% | VISITA 38 & DRONE 26.01.26
39 | CPQ11-FALM-FALM-SITE-R24.rvt | CPQ11-FALM-FALM-SITE-R22.rvt | SITE | MENDES HOLLER | 1112 | MENDES HOLLER | 1112 | V11 | 08/05/2026 | V3 | 10/07/2026 | V7 | 03/03/2026 | R22 | GUI | NEXT ROUND |  | NEXT ROUND |  | APPROVED | 0 | 100% | DRONE 26.01.2026 | PREVIOUSLY APPROVED | 0 | 100% | DRONE 26.01.2026 | PREVIOUSLY APPROVED | 0 | 100% | DRONE 26.01.2026 | PREVIOUSLY APPROVED | 0 | 100% | DRONE 26.01.2026 | PREVIOUSLY APPROVED | 0 | 100% | DRONE 26.01.2026 | PREVIOUSLY APPROVED | 0 | 100% | DRONE 26.01.2026 | PREVIOUSLY APPROVED | 0 | 100% | DRONE 26.01.2026 | PREVIOUSLY APPROVED | 0 | 100% | DRONE 26.01.2026 | PREVIOUSLY APPROVED | 0 | 100% | DRONE 26.01.2026 | PREVIOUSLY APPROVED | 0 | 100% | DRONE 26.01.2026 | PREVIOUSLY APPROVED | 0 | 100% | DRONE 26.01.2026 | PREVIOUSLY APPROVED | 0 | 100% | DRONE 26.01.2026 | PREVIOUSLY APPROVED | 0 | 100% | DRONE 26.01.2026 | PREVIOUSLY APPROVED | 0 | 100% | DRONE 26.01.2026 | PREVIOUSLY APPROVED | 0 | 100% | DRONE 26.01.2026 | PREVIOUSLY APPROVED | 0 | 100% | DRONE 26.01.2026 | PREVIOUSLY APPROVED | 0 | 100% | DRONE 26.01.2026 | PREVIOUSLY APPROVED | 0 | 100% | DRONE 26.01.2026 | PREVIOUSLY APPROVED | 0 | 100% | DRONE 26.01.2026 | PREVIOUSLY APPROVED | 0 | 100% | DRONE 26.01.2026 | PREVIOUSLY APPROVED | 0 | 100% | DRONE 26.01.2026
46 | CPQ11-PLMB-NPWT-SITE-R24.rvt | CPQ11-PLMB-NPWT-SITE-R22.rvt | SITE | STARCENTER | 1118 | STARCENTER | 1118 | V46 | 24/04/2026 | V2 | 15/06/2026 | V43 | 2026-03-20 | R22 | LUIZA | REPROVED | 3 | 1% | 13, 14, 15, 26, 27, 28, 29, 30, 36, 38, 39 | OUTDATED |  | OUTDATED | 13, 14, 15, 26, 27, 28, 29, 30, 36, 38, 39 | NEXT ROUND |  | NEXT ROUND | 13, 14, 15, 26, 27, 28, 29, 30, 36, 38, 39 | NEXT ROUND |  | NEXT ROUND | 13, 14, 15, 26, 27, 28, 29, 30, 36, 38, 39 | NEXT ROUND |  | NEXT ROUND | 13, 14, 15, 26, 27, 28, 29, 30, 36, 38, 39 | APPROVED | 3 | 100% | DRONE 26.01.2026 | PREVIOUSLY APPROVED | 3 | 100% | DRONE 26.01.2026 | PREVIOUSLY APPROVED | 3 | 100% | DRONE 26.01.2026 | PREVIOUSLY APPROVED | 3 | 100% | DRONE 26.01.2026 | PREVIOUSLY APPROVED | 3 | 100% | DRONE 26.01.2026 | PREVIOUSLY APPROVED | 3 | 100% | DRONE 26.01.2026 | PREVIOUSLY APPROVED | 3 | 100% | DRONE 26.01.2026 | PREVIOUSLY APPROVED | 3 | 100% | DRONE 26.01.2026 | PREVIOUSLY APPROVED | 3 | 100% | DRONE 26.01.2026 | PREVIOUSLY APPROVED | 3 | 100% | DRONE 26.01.2026 | PREVIOUSLY APPROVED | 3 | 100% | DRONE 26.01.2026 | PREVIOUSLY APPROVED | 3 | 100% | DRONE 26.01.2026 | PREVIOUSLY APPROVED | 3 | 100% | DRONE 26.01.2026 | PREVIOUSLY APPROVED | 3 | 100% | DRONE 26.01.2026 | PREVIOUSLY APPROVED | 3 | 100% | DRONE 26.01.2026 | PREVIOUSLY APPROVED | 3 | 100% | DRONE 26.01.2026 | PREVIOUSLY APPROVED | 3 | 100% | DRONE 26.01.2026
58 | STRC-STRUCTURE
53 | CPQ11-CIVL-DRNG-SITE-R24.rvt | CPQ11-CIVL-DRNG-SITE-R22.rvt | SITE | GARCIA | 1119 | CADBIM | 1128 | V20 | 06/05/2026 | V4 | 11/06/2026 | V20 | 2026-05-06 | R22 | LUIZA | NEXT ROUND |  | NEXT ROUND |  | REPROVED | 92 | 1% | DRONE 26.01.2026 | REPROVED | 0 | 1% | DRONE 26.01.2026 | NEXT ROUND |  | NEXT ROUND | DRONE 26.01.2026 | NEXT ROUND |  | NEXT ROUND | DRONE 26.01.2026 | REPROVED | 21 | 22% | DRONE 26.01.2026 | NEXT ROUND | 21 | NEXT ROUND | DRONE 26.01.2026 | REPROVED | 54 | 59% | DRONE 26.01.2026 | NEXT ROUND | 54 | NEXT ROUND | DRONE 26.01.2026 | NEXT ROUND | 54 | NEXT ROUND | DRONE 26.01.2026 | REPROVED | 54 | 59% | DRONE 26.01.2026 | NEXT ROUND | 54 | NEXT ROUND | DRONE 26.01.2026 | APPROVED | 92 | 100% | DRONE 26.01.2026 | PREVIOUSLY APPROVED | 92 | 100% | DRONE 26.01.2026 | PREVIOUSLY APPROVED | 92 | 100% | DRONE 26.01.2026 | PREVIOUSLY APPROVED | 92 | 100% | DRONE 26.01.2026 | PREVIOUSLY APPROVED | 92 | 100% | DRONE 26.01.2026 | PREVIOUSLY APPROVED | 92 | 100% | DRONE 26.01.2026 | PREVIOUSLY APPROVED | 92 | 100% | DRONE 26.01.2026 | PREVIOUSLY APPROVED | 92 | 100% | DRONE 26.01.2026 | PREVIOUSLY APPROVED | 92 | 100% | DRONE 26.01.2026 | PREVIOUSLY APPROVED | 92 | 100% | DRONE 26.01.2026
54 | CPQ11-CIVL-ERTH-SITE-R24.rvt | CPQ11-CIVL-ERTH-SITE-R22.rvt | SITE | GARCIA | 1119 | CADBIM | 1128 | V18 | 08/04/2026 | V6 | 24/06/2026 | V18 | 2026-04-08 | R22 | CAROL | REPROVED | 14 | 1% | DRONE 30.01.26 | OUTDATED |  | OUTDATED | DRONE 30.01.26 | NEXT ROUND |  | NEXT ROUND | DRONE 30.01.26 | NEXT ROUND |  | NEXT ROUND | DRONE 30.01.26 | REPROVED | 0 | 1% | DRONE 30.01.26 | REPROVED | 8 | 62% | DRONE 26.01.26 | REPROVED | 9 | 69.23% | DRONE 26.01.26 | NEXT ROUND | 9 | NEXT ROUND | DRONE 26.01.26 | NEXT ROUND | 9 | NEXT ROUND | DRONE 26.01.26 | APPROVED | 13 | 100% | DRONE 26.01.26 | PREVIOUSLY APPROVED | 13 | 100% | DRONE 26.01.26 | PREVIOUSLY APPROVED | 13 | 100% | DRONE 26.01.26 | PREVIOUSLY APPROVED | 13 | 100% | DRONE 26.01.26 | PREVIOUSLY APPROVED | 13 | 100% | DRONE 26.01.26 | PREVIOUSLY APPROVED | 13 | 100% | DRONE 26.01.26 | PREVIOUSLY APPROVED | 13 | 100% | DRONE 26.01.26 | PREVIOUSLY APPROVED | 13 | 100% | DRONE 26.01.26 | PREVIOUSLY APPROVED | 13 | 100% | DRONE 26.01.26 | PREVIOUSLY APPROVED | 13 | 100% | DRONE 26.01.26 | PREVIOUSLY APPROVED | 13 | 100% | DRONE 26.01.26 | PREVIOUSLY APPROVED | 13 | 100% | DRONE 26.01.26 | PREVIOUSLY APPROVED | 13 | 100% | DRONE 26.01.26
55 | CPQ11-CIVL-PAVM-SITE-R24.rvt | CPQ11-CIVL-PAVM-SITE-R22.rvt | SITE | GARCIA | 1119 | CADBIM | 1128 | V18 | 30/04/2026 | V2 | 20/05/2026 | V18 | 2026-04-30 | R22 | FLAVIO | REPROVED | 121 | 1% | 13, 14, 15, 26, 27, 28, 29, 30, 36, 38, 39, DRONE 31/07 | OUTDATED |  | OUTDATED | 13, 14, 15, 26, 27, 28, 29, 30, 36, 38, 39, DRONE 31/07 | NEXT ROUND |  | NEXT ROUND | 13, 14, 15, 26, 27, 28, 29, 30, 36, 38, 39, DRONE 31/07 | NEXT ROUND |  | NEXT ROUND |  | REPROVED | 31 | 25.61% | 26, 27, 28, 29, 30, 36, 38, 39, DRONE 26.01.2026 | NEXT ROUND | 31 | NEXT ROUND | 26, 27, 28, 29, 30, 36, 38, 39, DRONE 26.01.2026 | REPROVED | 70 | 57% | DRONE 26.01.2026 | NEXT ROUND | 70 | NEXT ROUND | DRONE 26.01.2026 | NEXT ROUND | 70 | NEXT ROUND | DRONE 26.01.2026 | REPROVED | 83 | 68% | DRONE 26.01.2026 | REPROVED | 83 | 87% | DRONE 26.01.2026 | APPROVED | 121 | 100% | DRONE 26.01.2026 | PREVIOUSLY APPROVED | 121 | 100% | DRONE 26.01.2026 | PREVIOUSLY APPROVED | 121 | 100% | DRONE 26.01.2026 | PREVIOUSLY APPROVED | 121 | 100% | DRONE 26.01.2026 | PREVIOUSLY APPROVED | 121 | 100% | DRONE 26.01.2026 | PREVIOUSLY APPROVED | 121 | 100% | DRONE 26.01.2026 | PREVIOUSLY APPROVED | 121 | 100% | DRONE 26.01.2026 | PREVIOUSLY APPROVED | 121 | 100% | DRONE 26.01.2026 | PREVIOUSLY APPROVED | 121 | 100% | DRONE 26.01.2026 | PREVIOUSLY APPROVED | 121 | 100% | DRONE 26.01.2026 | PREVIOUSLY APPROVED | 121 | 100% | DRONE 26.01.2026
57 | CPQ11-CIVL-LOCK-SITE-R24.rvt | CPQ11-CIVL-LOCK-SITE-R22.rvt | SITE | STEINER | 0000 | PMD | 0000 | V11 | 21/03/2026 | V1 | 18/05/2026 | V11 | 2026-03-21 | R22 | CAROL | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | REPROVED | 3 | 1% | DRONE 26.01.2026 | NEXT ROUND |  | NEXT ROUND | DRONE 26.01.2026 | APPROVED | 3 | 100% | DRONE 26.01.2026 | PREVIOUSLY APPROVED | 3 | 100% | DRONE 26.01.2026 | PREVIOUSLY APPROVED | 3 | 100% | DRONE 26.01.2026 | PREVIOUSLY APPROVED | 3 | 100% | DRONE 26.01.2026 | PREVIOUSLY APPROVED | 3 | 100% | DRONE 26.01.2026 | PREVIOUSLY APPROVED | 3 | 100% | DRONE 26.01.2026 | PREVIOUSLY APPROVED | 3 | 100% | DRONE 26.01.2026 | PREVIOUSLY APPROVED | 3 | 100% | DRONE 26.01.2026 | PREVIOUSLY APPROVED | 3 | 100% | DRONE 26.01.2026 | PREVIOUSLY APPROVED | 3 | 100% | DRONE 26.01.2026 | PREVIOUSLY APPROVED | 3 | 100% | DRONE 26.01.2026 | PREVIOUSLY APPROVED | 3 | 100% | DRONE 26.01.2026 | PREVIOUSLY APPROVED | 3 | 100% | DRONE 26.01.2026 | PREVIOUSLY APPROVED | 3 | 100% | DRONE 26.01.2026 | PREVIOUSLY APPROVED | 3 | 100% | DRONE 26.01.2026 | PREVIOUSLY APPROVED | 3 | 100% | DRONE 26.01.2026 | PREVIOUSLY APPROVED | 3 | 100% | DRONE 26.01.2026
59 | CPQ11-STRC-CONC-SITE-R24.rvt | CPQ11-STRC-CONC-SITE-R22.rvt | SITE | SERV OBRAS | 1120 | TENAX | 0000 | V17 | 12/05/2026 | V1 | 15/05/2026 | V1 | 2026-05-15 | R24 | YASMIN | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND | VISITA 13,14,29 E DRONE 26.01.2026 | REPROVED | 33 LAMPADAS INICIAIS | 1% | VISITA 13,14,29 E DRONE 26.01.2026 | OUTDATED | 33 LAMPADAS INICIAIS | OUTDATED | VISITA 13,14,29 E DRONE 26.01.2026 | OUTDATED | 33 LAMPADAS INICIAIS | OUTDATED | VISITA 13,14,29 E DRONE 26.01.2026 | OUTDATED | 33 LAMPADAS INICIAIS | OUTDATED | VISITA 13,14,29 E DRONE 26.01.2026 | NEXT ROUND | 33 LAMPADAS INICIAIS | NEXT ROUND | VISITA 13,14,29 E DRONE 26.01.2026 | REPROVED | 3 | 9% | VISITA 13,14,29 E DRONE 26.01.2026 | OUTDATED | 3 | OUTDATED | VISITA 13,14,29 E DRONE 26.01.2026 | NEXT ROUND | 3 | NEXT ROUND | VISITA 13,14,29 E DRONE 26.01.2026 | NEXT ROUND | 3 | NEXT ROUND | VISITA 13,14,29 E DRONE 26.01.2026 | NEXT ROUND | 3 | NEXT ROUND | VISITA 13,14,29 E DRONE 26.01.2026 | APPROVED | 33 | 100% | VISITA 13,14,29 E DRONE 26.01.2026 | PREVIOUSLY APPROVED | 33 | 100% | VISITA 13,14,29 E DRONE 26.01.2026 | PREVIOUSLY APPROVED | 33 | 100% | VISITA 13,14,29 E DRONE 26.01.2026 | PREVIOUSLY APPROVED | 33 | 100% | VISITA 13,14,29 E DRONE 26.01.2026 | PREVIOUSLY APPROVED | 33 | 100% | VISITA 13,14,29 E DRONE 26.01.2026 | PREVIOUSLY APPROVED | 33 | 100% | VISITA 13,14,29 E DRONE 26.01.2026 | PREVIOUSLY APPROVED | 33 | 100% | VISITA 13,14,29 E DRONE 26.01.2026
6 | CPQ11-ARCH-METL-SITE-R24.rvt | CPQ11-ARCH-METL-SITE-R22.rvt | SITE | SERCOP | 1103 | ARE ARQUITETURA | 1130 | V12 | 05/05/2026 | V5 | 22/06/2026 | V5 | 2026-06-22 | R24 | CAROL | REPROVED | 38 | 1% | DRONE 26.01.26 | NEXT ROUND |  | NEXT ROUND | DRONE 26.01.26 | NEXT ROUND |  | NEXT ROUND | DRONE 26.01.26 | NEXT ROUND |  | NEXT ROUND | DRONE 26.01.26 | REPROVED | 9 | 23.68% | DRONE 26.01.26 | NEXT ROUND |  | NEXT ROUND | DRONE 26.01.26 | REPROVED | 5 | 36.8% | 21, 36, 39, 42, DRONE 26.01.26 | NEXT ROUND | 5 | NEXT ROUND | 21, 36, 39, 42, DRONE 26.01.26 | REPROVED | 15 | 39% | 21, 36, 39, 42, DRONE 26.01.26 | REPROVED | 15 | 39% | 21, 36, 39, 42, DRONE 26.01.26 | OUTDATED | 15 | OUTDATED | 21, 36, 39, 42, DRONE 26.01.26 | NEXT ROUND | 15 | NEXT ROUND | 21, 36, 39, 42, DRONE 26.01.26 | NEXT ROUND | 15 | NEXT ROUND | 21, 36, 39, 42, DRONE 26.01.26 | NEXT ROUND | 15 | NEXT ROUND | 21, 36, 39, 42, DRONE 26.01.26 | NEXT ROUND | 15 | NEXT ROUND | 21, 36, 39, 42, DRONE 26.01.26 | NEXT ROUND | 15 | NEXT ROUND | 21, 36, 39, 42, DRONE 26.01.26 | NEXT ROUND | 15 | NEXT ROUND | 21, 36, 39, 42, DRONE 26.01.26 | REPROVED | 15 | 39% | 21, 36, 39, 42, DRONE 26.01.26 | NEXT ROUND | 15 | NEXT ROUND | 21, 36, 39, 42, DRONE 26.01.26 | NEXT ROUND | 15 | NEXT ROUND | 21, 36, 39, 42, DRONE 26.01.26 | NEXT ROUND | 15 | NEXT ROUND | 21, 36, 39, 42, DRONE 26.01.26 | REPROVED | 24 | 63% | DRONE 26.01.26
Note on AL5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Quantidade de lâmpadas criadas Round equivalente a 0
Note on Q16: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Modelo não possui elementos fora das áreas de Utilities e Guardhouse, e portanto deve ser auditado somente nesses setores.
Note on U17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Modelo não possui elementos fora das áreas de Utilities, e portanto deve ser auditado somente nesse setor.
Note on AP51: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Lâmpada inserida Round equivalente ao 0

## LOD 500 - GUAR
LOD 500 ¦ GUAR
| FILE NAME (R24) | FILE NAME (R22) | AREA | TRADE COMPANY | CODE | BIM COMPANY | CODE | ACC VERSION (R22) | ACC FILE DATE (R22) | ACC VERSION (R24) | ACC FILE DATE (R24) | VERSION | FILE DATE | RVT TYPE APROVAL (GUAR) | RESPONSAVEL | R0 - AUDIT STATUS | LAMPS QTDE | R0 - AUDIT STATUS | NUVEM UTILIZADA | ESTIMATED DELIVERY R0 | R1 - AUDIT STATUS | LAMPS QTDE RESOLVIDAS - R1 | R1 - APPROVAL (%) | NUVEM UTILIZADA | R2 - AUDIT STATUS | LAMPS QTDE RESOLVIDAS - R2 | R2 - APPROVAL (%) | R2 - NUVEM UTILIZADA | R3 - AUDIT STATUS | R3 - LAMPS QTDE RESOLVIDAS | R3 - APPROVAL (%) | R3 - NUVEM UTILIZADA | R4- AUDIT STATUS | R4 - LAMPS QTDE RESOLVIDAS | R4 - APPROVAL (%) | R4 - NUVEM UTILIZADA | R5- AUDIT STATUS | R5 - LAMPS QTDE RESOLVIDAS | R5 - APPROVAL (%) | R5 - NUVEM UTILIZADA | R6- AUDIT STATUS | R6 - LAMPS QTDE RESOLVIDAS | R6 - APPROVAL (%) | R6 - NUVEM UTILIZADA | R7- AUDIT STATUS | R7 - LAMPS QTDE RESOLVIDAS | R7 - APPROVAL (%) | R7 - NUVEM UTILIZADA | R8- AUDIT STATUS | R8 - LAMPS QTDE RESOLVIDAS | R8 - APPROVAL (%) | R8 - NUVEM UTILIZADA | R9- AUDIT STATUS | R9 - LAMPS QTDE RESOLVIDAS | R9 - APPROVAL (%) | R9 - NUVEM UTILIZADA | R10- AUDIT STATUS | R10 - LAMPS QTDE RESOLVIDAS | R10 - APPROVAL (%) | R10 - NUVEM UTILIZADA | R11- AUDIT STATUS | R11 - LAMPS QTDE RESOLVIDAS | R11 - APPROVAL (%) | R11 - NUVEM UTILIZADA | R12- AUDIT STATUS | R12 - LAMPS QTDE RESOLVIDAS | R12 - APPROVAL (%) | R12 - NUVEM UTILIZADA | R13- AUDIT STATUS | R13 - LAMPS QTDE RESOLVIDAS | R13 - APPROVAL (%) | R13 - NUVEM UTILIZADA | R14- AUDIT STATUS | R14 - LAMPS QTDE RESOLVIDAS | R14 - APPROVAL (%) | R14 - NUVEM UTILIZADA | R15- AUDIT STATUS | R15 - LAMPS QTDE RESOLVIDAS | R15 - APPROVAL (%) | R15 - NUVEM UTILIZADA | R16- AUDIT STATUS | R16 - LAMPS QTDE RESOLVIDAS | R16 - APPROVAL (%) | R16 - NUVEM UTILIZADA | R17- AUDIT STATUS | R17 - LAMPS QTDE RESOLVIDAS | R17 - APPROVAL (%) | R17 - NUVEM UTILIZADA | R18- AUDIT STATUS | R18 - LAMPS QTDE RESOLVIDAS | R18 - APPROVAL (%) | R18 - NUVEM UTILIZADA | R19- AUDIT STATUS | R19 - LAMPS QTDE RESOLVIDAS | R19 - APPROVAL (%) | R19 - NUVEM UTILIZADA | R20 - AUDIT STATUS | R20 - LAMPS QTDE RESOLVIDAS | R20 - APPROVAL (%) | R20 - NUVEM UTILIZADA | R21 - AUDIT STATUS | R21 - LAMPS QTDE RESOLVIDAS | R21 - APPROVAL (%) | R21 - NUVEM UTILIZADA | R22 - AUDIT STATUS | R22 - LAMPS QTDE RESOLVIDAS | R22 - APPROVAL (%) | R22 - NUVEM UTILIZADA | R23 - AUDIT STATUS | R23 - LAMPS QTDE RESOLVIDAS | R23 - APPROVAL (%) | R23 - NUVEM UTILIZADA | R24 - AUDIT STATUS | R24 - LAMPS QTDE RESOLVIDAS | R24 - APPROVAL (%) | R24 - NUVEM UTILIZADA | R25 - AUDIT STATUS | R25 - LAMPS QTDE RESOLVIDAS | R25 - APPROVAL (%) | R25 - NUVEM UTILIZADA
1 | ARCH ¦ ARCHITECTURE
66 | CPQ11-SCTY-GATE-SITE-R24.rvt | CPQ11-SCTY-GATE-SITE-R24.rvt | SITE | FM SECURITY | 0000 | FM SECURITY | 0000 | V2 | 07/05/2026 | V5 | 08/07/2026 | N/A | N/A | R24 |  | NOT PUBLISHED |  | NOT PUBLISHED |  |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NEXT ROUND |  | 0% |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | ANALYSING |  | ANALYSING
12 | CPQ11-ARCH-PART-SITE-R24.rvt | CPQ11-ARCH-PART-SITE-R22.rvt | SITE | IDEIA DRYWALL | 1101 | FCH | 1126 | V14 | 18/03/2026 | V2 | 17/06/2026 | V2 | 2026-06-17 | R24 | CAROL | REPROVED | 2 | 1% | 21 | 2025-01-07 | OUTDATED | 2 | OUTDATED | 21 | OUTDATED | 2 | OUTDATED | 21 | OUTDATED | 2 | OUTDATED | 21 | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | NEXT ROUND |  | NEXT ROUND |  | REPROVED | 0 | 1% | 21 | OUTDATED | 0 | OUTDATED | 21 | OUTDATED | 0 | OUTDATED | 21 | OUTDATED | 0 | OUTDATED | 21 | OUTDATED | 0 | OUTDATED | 21 | OUTDATED | 0 | OUTDATED | 21 | OUTDATED | 0 | OUTDATED | 21 | OUTDATED | 0 | OUTDATED | 21 | IMPROPER | 0 | IMPROPER | 21 | OUTDATED | 0 | OUTDATED | 21 | OUTDATED | 0 | OUTDATED | 21 | OUTDATED | 0 | OUTDATED | 21 | NEXT ROUND | 0 | NEXT ROUND | 21 | NEXT ROUND | 0 | NEXT ROUND | 21 | NEXT ROUND | 0 | NEXT ROUND | 21 | NEXT ROUND | 0 | NEXT ROUND | 21 | ANALYSING | 0 | ANALYSING | 21
39 | CPQ11-FALM-FALM-SITE-R24.rvt | CPQ11-FALM-FALM-SITE-R22.rvt | SITE | MENDES HOLLER | 1112 | MENDES HOLLER | 1112 | V11 | 08/05/2026 | V3 | 10/07/2026 | V2 | 2026-06-23 | R24 | ALINNE | NEXT ROUND |  | NEXT ROUND | NÃO FOI POSSIVEL AUDITAR | 2025-01-07 | REPROVED | 4 | 1% | 39 | OUTDATED | 4 | OUTDATED | 39 | NEXT ROUND | 4 | NEXT ROUND | 39 | IMPROPER | 0 | IMPROPER | 39 | OUTDATED | 0 | OUTDATED | 39 | NEXT ROUND | 0 | NEXT ROUND | 39 | NEXT ROUND | 0 | NEXT ROUND | 39 | NEXT ROUND | 0 | NEXT ROUND | 39 | NEXT ROUND | 0 | NEXT ROUND | 39 | NEXT ROUND | 0 | NEXT ROUND | 39 | NEXT ROUND | 0 | NEXT ROUND | 39 | NEXT ROUND | 0 | NEXT ROUND | 39 | NEXT ROUND | 0 | NEXT ROUND | 39 | NEXT ROUND | 0 | NEXT ROUND | 39 | NEXT ROUND | 0 | NEXT ROUND | 39 | NEXT ROUND | 0 | NEXT ROUND | 39 | NEXT ROUND | 0 | NEXT ROUND | 39 | IMPROPER | 0 | IMPROPER | 39 | OUTDATED | 0 | OUTDATED | 39 | OUTDATED | 0 | OUTDATED | 39 | OUTDATED | 0 | OUTDATED | 39 | IMPROPER | 0 | IMPROPER | 39 | IMPROPER | 0 | IMPROPER | 39 | NEXT ROUND | 0 | NEXT ROUND | 39 | ANALYSING | 0 | ANALYSING | 39
18 | CPQ11-SYST-INFR-SITE-R24.rvt | CPQ11-SYST-INFR-SITE-R22.rvt | SITE | MENDES HOLLER | 1112 | PGMAK | 1129 | V39 | 12/05/2026 | V4 | 14/07/2026 | V4 | 2026-07-14 | R24 | FLAVIO | NEXT ROUND | 20 | NEXT ROUND | NÃO FOI POSSIVEL AUDITAR | 2025-01-07 | REPROVED | 20 | 1% | 39 | OUTDATED | 20 | OUTDATED | 39 | OUTDATED | 20 | OUTDATED | 39 | IMPROPER | 0 | IMPROPER | 39 | NEXT ROUND | 0 | NEXT ROUND | 39 | NEXT ROUND | 0 | NEXT ROUND | 39 | NEXT ROUND | 0 | NEXT ROUND | 39 | REPROVED | 0 | 1% | 39 | OUTDATED | 0 | OUTDATED | 39 | OUTDATED | 0 | OUTDATED | 39 | OUTDATED | 0 | OUTDATED | 39 | OUTDATED | 0 | OUTDATED | 39 | OUTDATED | 0 | OUTDATED | 39 | OUTDATED | 0 | OUTDATED | 39 | OUTDATED | 0 | OUTDATED | 39 | NEXT ROUND | 0 | NEXT ROUND | 39 | REPROVED | 3 | 15% | 39 | OUTDATED | 3 | OUTDATED | 39 | OUTDATED | 3 | OUTDATED | 39 | OUTDATED | 3 | OUTDATED | 39 | OUTDATED | 3 | OUTDATED | 39 | NEXT ROUND | 3 | NEXT ROUND | 39 | REPROVED | 10 | 58% | FEDERADO-ANEXO | NEXT ROUND | 10 | NEXT ROUND | FEDERADO-ANEXO | APPROVED | 19 | 100% | FEDERADO-ANEXO
8 | CPQ11-ARCH-CHAI-SITE-R24.rvt | CPQ11-ARCH-CHAI-SITE-R22.rvt | SITE | S-VALE | 1104 | SPBIM | 1127 | V12 | 06/04/2026 | V1 | 15/05/2026 | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A
16 | CPQ11-ARCH-STON-SITE-R24.rvt | CPQ11-ARCH-STON-SITE-R23.rvt | SITE | STONE | 0000 | STONE | 0000 | V10 | 11/05/2026 | V3 | 09/06/2026 | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
20 | CPQ11-EPMS-DEVS-SITE-R24.rvt | CPQ11-EPMS-DEVS-SITE-R22.rvt | SITE | BLACKBOX | 1114 | BLACKBOX | 1114 | V11 | 03/02/2026 | V1 | 15/05/2026 | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A
26 | CPQ11-BASM-INFR-PUMP-R24.rvt | CPQ11-BASM-INFR-PUMP-R22.rvt | PUMP | MENDES HOLLER | 1112 | PGMAK | 1129 | V32 | 24/04/2026 | V3 | 03/07/2026 | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A
28 | CPQ11-BASM-DEVS-PUMP-R24.rvt | CPQ11-BASM-DEVS-PUMP-R22.rvt | PUMP | BLACKBOX | 1114 | BLACKBOX | 1114 | V14 | 03/02/2026 | V1 | 15/05/2026 | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A
37 | CPQ11-ELEC-SPDA-SITE-R24.rvt | CPQ11-ELEC-SPDA-SITE-R22.rvt | SITE | MENDES HOLLER | 1112 | MENDES HOLLER | 1112 | V7 | 08/12/2025 | V2 | 03/07/2026 | N/A | N/A | N/A |  | N/A | N/A | N/A | NÃO FOI POSSIVEL AUDITAR | 2025-01-07 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A
42 | CPQ11-FPRT-METK-UTLS-R24.rvt | CPQ11-FPRT-METK-UTLS-R22.rvt | UTLS | PETROTANQUE | 1117 | CADBIM | 1128 | V16 | 06/03/2026 | V5 | 08/07/2026 | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A
45 | CPQ11-PLMB-DIES-SITE-R24.rvt | CPQ11-PLMB-DIES-SITE-R22.rvt | SITE | MENDES HOLLER | 1112 | MENDES HOLLER | 1112 | V14 | 03/03/2026 | V4 | 13/07/2026 | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A
17 | SYST-SYSTEMS ¦ INFRASTRUCTURE
46 | CPQ11-PLMB-NPWT-SITE-R24.rvt | CPQ11-PLMB-NPWT-SITE-R22.rvt | SITE | STARCENTER | 1118 | STARCENTER | 1118 | V46 | 24/04/2026 | V2 | 15/06/2026 | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A
19 | EPMS-ELECTRICAL POWER MAN/AGEMENT SYSTEM ¦ DEVICES
47 | CPQ11-PLMB-METK-UTLS-R24.rvt | CPQ11-PLMB-METK-UTLS-R22.rvt | UTLS | STARCENTER | 1118 | STARCENTER | 1118 | V28 | 26/02/2026 | V1 | 19/05/2026 | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A
21 | ROIP-RADIO OVER IP ¦ DEVICES
53 | CPQ11-CIVL-DRNG-SITE-R24.rvt | CPQ11-CIVL-DRNG-SITE-R22.rvt | SITE | GARCIA | 1119 | CADBIM | 1128 | V20 | 06/05/2026 | V4 | 11/06/2026 | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A
23 | TELECOM ¦ DEVICES
55 | CPQ11-CIVL-PAVM-SITE-R24.rvt | CPQ11-CIVL-PAVM-SITE-R22.rvt | SITE | GARCIA | 1119 | CADBIM | 1128 | V18 | 30/04/2026 | V2 | 20/05/2026 | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A
25 | BAS-BUILDING AUTOMATION SYSTEM ¦ INFRASTRUCTURE
57 | CPQ11-CIVL-LOCK-SITE-R24.rvt | CPQ11-CIVL-LOCK-SITE-R22.rvt | SITE | STEINER | 0000 | PMD | 0000 | V11 | 21/03/2026 | V1 | 18/05/2026 | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A
27 | BAS ¦ DEVICES
64 | CPQ11-STRC-STEE-UTLS-2X3.ifc | CPQ11-STRC-STEE-UTLS-2X3.ifc | UTLS | METASA | 1125 | METASA | 1125 | V6 | 11/02/2026 | V1 | 21/05/2026 | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A
29 | SCTY-SECURITY ¦ INFRASTRUCTURE
66 | CPQ11-STRC-STEE-STIR-2X3.ifc | CPQ11-STRC-STEE-STIR-2X3.ifc | STIR | METASA | 1125 | METASA | 1125 | V3 | 31/10/2025 | V1 | 21/05/2026 | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A
31 | SCTY ¦ DEVICES
5 | CPQ11-ARCH-FENC-SITE-R24.rvt | CPQ11-ARCH-FENC-SITE-R22.rvt | SITE | SERCOP | 1103 | ARE ARQUITETURA | 1130 | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED
34 | ELEC-ELETRICAL
10 | CPQ11-ARCH-WTRP-SITE-R24.rvt | CPQ11-ARCH-WTRP-SITE-R22.rvt | SITE | ITS | 1107 | RBV | 0000 | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED
36 | SPDA ¦ PROTECTION SYSTEM ATMOSPHERIC DISCHARGE
13 | CPQ11-ARCH-SGNV-SITE-R24.rvt | CPQ11-ARCH-SGNV-SITE-R22.rvt | SITE | VISUAL GEAC | 0000 | CONTRACTING | 0000 | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED
38 | FALM-FIRE ALARM
14 | CPQ11-ARCH-SGNH-SITE-R24.rvt | CPQ11-ARCH-SGNH-SITE-R22.rvt | SITE | CONTRACTING | 0000 | CONTRACTING | 0000 | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED
40 | FPRT-FIRE PROTECTION
51 | CPQ11-LAND-LAND-SITE-R24.rvt | CPQ11-LAND-LAND-SITE-R22.rvt | SITE | ORGANISMO VIVO | 0000 | CONTRACTING | 0000 | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED
56 | CPQ11-CIVL-SIGN-SITE-R24.rvt | CPQ11-CIVL-SIGN-SITE-R22.rvt | SITE | CONTRACTING | 0000 | CONTRACTING | 0000 | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED
43 | PLMB-PLUMBING
62 | CPQ11-STRC-CHAI-SITE-R24.rvt | CPQ11-STRC-CHAI-SITE-R22.rvt | SITE | S-VALE | 1104 | SPBIM | 1127 | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED
63 | CPQ11-STRC-FENC-SITE-R24.rvt | CPQ11-STRC-FENC-SITE-R22.rvt | SITE | SERCOP, SERV OBRAS | 1124 | CONTRACTING | 0000 | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED
41 | CPQ11-FPRT-FPRT-SITE-R24.rvt | CPQ11-FPRT-FPRT-SITE-R22.rvt | SITE | MENDES HOLLER | 1112 | MENDES HOLLER | 1112 | V16 | 14/05/2026 | V4 | 13/07/2026 | V3 | 2026-06-24 | R24 | ALINNE | NEXT ROUND |  | NEXT ROUND | NÃO FOI POSSIVEL AUDITAR | 2025-01-07 | REPROVED | 6 | 1% | 39 | OUTDATED |  | OUTDATED | 39 | NEXT ROUND |  | NEXT ROUND | 39 | IMPROPER | 0 | IMPROPER | 39 | OUTDATED | 0 | OUTDATED | 39 | NEXT ROUND | 0 | NEXT ROUND | 39 | NEXT ROUND | 0 | NEXT ROUND | 39 | NEXT ROUND | 0 | NEXT ROUND | 39 | NEXT ROUND | 0 | NEXT ROUND | 39 | NEXT ROUND | 0 | NEXT ROUND | 39 | NEXT ROUND | 0 | NEXT ROUND | 39 | IMPROPER | 0 | IMPROPER | 39 | OUTDATED | 0 | OUTDATED | 39 | NEXT ROUND | 0 | NEXT ROUND | 39 | NEXT ROUND | 0 | NEXT ROUND | 39 | NEXT ROUND | 0 | NEXT ROUND | 39 | NEXT ROUND | 0 | NEXT ROUND | 39 | NEXT ROUND | 0 | NEXT ROUND | 39 | IMPROPER | 0 | IMPROPER | 39 | OUTDATED | 0 | OUTDATED | 39 | NEXT ROUND | 0 | NEXT ROUND | 39 | NEXT ROUND | 0 | NEXT ROUND | 39 | IMPROPER | 0 | IMPROPER | 39 | OUTDATED | 0 | OUTDATED | 39 | NEXT ROUND | 0 | NEXT ROUND | 39
2 | CPQ11-ARCH-ARCH-SITE-R24.rvt | CPQ11-ARCH-ARCH-SITE-R22.rvt | SITE | ARE ARQUITETURA | 1130 | ARE ARQUITETURA | 1130 | V28 | 17/04/2026 | V4 | 15/07/2026 | V3 | 03/06/2026 | R24 | FLAVIO | NEXT ROUND |  | NEXT ROUND | NÃO FOI POSSIVEL AUDITAR | 2025-01-07 | REPROVED | 8 | 1% | 13, 21, 39 | OUTDATED | 8 | OUTDATED | 13, 21, 39 | REPROVED | 0 | 1% | 13, 21, 39 | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | REPROVED | 1 | 11% | 39 | OUTDATED | 1 | OUTDATED | 39 | OUTDATED | 1 | OUTDATED | 39 | NEXT ROUND | 1 | NEXT ROUND | 39 | NEXT ROUND | 1 | NEXT ROUND | 39 | REPROVED | 1 | 60% | 39 | OUTDATED | 1 | OUTDATED | 39 | OUTDATED | 1 | OUTDATED | 39 | OUTDATED | 1 | OUTDATED | 39 | NEXT ROUND | 1 | NEXT ROUND | 39 | NEXT ROUND | 1 | NEXT ROUND | 39 | IMPROPER | 1 | IMPROPER | 39 | IMPROPER | 1 | IMPROPER | 39 | OUTDATED | 1 | OUTDATED | 39 | OUTDATED | 1 | OUTDATED | 39 | OUTDATED | 1 | OUTDATED | 39 | OUTDATED | 1 | OUTDATED | 39 | NEXT ROUND | 1 | NEXT ROUND | 39
48 | MECH-MECHANICAL
15 | CPQ11-ARCH-CEIL-SITE-R24.rvt | CPQ11-ARCH-CEIL-SITE-R22.rvt | SITE | IDEIA DRYWALL | 1101 | T2B | 0000 | V2 | 29/04/2026 | V1 | 12/06/2026 | V1 | 2026-06-12 | R24 |  | REPROVED | 1 | 1% | 21 | 2025-01-07 | OUTDATED | 1 | OUTDATED | 21 | OUTDATED | 1 | OUTDATED | 21 | OUTDATED | 1 | OUTDATED | 21 | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | IMPROPER |  | IMPROPER |  | IMPROPER |  | IMPROPER |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED
50 | LAND-LANDSCAPE
11 | CPQ11-ARCH-BLPR-GUAR-R24.rvt | CPQ11-ARCH-BLPR-GUAR-R22.rvt | GUAR | INOVAGLASS | 1109 | INOVAGLASS | 1109 | V9 | 04/12/2025 | V1 | 20/05/2026 | V1 | 2026-05-20 | R24 |  | REPROVED | 3 | 1% | 1, 13, 21, 22. | 2025-01-07 | OUTDATED | 3 | OUTDATED | 13, 21, 22. | OUTDATED | 3 | OUTDATED | 13, 21, 22. | OUTDATED | 3 | OUTDATED | 13, 21, 22. | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | IMPROPER |  | IMPROPER |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED
52 | CIVIL
35 | CPQ11-ELEC-ELEC-SITE-R24.rvt | CPQ11-ELEC-ELEC-SITE-R22.rvt | SITE | MENDES HOLLER | 1112 | PGMAK | 1129 | V33 | 05/03/2026 | V1 | 19/05/2026 | V1 | 2026-05-19 | R24 |  | NEXT ROUND |  | NEXT ROUND | NÃO FOI POSSIVEL AUDITAR | 2025-01-07 | REPROVED | 44 | 1% | 39 | OUTDATED | 44 | OUTDATED | 39 | OUTDATED | 44 | OUTDATED | 39 | IMPROPER | 0 | IMPROPER | 39 | NEXT ROUND | 0 | NEXT ROUND | 39 | NEXT ROUND | 0 | NEXT ROUND | 39 | NEXT ROUND | 0 | NEXT ROUND | 39 | NEXT ROUND | 0 | NEXT ROUND | 39 | NEXT ROUND | 0 | NEXT ROUND | 39 | NEXT ROUND | 0 | NEXT ROUND | 39 | NEXT ROUND | 0 | NEXT ROUND | 39 | NEXT ROUND | 0 | NEXT ROUND | 39 | NEXT ROUND | 0 | NEXT ROUND | 39 | NEXT ROUND | 0 | NEXT ROUND | 39 | NEXT ROUND | 0 | NEXT ROUND | 39 | NEXT ROUND | 0 | NEXT ROUND | 39 | NEXT ROUND | 0 | NEXT ROUND | 39 | NEXT ROUND | 0 | NEXT ROUND | 39 | REPROVED | 0 | 1% | DRONE 26.01.2026 e 39 | OUTDATED | 0 | OUTDATED | DRONE 26.01.2026 e 39 | OUTDATED | 0 | OUTDATED | DRONE 26.01.2026 e 39 | OUTDATED | 0 | OUTDATED | DRONE 26.01.2026 e 39 | OUTDATED | 0 | OUTDATED | DRONE 26.01.2026 e 39 | OUTDATED | 0 | OUTDATED | DRONE 26.01.2026 e 39 | OUTDATED | 0 | OUTDATED | DRONE 26.01.2026 e 39
61 | CPQ11-STRC-FLOO-SITE-R24.rvt | CPQ11-STRC-FLOO-SITE-R22.rvt | SITE | MODAX | 1121 | MODAX | 1121 | V1 | 05/05/2026 | V2 | 26/05/2026 | V2 | 2026-05-26 | R24 |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NEXT ROUND |  | 0% |  | NEXT ROUND |  | 0% |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | REPROVED |  | 1% |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED
44 | CPQ11-PLMB-PLMB-SITE-R24.rvt | CPQ11-PLMB-PLMB-SITE-R22.rvt | SITE | MENDES HOLLER | 1112 | PGMAK | 1129 | V27 | 08/04/2026 | V2 | 23/06/2026 | V2 | 2026-06-23 | R24 | CAROL | NEXT ROUND |  | NEXT ROUND | NÃO FOI POSSIVEL AUDITAR | 2025-01-07 | REPROVED |  | 1% | 21 | OUTDATED |  | OUTDATED | 39 | OUTDATED |  | OUTDATED | 39 | IMPROPER | 0 | IMPROPER | 39 | OUTDATED | 0 | OUTDATED | 39 | OUTDATED | 0 | OUTDATED | 39 | NEXT ROUND | 0 | NEXT ROUND | 39 | NEXT ROUND | 0 | NEXT ROUND | 39 | NEXT ROUND | 0 | NEXT ROUND | 39 | NEXT ROUND | 0 | NEXT ROUND | 39 | IMPROPER |  | IMPROPER |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | IMPROPER |  | IMPROPER |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | NEXT ROUND |  | NEXT ROUND |  | REPROVED |  | 1% | FEDERADO - ANEXO | OUTDATED |  | OUTDATED | FEDERADO - ANEXO | OUTDATED |  | OUTDATED | FEDERADO - ANEXO
6 | CPQ11-ARCH-METL-SITE-R24.rvt | CPQ11-ARCH-METL-SITE-R22.rvt | SITE | SERCOP | 1103 | ARE ARQUITETURA | 1130 | V12 | 05/05/2026 | V5 | 22/06/2026 | V5 | 2026-06-22 | R24 | LUIZA | REPROVED | 2 | 1% | 21 | DONE | NEXT ROUND | 2 | NEXT ROUND | 21 | REPROVED | 10 | 1% | 13, 21, 39 | OUTDATED | 10 | OUTDATED | 13, 21, 39 | OUTDATED |  | OUTDATED |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | REPROVED | 3 | 31% | 39 | NEXT ROUND |  | NEXT ROUND | 39 | REPROVED | 0 | 30% | 39 | NEXT ROUND | 0 | NEXT ROUND | 39 | REPROVED | 9 | 90% | 39 e DRONE 26.01.2026 | NEXT ROUND | 9 | NEXT ROUND | 39 e DRONE 26.01.2026 | NEXT ROUND | 9 | NEXT ROUND | 39 e DRONE 26.01.2026 | REPROVED | 9 | 90% | 39 e DRONE 26.01.2026 | NEXT ROUND | 9 | NEXT ROUND | 39 e DRONE 26.01.2026 | NEXT ROUND | 9 | NEXT ROUND | 39 e DRONE 26.01.2026 | NEXT ROUND | 9 | NEXT ROUND | 39 e DRONE 26.01.2026 | IMPROPER | 9 | IMPROPER | 39 e DRONE 26.01.2026 | IMPROPER | 9 | IMPROPER | 39 e DRONE 26.01.2026 | REPROVED | 9 | 90% | 39 e DRONE 26.01.2026 | NEXT ROUND | 9 | NEXT ROUND | 39 e DRONE 26.01.2026 | NEXT ROUND | 9 | NEXT ROUND | 39 e DRONE 26.01.2026 | APPROVED | 10 | 100% | DRONE MAIO-2026 | PREVIOUSLY APPROVED | 10 | 100% | DRONE MAIO-2026
3 | CPQ11-ARCH-HMET-SITE-R24.rvt | CPQ11-ARCH-HMET-SITE-R22.rvt | SITE | S-VALE | 1104 | SPBIM | 1127 | V9 | 10/04/2026 | V1 | 15/05/2026 | V7 | 2026-03-17 | R22 |  | NEXT ROUND |  | NEXT ROUND | NÃO FOI POSSIVEL AUDITAR | 2025-01-07 | REPROVED | 1 | 1% | 39 | OUTDATED | 1 | OUTDATED | 39 | OUTDATED | 1 | OUTDATED | 39 | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100%
58 | STRC-STRUCTURE
22 | CPQ11-ROIP-DEVS-GUAR-R24.rvt | CPQ11-ROIP-DEVS-GUAR-R22.rvt | GUAR | IB TECH | 1113 | IB TECH | 1113 | V12 | 13/05/2026 | V2 | 01/06/2026 | V2 | 2026-06-01 | R24 | YASMIN | NEXT ROUND |  | NEXT ROUND | NÃO FOI POSSIVEL AUDITAR | 2025-01-07 | REPROVED | 3 | 1% | 39 | OUTDATED | 3 | OUTDATED | 39 | OUTDATED | 3 | OUTDATED | 39 | OUTDATED |  | OUTDATED |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | REPROVED | 0 | 1% | 39 | OUTDATED | 0 | OUTDATED | 39 | NEXT ROUND | 0 | NEXT ROUND | 39 | NEXT ROUND | 0 | NEXT ROUND | 39 | REPROVED | 0 | 1% | 39 | OUTDATED | 0 | OUTDATED | 39 | OUTDATED | 0 | OUTDATED | 39 | OUTDATED | 0 | OUTDATED | 39 | NEXT ROUND | 0 | NEXT ROUND | 39 | REPROVED | 1 | 33% | 39 | OUTDATED | 1 | OUTDATED | 39 | APPROVED | 3 | 100% | 39 | PREVIOUSLY APPROVED | 3 | 100% | 39 | PREVIOUSLY APPROVED | 3 | 100% | 39 | PREVIOUSLY APPROVED | 3 | 100% | 39 | PREVIOUSLY APPROVED | 3 | 100% | 39 | PREVIOUSLY APPROVED | 3 | 100% | 39 | PREVIOUSLY APPROVED | 3 | 100% | 39
24 | CPQ11-TCOM-DEVS-SITE-R24.rvt | CPQ11-TCOM-DEVS-SITE-R22.rvt | SITE | BLACKBOX | 1114 | BLACKBOX | 1114 | V14 | 29/04/2026 | V2 | 07/07/2026 | V13 | 2026-03-25 | R22 | CAROL | NEXT ROUND |  | NEXT ROUND | NÃO FOI POSSIVEL AUDITAR | 2025-01-07 | REPROVED | 5 | 1% | 39 | OUTDATED | 5 | OUTDATED | 39 | OUTDATED | 5 | OUTDATED | 39 | REPROVED | 5 | 62.5% | 39 | OUTDATED | 5 | OUTDATED | 39 | OUTDATED | 5 | OUTDATED | 39 | OUTDATED | 5 | OUTDATED | 39 | OUTDATED | 5 | OUTDATED | 39 | NEXT ROUND | 5 | NEXT ROUND | 39 | APPROVED | 3 | 100% | 39 | PREVIOUSLY APPROVED | 3 | 100% | 39 | PREVIOUSLY APPROVED | 3 | 100% | 39 | PREVIOUSLY APPROVED | 3 | 100% | 39 | PREVIOUSLY APPROVED | 3 | 100% | 39 | PREVIOUSLY APPROVED | 3 | 100% | 39 | PREVIOUSLY APPROVED | 3 | 100% | 39 | PREVIOUSLY APPROVED | 3 | 100% | 39 | PREVIOUSLY APPROVED | 3 | 100% | 39 | PREVIOUSLY APPROVED | 3 | 100% | 39 | PREVIOUSLY APPROVED | 3 | 100% | 39 | PREVIOUSLY APPROVED | 3 | 100% | 39 | PREVIOUSLY APPROVED | 3 | 100% | 39 | PREVIOUSLY APPROVED | 3 | 100% | 39 | PREVIOUSLY APPROVED | 3 | 100% | 39 | PREVIOUSLY APPROVED | 3 | 100% | 39
32 | CPQ11-SCTY-DEVS-SITE-R24.rvt | CPQ11-SCTY-DEVS-SITE-R22.rvt | SITE | SEGURPRO | 1115 | SEGURPRO | 1115 | V37 | 10/04/2026 | V1 | 20/05/2026 | V37 | 10/04/2026 | R22 | CAROL | NEXT ROUND |  | NEXT ROUND | NÃO FOI POSSIVEL AUDITAR | 2025-01-07 | REPROVED | 9 | 1% | 39 | OUTDATED | 9 | OUTDATED | 39 | NEXT ROUND | 9 | NEXT ROUND | 39 | REPROVED | 1 | 11.11% | 39 | NEXT ROUND | 1 | NEXT ROUND | 39 | NEXT ROUND | 1 | NEXT ROUND | 39 | NEXT ROUND | 1 | NEXT ROUND | 39 | REPROVED | 4 | 44% | 39 | NEXT ROUND |  | NEXT ROUND | 39 | REPROVED | 2 | 77.7% | 39 | NEXT ROUND | 2 | NEXT ROUND | 39 | APPROVED | 9 | 100% | 39 | PREVIOUSLY APPROVED | 9 | 100% | 39 | PREVIOUSLY APPROVED | 9 | 100% | 39 | PREVIOUSLY APPROVED | 9 | 100% | 39 | PREVIOUSLY APPROVED | 9 | 100% | 39 | PREVIOUSLY APPROVED | 9 | 100% | 39 | PREVIOUSLY APPROVED | 9 | 100% | 39 | PREVIOUSLY APPROVED | 9 | 100% | 39 | PREVIOUSLY APPROVED | 9 | 100% | 39 | PREVIOUSLY APPROVED | 9 | 100% | 39 | PREVIOUSLY APPROVED | 9 | 100% | 39 | PREVIOUSLY APPROVED | 9 | 100% | 39 | PREVIOUSLY APPROVED | 9 | 100% | 39 | PREVIOUSLY APPROVED | 9 | 100% | 39
49 | CPQ11-MECH-MECH-GUAR-R24.rvt | CPQ11-MECH-MECH-GUAR-R22.rvt | GUAR | STARCENTER | 1118 | STARCENTER | 1118 | V23 | 16/04/2026 | V1 | 19/05/2026 | V23 | 2026-04-16 | R22 | CAROL | NEXT ROUND |  | NEXT ROUND | NÃO FOI POSSIVEL AUDITAR | 2025-01-07 | REPROVED | 7 | 1% | 39 | OUTDATED | 7 | OUTDATED | 39 | OUTDATED | 7 | OUTDATED | 39 | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | REPROVED | 1 | 14% | 39 | REPROVED | 3 | 42% | 39 | NEXT ROUND | 3 | NEXT ROUND | 39 | REPROVED | 3 | 42% | 39 | REPROVED | 6 | 86% | 39 | APPROVED | 1 | 100% | 39 | PREVIOUSLY APPROVED | 1 | 100% | 39 | PREVIOUSLY APPROVED | 1 | 100% | 39 | PREVIOUSLY APPROVED | 1 | 100% | 39 | PREVIOUSLY APPROVED | 1 | 100% | 39 | PREVIOUSLY APPROVED | 1 | 100% | 39 | PREVIOUSLY APPROVED | 1 | 100% | 39 | PREVIOUSLY APPROVED | 1 | 100% | 39 | PREVIOUSLY APPROVED | 1 | 100% | 39 | PREVIOUSLY APPROVED | 1 | 100% | 39 | PREVIOUSLY APPROVED | 1 | 100% | 39 | PREVIOUSLY APPROVED | 1 | 100% | 39 | PREVIOUSLY APPROVED | 1 | 100% | 39
54 | CPQ11-CIVL-ERTH-SITE-R24.rvt | CPQ11-CIVL-ERTH-SITE-R22.rvt | SITE | GARCIA | 1119 | CADBIM | 1128 | V18 | 08/04/2026 | V6 | 24/06/2026 | V2 | 2026-05-20 | R24 | CAROL | NOT PUBLISHED | 3 | NOT PUBLISHED |  | NOT PUBLISHED | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NEXT ROUND |  | NEXT ROUND |  | REPROVED | 0 | 1% | DRONE 30.01.26 | NEXT ROUND | 0 | NEXT ROUND | DRONE 30.01.26 | NEXT ROUND | 0 | NEXT ROUND | DRONE 30.01.26 | REPROVED | 0 | 1% | DRONE 30.01.26 | REPROVED | 0 | 1% | DRONE 26.01.26 | REPROVED | 0 | 1% | DRONE 26.01.26 | NEXT ROUND | 0 | NEXT ROUND | DRONE 26.01.26 | NEXT ROUND | 0 | NEXT ROUND | DRONE 26.01.26 | NEXT ROUND | 0 | NEXT ROUND | DRONE 26.01.26 | REPROVED | 0 | 1% | DRONE 26.01.26 | OUTDATED | 0 | OUTDATED | DRONE 26.01.26 | OUTDATED | 0 | OUTDATED | DRONE 26.01.26 | NEXT ROUND | 0 | NEXT ROUND | DRONE 26.01.26 | NEXT ROUND | 0 | NEXT ROUND | DRONE 26.01.26 | APPROVED | 3 | 100% | DRONE 26.01.26 | PREVIOUSLY APPROVED | 3 | 100% | DRONE 26.01.26 | PREVIOUSLY APPROVED | 3 | 100% | DRONE 26.01.26 | PREVIOUSLY APPROVED | 3 | 100% | DRONE 26.01.26 | PREVIOUSLY APPROVED | 3 | 100% | DRONE 26.01.26 | PREVIOUSLY APPROVED | 3 | 100% | DRONE 26.01.26 | PREVIOUSLY APPROVED | 3 | 100% | DRONE 26.01.26
59 | CPQ11-STRC-CONC-SITE-R24.rvt | CPQ11-STRC-CONC-SITE-R22.rvt | SITE | SERV OBRAS | 1120 | TENAX | 0000 | V17 | 12/05/2026 | V1 | 15/05/2026 | V14 | 2026-03-13 | R22 | LUIZA | NEXT ROUND |  | NEXT ROUND | NÃO FOI POSSIVEL AUDITAR | 2025-01-07 | APPROVED |  | 100% | 13, 39 | PREVIOUSLY APPROVED |  | 100% | 13, 39 | PREVIOUSLY APPROVED |  | 100% | 13, 39 | REPROVED | 10 | 1% | 21 | NEXT ROUND | 10 | NEXT ROUND | 21 | NEXT ROUND | 10 | NEXT ROUND | 21 | NEXT ROUND | 10 | NEXT ROUND | 21 | APPROVED | 10 | 100% | 39 | PREVIOUSLY APPROVED | 10 | 100% | 39 | PREVIOUSLY APPROVED | 10 | 100% | 39 | PREVIOUSLY APPROVED | 10 | 100% | 39 | PREVIOUSLY APPROVED | 10 | 100% | 39 | PREVIOUSLY APPROVED | 10 | 100% | 39 | PREVIOUSLY APPROVED | 10 | 100% | 39 | PREVIOUSLY APPROVED | 10 | 100% | 39 | PREVIOUSLY APPROVED | 10 | 100% | 39 | PREVIOUSLY APPROVED | 10 | 100% | 39 | PREVIOUSLY APPROVED | 10 | 100% | 39 | PREVIOUSLY APPROVED | 10 | 100% | 39 | PREVIOUSLY APPROVED | 10 | 100% | 39 | PREVIOUSLY APPROVED | 10 | 100% | 39 | PREVIOUSLY APPROVED | 10 | 100% | 39 | PREVIOUSLY APPROVED | 10 | 100% | 39 | PREVIOUSLY APPROVED | 10 | 100% | 39 | PREVIOUSLY APPROVED | 10 | 100% | 39
60 | CPQ11-STRC-DPFN-SITE-R24.rvt | CPQ11-STRC-DPFN-SITE-R22.rvt | SITE | GEOFIX/TECNOGEO | 0000 | TENAX | 0000 | V13 | 12/05/2026 | V1 | 15/05/2026 | V7 | 2025-12-10 | R22 |  | APPROVED | 0 | 100% | 13.21 | 2025-01-07 | PREVIOUSLY APPROVED |  | 100% | 13.21 | PREVIOUSLY APPROVED |  | 100% | 13.21 | PREVIOUSLY APPROVED |  | 100% | 13.21 | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100%
65 | CPQ11-STRC-STEE-GUAR-2X3.ifc | CPQ11-STRC-STEE-GUAR-2X3.ifc | GUAR | METASA | 1125 | METASA | 1125 | V6 | 01/11/2025 | V1 | 21/05/2026 | V6 | 01/11/2025 | R22 |  | APPROVED | 0 | 100% | 13, 21 | 2025-01-07 | PREVIOUSLY APPROVED |  | 100% | 13, 21 | PREVIOUSLY APPROVED |  | 100% | 13, 21 | PREVIOUSLY APPROVED |  | 100% | 13, 21 | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100%
30 | CPQ11-SCTY-INFR-SITE-R24.rvt | CPQ11-SCTY-INFR-SITE-R22.rvt | SITE | MENDES HOLLER | 1112 | PGMAK | 1129 | V34 | 05/05/2026 | V3 | 03/07/2026 | V3 | 2026-07-03 | R24 | INGRYD | NEXT ROUND | 15 | NEXT ROUND | NÃO FOI POSSIVEL AUDITAR | 2025-01-07 | REPROVED | 15 | 1% | 39 | IMPROPER | 0 | IMPROPER |  | IMPROPER | 0 | IMPROPER |  | IMPROPER | 0 | IMPROPER | 39 | NEXT ROUND | 0 | NEXT ROUND | 39 | NEXT ROUND | 0 | NEXT ROUND | 39 | NEXT ROUND | 0 | NEXT ROUND | 39 | NEXT ROUND | 0 | NEXT ROUND | 39 | NEXT ROUND | 0 | NEXT ROUND | 39 | NEXT ROUND | 0 | NEXT ROUND | 39 | NEXT ROUND | 0 | NEXT ROUND | 39 | REPROVED | 0 | 1% | 39 | NEXT ROUND | 0 | NEXT ROUND | 39 | NEXT ROUND | 0 | NEXT ROUND | 39 | REPROVED | 6 | 40% | 39 | NEXT ROUND | 6 | NEXT ROUND | 39 | REPROVED | 6 | 40% | 39 | NEXT ROUND | 6 | NEXT ROUND | 39 | ANALYSING | 6 | ANALYSING | 39 | REPROVED | 6 | 40% | 39 | OUTDATED | 6 | OUTDATED | 39 | OUTDATED | 6 | OUTDATED | 39 | NEXT ROUND | 6 | NEXT ROUND | 39 | NEXT ROUND | 6 | NEXT ROUND | 39 | REPROVED | 7 | 47% | FEDERADO-ANEXO
Note on AI62: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: NUMERO DE NOVAS LÂMPADAS ADICIONADAS, NENHUMA RESOLVIDA

## LOD 500 - UTLS
LOD 500 ¦ UTLS
| FILE NAME (R24) | FILE NAME (R22) | AREA | TRADE COMPANY | CODE | BIM COMPANY | CODE | ACC VERSION (R22) | ACC FILE DATE (R22) | ACC VERSION (R24) | ACC FILE DATE (R24) | VERSION | FILE DATE | RVT TYPE APROVAL (UTLS) | RESPONSAVEL | R0 - AUDIT STATUS | LAMPS QTDE | R0 - APPROVAL (%) | ESTIMATED DELIVERY R0 | R1 - AUDIT STATUS | LAMPS QTDE RESOLVIDAS | R1 - APPROVAL (%) | ESTIMATED DELIVERY R1 | R2 - AUDIT STATUS | R2 LAMPS QTDE RESOLVIDAS | R2 - APPROVAL (%) | NUVEM UTILIZADA | R3 - AUDIT STATUS | R3 LAMPS QTDE RESOLVIDAS | R3 - APPROVAL (%) | NUVEM UTILIZADA | R4 - AUDIT STATUS | R4 LAMPS QTDE RESOLVIDAS | R4 - APPROVAL (%) | NUVEM UTILIZADA | R5 - AUDIT STATUS | R5 LAMPS QTDE RESOLVIDAS | R5 - APPROVAL (%) | R5 - NUVEM UTILIZADA | R6 - AUDIT STATUS | R6 LAMPS QTDE RESOLVIDAS | R6 - APPROVAL (%) | R6- NUVEM UTILIZADA | R7 - AUDIT STATUS | R7 LAMPS QTDE RESOLVIDAS | R7 - APPROVAL (%) | R7- NUVEM UTILIZADA | R8 - AUDIT STATUS | R8 LAMPS QTDE RESOLVIDAS | R8 - APPROVAL (%) | R8- NUVEM UTILIZADA | R9 - AUDIT STATUS | R9 LAMPS QTDE RESOLVIDAS | R9 - APPROVAL (%) | R9- NUVEM UTILIZADA | R10 - AUDIT STATUS | R10 LAMPS QTDE RESOLVIDAS | R10 - APPROVAL (%) | R10- NUVEM UTILIZADA | R11 - AUDIT STATUS | R11 LAMPS QTDE RESOLVIDAS | R11 - APPROVAL (%) | R11- NUVEM UTILIZADA | R12 - AUDIT STATUS | R12 LAMPS QTDE RESOLVIDAS | R12 - APPROVAL (%) | R12- NUVEM UTILIZADA | R13 - AUDIT STATUS | R13 LAMPS QTDE RESOLVIDAS | R13 - APPROVAL (%) | R13- NUVEM UTILIZADA | R14 - AUDIT STATUS | R14 LAMPS QTDE RESOLVIDAS | R14 - APPROVAL (%) | R14- NUVEM UTILIZADA | R15 - AUDIT STATUS | R15 LAMPS QTDE RESOLVIDAS | R15 - APPROVAL (%) | R15- NUVEM UTILIZADA | R16 - AUDIT STATUS | R16 LAMPS QTDE RESOLVIDAS | R16 - APPROVAL (%) | R16- NUVEM UTILIZADA | R17 - AUDIT STATUS | R17 LAMPS QTDE RESOLVIDAS | R17 - APPROVAL (%) | R17- NUVEM UTILIZADA | R18 - AUDIT STATUS | R18 LAMPS QTDE RESOLVIDAS | R18 - APPROVAL (%) | R18- NUVEM UTILIZADA | R19 - AUDIT STATUS | R19 LAMPS QTDE RESOLVIDAS | R19 - APPROVAL (%) | R19- NUVEM UTILIZADA | R20 - AUDIT STATUS | R20 LAMPS QTDE RESOLVIDAS | R20 - APPROVAL (%) | R20- NUVEM UTILIZADA | R21 - AUDIT STATUS | R21 LAMPS QTDE RESOLVIDAS | R21 - APPROVAL (%) | R21- NUVEM UTILIZADA | R22 - AUDIT STATUS | R22 LAMPS QTDE RESOLVIDAS | R22 - APPROVAL (%) | R22 - NUVEM UTILIZADA | R23 - AUDIT STATUS | R23 LAMPS QTDE RESOLVIDAS | R23 - APPROVAL (%) | R23 - NUVEM UTILIZADA | R24 - AUDIT STATUS | R24 LAMPS QTDE RESOLVIDAS | R24 - APPROVAL (%) | R24 - NUVEM UTILIZADA | R25 - AUDIT STATUS | R25 LAMPS QTDE RESOLVIDAS | R25 - APPROVAL (%) | R25 - NUVEM UTILIZADA | R26 - AUDIT STATUS | R26 LAMPS QTDE RESOLVIDAS | R26 - APPROVAL (%) | R26 - NUVEM UTILIZADA | R27 - AUDIT STATUS | R27 LAMPS QTDE RESOLVIDAS | R27 - APPROVAL (%) | R27 - NUVEM UTILIZADA
8 | CPQ11-ARCH-CHAI-SITE-R24.rvt | CPQ11-ARCH-CHAI-SITE-R22.rvt | SITE | S-VALE | 1104 | SPBIM | 1127 | V12 | 06/04/2026 | V1 | 15/05/2026 | V10 | 23/12/2025 | R24 |  | REPROVED | 2 | 1% | DONE | IMPROPER | 0 | IMPROPER | DONE | REPROVED | 0 | 1% | 21 e 36 | OUTDATED | 0 | OUTDATED | 21 e 36 | OUTDATED | 0 | OUTDATED | 21 e 36 | OUTDATED | 0 | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | NEXT ROUND |  | NEXT ROUND | 36 | NEXT ROUND |  | NEXT ROUND | 36 | NEXT ROUND |  | NEXT ROUND | 36 | NEXT ROUND |  | NEXT ROUND | 36 | NEXT ROUND |  | NEXT ROUND | 36 | NEXT ROUND |  | NEXT ROUND | 36 | NEXT ROUND |  | NEXT ROUND | 36 | NEXT ROUND |  | NEXT ROUND | 36 | NEXT ROUND |  | NEXT ROUND | 36 | NEXT ROUND |  | NEXT ROUND | 36 | NEXT ROUND |  | NEXT ROUND | 36 | NEXT ROUND |  | NEXT ROUND | 36 | NEXT ROUND |  | NEXT ROUND | 36 | NEXT ROUND |  | NEXT ROUND | 36 | NEXT ROUND |  | NEXT ROUND | 36 | NEXT ROUND |  | NEXT ROUND | 36 | ANALYSING |  | ANALYSING | 36
30 | CPQ11-SCTY-INFR-SITE-R24.rvt | CPQ11-SCTY-INFR-SITE-R22.rvt | SITE | MENDES HOLLER | 1112 | PGMAK | 1129 | V34 | 05/05/2026 | V3 | 03/07/2026 | V2 | 2026-05-21 | R24 | FLAVIO | REPROVED | 10 | 1% | DONE | IMPROPER | 0 | IMPROPER | DONE | IMPROPER | 0 | IMPROPER |  | NEXT ROUND | 0 | NEXT ROUND |  | REPROVED | 1 | 11% | 21 e 36 | NEXT ROUND | 1 | NEXT ROUND |  | IMPROPER |  | IMPROPER |  | REPROVED | 2 | 20% | 25, 31, 36 | NEXT ROUND | 2 | NEXT ROUND | 25, 31, 36 | NEXT ROUND | 2 | NEXT ROUND | 25, 31, 36 | REPROVED | 2 | REPROVED | 25, 31, 36 | OUTDATED | 2 | OUTDATED | 25, 31, 36 | OUTDATED | 2 | OUTDATED | 25, 31, 36 | OUTDATED | 2 | OUTDATED | 25, 31, 36 | OUTDATED | 2 | OUTDATED | 25, 31, 36 | NEXT ROUND | 2 | NEXT ROUND | 25, 31, 36 | REPROVED | 4 | 40% | 25, 31, 36 | NEXT ROUND | 4 | NEXT ROUND | 25, 31, 36 | REPROVED | 6 | 50% | 36 | NEXT ROUND | 6 | NEXT ROUND | 36 | NEXT ROUND | 6 | NEXT ROUND | 36 | REPROVED | 7 | 70% | 36 | OUTDATED | 7 | OUTDATED | 36 | OUTDATED | 7 | OUTDATED | 36 | OUTDATED | 7 | OUTDATED | 36 | NEXT ROUND | 7 | NEXT ROUND | 36 | NEXT ROUND | 7 | NEXT ROUND | 36 | ANALYSING | 7 | ANALYSING | 36
38 | CPQ11-FALM-FALM-SITE-R24.rvt | CPQ11-FALM-FALM-SITE-R22.rvt | SITE | MENDES HOLLER | 1112 | MENDES HOLLER | 1112 | V11 | 08/05/2026 | V3 | 10/07/2026 | V2 | 2026-06-23 | R24 | N/A | APPROVED | 0 | 100% | DONE | PREVIOUSLY APPROVED | 0 | 100% | DONE | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | REPROVED |  | 1% | 36 | NEXT ROUND |  | NEXT ROUND | 36 | NEXT ROUND |  | NEXT ROUND | 36 | IMPROPER |  | IMPROPER | 36 | OUTDATED |  | OUTDATED | 36 | OUTDATED |  | OUTDATED | 36 | OUTDATED |  | OUTDATED | 36 | NEXT ROUND |  | NEXT ROUND | 36 | IMPROPER |  | IMPROPER | 36 | NEXT ROUND |  | NEXT ROUND | 36 | ANALYSING |  | ANALYSING | 36
18 | CPQ11-SYST-INFR-SITE-R24.rvt | CPQ11-SYST-INFR-SITE-R22.rvt | SITE | MENDES HOLLER | 1112 | PGMAK | 1129 | V39 | 12/05/2026 | V4 | 14/07/2026 | V46 | 2026-07-14 | R24 | YASMIN | REPROVED | 4 | 1% | DONE | IMPROPER | 0 | IMPROPER | DONE | IMPROPER | 0 | IMPROPER |  | IMPROPER | 0 | IMPROPER |  | OUTDATED | 0 | OUTDATED |  | NEXT ROUND | 0 | NEXT ROUND |  | IMPROPER |  | IMPROPER |  | NEXT ROUND |  | NEXT ROUND |  | REPROVED | 1 | 25% | 36 | NEXT ROUND | 1 | NEXT ROUND | 36 | REPROVED | 3 | 75% | 36 | OUTDATED | 3 | OUTDATED | 36 | OUTDATED | 3 | OUTDATED | 36 | OUTDATED | 3 | OUTDATED | 36 | OUTDATED | 3 | OUTDATED | 36 | OUTDATED | 3 | OUTDATED | 36 | OUTDATED | 3 | OUTDATED | 36 | OUTDATED | 3 | OUTDATED | 36 | NEXT ROUND | 3 | NEXT ROUND | 36 | REPROVED | 3 | 75% | 36 | OUTDATED | 3 | OUTDATED | 36 | OUTDATED | 3 | OUTDATED | 36 | OUTDATED | 3 | OUTDATED | 36 | OUTDATED | 3 | OUTDATED | 36 | NEXT ROUND | 3 | NEXT ROUND | 36 | REPROVED | 3 | 75% | FEDERADO - ANEXO | NEXT ROUND | 3 | NEXT ROUND | FEDERADO - ANEXO | APPROVED | 4 | 100% | FEDERADO - ANEXO
11 | CPQ11-ARCH-BLPR-GUAR-R24.rvt | CPQ11-ARCH-BLPR-GUAR-R22.rvt | GUAR | INOVAGLASS | 1109 | INOVAGLASS | 1109 | V9 | 04/12/2025 | V1 | 20/05/2026 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A
48 | CPQ11-MECH-MECH-GUAR-R24.rvt | CPQ11-MECH-MECH-GUAR-R22.rvt | GUAR | STARCENTER | 1118 | STARCENTER | 1118 | V23 | 16/04/2026 | V1 | 19/05/2026 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A
22 | CPQ11-ROIP-DEVS-GUAR-R24.rvt | CPQ11-ROIP-DEVS-GUAR-R22.rvt | GUAR | IB TECH | 1113 | IB TECH | 1113 | V12 | 13/05/2026 | V2 | 01/06/2026 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A
64 | CPQ11-STRC-STEE-GUAR-2X3.ifc | CPQ11-STRC-STEE-GUAR-2X3.ifc | GUAR | METASA | 1125 | METASA | 1125 | V6 | 01/11/2025 | V1 | 21/05/2026 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A
15 | CPQ11-ARCH-CEIL-SITE-R24.rvt | CPQ11-ARCH-CEIL-SITE-R22.rvt | SITE | IDEIA DRYWALL | 1101 | T2B | 0000 | V2 | 29/04/2026 | V1 | 12/06/2026 | N/A | N/A | N/A | N/A | NOT PUBLISHED | N/A | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | N/A | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A
16 | CPQ11-ARCH-STON-SITE-R24.rvt | CPQ11-ARCH-STON-SITE-R23.rvt | SITE | STONE | 0000 | STONE | 0000 | V10 | 11/05/2026 | V3 | 09/06/2026 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A
56 | CPQ11-CIVL-LOCK-SITE-R24.rvt | CPQ11-CIVL-LOCK-SITE-R22.rvt | SITE | STEINER | 0000 | PMD | 0000 | V11 | 21/03/2026 | V1 | 18/05/2026 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A
44 | CPQ11-PLMB-DIES-SITE-R24.rvt | CPQ11-PLMB-DIES-SITE-R22.rvt | SITE | MENDES HOLLER | 1112 | MENDES HOLLER | 1112 | V14 | 03/03/2026 | V4 | 13/07/2026 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A
| CPQ11-SCTY-GATE-SITE-R24.rvt | CPQ11-SCTY-GATE-SITE-R24.rvt | SITE | FM SECURITY | 0000 | FM SECURITY | 0000 | V2 | 07/05/2026 | V5 | 08/07/2026 | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A
24 | CPQ11-TCOM-DEVS-SITE-R24.rvt | CPQ11-TCOM-DEVS-SITE-R22.rvt | SITE | BLACKBOX | 1114 | BLACKBOX | 1114 | V14 | 29/04/2026 | V2 | 07/07/2026 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A
40 | CPQ11-FPRT-FPRT-SITE-R24.rvt | CPQ11-FPRT-FPRT-SITE-R22.rvt | SITE | MENDES HOLLER | 1112 | MENDES HOLLER | 1112 | V16 | 14/05/2026 | V4 | 13/07/2026 | V3 | 2026-06-24 | R24 |  | REPROVED | 4 | 1% | DONE | IMPROPER | 4 | IMPROPER | DONE | IMPROPER | 0 | IMPROPER |  | OUTDATED | 0 | OUTDATED |  | OUTDATED | 0 | OUTDATED |  | NEXT ROUND | 0 | NEXT ROUND |  | IMPROPER |  | IMPROPER |  | OUTDATED |  | OUTDATED |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | IMPROPER |  | IMPROPER |  | OUTDATED |  | OUTDATED |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | IMPROPER |  | IMPROPER |  | OUTDATED |  | OUTDATED |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | IMPROPER |  | IMPROPER |  | OUTDATED |  | OUTDATED |  | NEXT ROUND |  | NEXT ROUND
2 | CPQ11-ARCH-ARCH-SITE-R24.rvt | CPQ11-ARCH-ARCH-SITE-R22.rvt | SITE | ARE ARQUITETURA | 1130 | ARE ARQUITETURA | 1130 | V28 | 17/04/2026 | V4 | 15/07/2026 | V3 | 2026-06-03 | R24 | NICOLE | APPROVED | 0 | 100% | DONE | PREVIOUSLY APPROVED | 0 | 100% | DONE | PREVIOUSLY APPROVED | 0 | 100% |  | PREVIOUSLY APPROVED | 0 | 100% |  | PREVIOUSLY APPROVED | 0 | 100% |  | PREVIOUSLY APPROVED | 0 | 100% |  | REPROVED | 18 | 1% | VISITA 36 | REPROVED | 8 | 44% | VISITA 36 | NEXT ROUND | 8 | NEXT ROUND | VISITA 36 | NEXT ROUND | 8 | NEXT ROUND | VISITA 36 | REPROVED | 15 | 83% | VISITA 36 | OUTDATED | 15 | OUTDATED | VISITA 36 | OUTDATED | 15 | OUTDATED | VISITA 36 | NEXT ROUND | 15 | NEXT ROUND | VISITA 36 | NEXT ROUND | 15 | NEXT ROUND | VISITA 36 | NEXT ROUND | 15 | NEXT ROUND | VISITA 36 | NEXT ROUND | 15 | NEXT ROUND | VISITA 36 | NEXT ROUND | 15 | NEXT ROUND | VISITA 36 | NEXT ROUND | 15 | NEXT ROUND | VISITA 36 | NEXT ROUND | 15 | NEXT ROUND | VISITA 36 | NEXT ROUND | 15 | NEXT ROUND | VISITA 36 | REPROVED | 15 | 83% | VISITA 36 | IMPROPER | 15 | IMPROPER | VISITA 36 | OUTDATED | 15 | OUTDATED | VISITA 36 | OUTDATED | 15 | OUTDATED | VISITA 36 | OUTDATED | 15 | OUTDATED | VISITA 36 | OUTDATED | 15 | OUTDATED | VISITA 36 | NEXT ROUND | 15 | NEXT ROUND | VISITA 36
5 | CPQ11-ARCH-FENC-SITE-R24.rvt | CPQ11-ARCH-FENC-SITE-R22.rvt | SITE | SERCOP | 1103 | ARE ARQUITETURA | 1130 | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | N/A | NOT PUBLISHED | N/A | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | N/A | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | N/A | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | N/A | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | N/A | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED
9 | CPQ11-ARCH-NEWJ-SITE-R24.rvt | CPQ11-ARCH-NEWJ-SITE-R22.rvt | SITE | RACIONAL | 1106 | TENAX | 0000 | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | N/A | NOT PUBLISHED | N/A | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | N/A | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | N/A | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | N/A | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | N/A | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED
14 | CPQ11-ARCH-SGNH-SITE-R24.rvt | CPQ11-ARCH-SGNH-SITE-R22.rvt | SITE | CONTRACTING | 0000 | CONTRACTING | 0000 | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | N/A | NOT PUBLISHED | N/A | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | N/A | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | N/A | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | N/A | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | N/A | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED
13 | CPQ11-ARCH-SGNV-SITE-R24.rvt | CPQ11-ARCH-SGNV-SITE-R22.rvt | SITE | VISUAL GEAC | 0000 | CONTRACTING | 0000 | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | N/A | NOT PUBLISHED | N/A | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | N/A | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | N/A | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | N/A | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | N/A | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED
10 | CPQ11-ARCH-WTRP-SITE-R24.rvt | CPQ11-ARCH-WTRP-SITE-R22.rvt | SITE | ITS | 1107 | RBV | 0000 | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | N/A | NOT PUBLISHED | N/A | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | N/A | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | N/A | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | N/A | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | N/A | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED
55 | CPQ11-CIVL-SIGN-SITE-R24.rvt | CPQ11-CIVL-SIGN-SITE-R22.rvt | SITE | CONTRACTING | 0000 | CONTRACTING | 0000 | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | N/A | NOT PUBLISHED | N/A | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | N/A | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | N/A | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | N/A | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | N/A | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED
50 | CPQ11-LAND-LAND-SITE-R24.rvt | CPQ11-LAND-LAND-SITE-R22.rvt | SITE | ORGANISMO VIVO | 0000 | CONTRACTING | 0000 | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | N/A | NOT PUBLISHED | N/A | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | N/A | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | N/A | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | N/A | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | N/A | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED
61 | CPQ11-STRC-CHAI-SITE-R24.rvt | CPQ11-STRC-CHAI-SITE-R22.rvt | SITE | S-VALE | 1104 | SPBIM | 1127 | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | N/A | NOT PUBLISHED | N/A | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | N/A | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | N/A | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | N/A | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | N/A | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED
62 | CPQ11-STRC-FENC-SITE-R24.rvt | CPQ11-STRC-FENC-SITE-R22.rvt | SITE | SERCOP, SERV OBRAS | 1124 | CONTRACTING | 0000 | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | N/A | NOT PUBLISHED | N/A | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | N/A | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | N/A | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | N/A | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | N/A | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED
12 | CPQ11-ARCH-PART-SITE-R24.rvt | CPQ11-ARCH-PART-SITE-R22.rvt | SITE | IDEIA DRYWALL | 1101 | FCH | 1126 | V14 | 18/03/2026 | V2 | 17/06/2026 | V2 | 2026-06-17 | R24 | FLAVIO | REPROVED | 11 | 1% | DONE | IMPROPER | 0 | IMPROPER | DONE | IMPROPER | 0 | IMPROPER |  | OUTDATED | 0 | OUTDATED |  | OUTDATED | 0 | OUTDATED |  | OUTDATED | 0 | OUTDATED |  | REPROVED | 23 | 1% | VISITA 36 | OUTDATED | 23 | OUTDATED | VISITA 36 | OUTDATED | 23 | OUTDATED | VISITA 36 | OUTDATED | 23 | OUTDATED | VISITA 36 | NEXT ROUND | 23 | NEXT ROUND | VISITA 36 | REPROVED | 4 | 17% | VISITA 36 | OUTDATED | 4 | OUTDATED | VISITA 36 | OUTDATED | 4 | OUTDATED | VISITA 36 | OUTDATED | 4 | OUTDATED | VISITA 36 | OUTDATED | 4 | OUTDATED | VISITA 36 | OUTDATED | 4 | OUTDATED | VISITA 36 | OUTDATED | 4 | OUTDATED | VISITA 36 | OUTDATED | 4 | OUTDATED | VISITA 36 | IMPROPER | 4 | IMPROPER | VISITA 36 | OUTDATED | 4 | OUTDATED | VISITA 36 | OUTDATED | 4 | OUTDATED | VISITA 36 | OUTDATED | 4 | OUTDATED | VISITA 36 | NEXT ROUND | 4 | NEXT ROUND | VISITA 36 | IMPROPER |  | IMPROPER | VISITA 36 | OUTDATED |  | OUTDATED | VISITA 36 | OUTDATED |  | OUTDATED | VISITA 36 | OUTDATED |  | OUTDATED | VISITA 36
34 | CPQ11-ELEC-ELEC-SITE-R24.rvt | CPQ11-ELEC-ELEC-SITE-R22.rvt | SITE | MENDES HOLLER | 1112 | PGMAK | 1129 | V33 | 05/03/2026 | V1 | 19/05/2026 | V1 | 2026-05-19 | R24 |  | REPROVED | 19 | 1% | DONE | IMPROPER | 19 | IMPROPER | DONE | IMPROPER | 0 | IMPROPER |  | OUTDATED | 0 | OUTDATED |  | OUTDATED | 0 | OUTDATED |  | OUTDATED | 0 | OUTDATED |  | IMPROPER |  | IMPROPER |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | IMPROPER |  | IMPROPER |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED
60 | CPQ11-STRC-FLOO-SITE-R24.rvt | CPQ11-STRC-FLOO-SITE-R22.rvt | SITE | MODAX | 1121 | MODAX | 1121 | V1 | 05/05/2026 | V2 | 26/05/2026 | V2 | 26/05/2026 | R24 | N/A | NOT PUBLISHED | N/A | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | N/A | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | N/A | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | N/A | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | N/A | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | N/A | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NEXT ROUND |  | 0% |  | NEXT ROUND |  | 0% |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND | FEDERADO - UTLS | REPROVED |  | 1% | FEDERADO - UTLS | OUTDATED |  | OUTDATED | FEDERADO - UTLS | OUTDATED |  | OUTDATED | FEDERADO - UTLS | OUTDATED |  | OUTDATED | FEDERADO - UTLS
43 | CPQ11-PLMB-PLMB-SITE-R24.rvt | CPQ11-PLMB-PLMB-SITE-R22.rvt | SITE | MENDES HOLLER | 1112 | PGMAK | 1129 | V27 | 08/04/2026 | V2 | 23/06/2026 | V2 | 2026-06-23 | R24 | FLAVIO | REPROVED | 11 | 1% | DONE | IMPROPER | 0 | IMPROPER | DONE | IMPROPER | 0 | IMPROPER |  | IMPROPER | 0 | IMPROPER |  | OUTDATED | 0 | OUTDATED |  | OUTDATED | 0 | OUTDATED |  | IMPROPER |  | IMPROPER |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | IMPROPER |  | IMPROPER |  | NEXT ROUND |  | NEXT ROUND |  | REPROVED |  | 1% | FEDERADO-ANEXO E DRONE MAIO 2026 | OUTDATED |  | OUTDATED | FEDERADO-ANEXO E DRONE MAIO 2026 | OUTDATED |  | OUTDATED | FEDERADO-ANEXO E DRONE MAIO 2026
26 | CPQ11-BASM-INFR-PUMP-R24.rvt | CPQ11-BASM-INFR-PUMP-R22.rvt | PUMP | MENDES HOLLER | 1112 | PGMAK | 1129 | V32 | 24/04/2026 | V3 | 03/07/2026 | V3 | 2026-07-03 | R24 | INGRYD | REPROVED | 9 | 1% | DONE | IMPROPER | 8 | IMPROPER | DONE | IMPROPER |  | IMPROPER |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | REPROVED | 0 | 1% | 13, 21, 25, 31, 36 | NEXT ROUND | 0 | NEXT ROUND | 13, 21, 25, 31, 36 | REPROVED | 1 | 1% | 36 | NEXT ROUND | 1 | NEXT ROUND | 36 | REPROVED | 3 | 33% | 36 | OUTDATED | 3 | OUTDATED | 36 | OUTDATED | 3 | OUTDATED | 36 | OUTDATED | 3 | OUTDATED | 36 | NEXT ROUND | 3 | NEXT ROUND | 36 | REPROVED | 6 | 67% | 36 | OUTDATED | 6 | OUTDATED | 36 | OUTDATED | 6 | OUTDATED | 36 | NEXT ROUND | 6 | NEXT ROUND | 36 | IMPROPER | 6 | IMPROPER | 36 | OUTDATED | 6 | OUTDATED | 36 | OUTDATED | 6 | OUTDATED | 36 | OUTDATED | 6 | OUTDATED | 36 | NEXT ROUND | 6 | NEXT ROUND | 36 | REPROVED | 6 | 67% | 36 | APPROVED | 9 | 100% | FEDERADO -ANEXO | PREVIOUSLY APPROVED | 9 | 100% | FEDERADO -ANEXO
59 | CPQ11-STRC-DPFN-SITE-R24.rvt | CPQ11-STRC-DPFN-SITE-R22.rvt | SITE | GEOFIX/TECNOGEO | 0000 | TENAX | 0000 | V13 | 12/05/2026 | V1 | 15/05/2026 | V1 | 2026-05-15 | R24 | N/A | APPROVED | 0 | 100% | DONE | PREVIOUSLY APPROVED | 0 | 100% | DONE | PREVIOUSLY APPROVED | 0 | 100% |  | PREVIOUSLY APPROVED | 0 | 100% |  | PREVIOUSLY APPROVED | 0 | 100% |  | PREVIOUSLY APPROVED | 0 | 100% | 36 | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | REPROVED |  | 1% |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | APPROVED | 1 | 100% |  | PREVIOUSLY APPROVED | 1 | 100% |  | PREVIOUSLY APPROVED | 1 | 100% |  | PREVIOUSLY APPROVED | 1 | 100%
- | CPQ11-BASM-DEVS-PUMP-R24.rvt | CPQ11-BASM-DEVS-PUMP-R22.rvt | PUMP | BLACKBOX | 1114 | BLACKBOX | 1114 | V14 | 03/02/2026 | V1 | 15/05/2026 | V14 | 2026-02-03 | R22 | FLAVIO | REPROVED | 4 | 1% | DONE | REPROVED | 3 | 75% | DONE | REPROVED | 3 | 75% | 36 | OUTDATED | 3 | OUTDATED | 36 | OUTDATED | 3 | OUTDATED | 36 | NEXT ROUND | 3 | NEXT ROUND |  | APPROVED | 4 | 100% | 36 | PREVIOUSLY APPROVED | 4 | 100% | 36 | PREVIOUSLY APPROVED | 4 | 100% | 36 | PREVIOUSLY APPROVED | 4 | 100% | 36 | PREVIOUSLY APPROVED | 4 | 100% | 36 | PREVIOUSLY APPROVED | 4 | 100% | 36 | PREVIOUSLY APPROVED | 4 | 100% | 36 | PREVIOUSLY APPROVED | 4 | 100% | 36 | PREVIOUSLY APPROVED | 4 | 100% | 36 | PREVIOUSLY APPROVED | 4 | 100% | 36 | PREVIOUSLY APPROVED | 4 | 100% | 36 | PREVIOUSLY APPROVED | 4 | 100% | 36 | PREVIOUSLY APPROVED | 4 | 100% | 36 | PREVIOUSLY APPROVED | 4 | 100% | 36 | PREVIOUSLY APPROVED | 4 | 100% | 36 | PREVIOUSLY APPROVED | 4 | 100% | 36 | PREVIOUSLY APPROVED | 4 | 100% | 36 | PREVIOUSLY APPROVED | 4 | 100% | 36 | PREVIOUSLY APPROVED | 4 | 100% | 36 | PREVIOUSLY APPROVED | 4 | 100% | 36 | PREVIOUSLY APPROVED | 4 | 100% | 36 | PREVIOUSLY APPROVED | 4 | 100% | 36
53 | CPQ11-CIVL-ERTH-SITE-R24.rvt | CPQ11-CIVL-ERTH-SITE-R22.rvt | SITE | GARCIA | 1119 | CADBIM | 1128 | V18 | 08/04/2026 | V6 | 24/06/2026 | V13 | 2026-03-06 | R24 | FLAVIO | APPROVED | 1 | 100% | DONE | PREVIOUSLY APPROVED | 0 | 100% | DONE | PREVIOUSLY APPROVED | 0 | 100% |  | PREVIOUSLY APPROVED | 0 | 100% |  | PREVIOUSLY APPROVED | 0 | 100% |  | PREVIOUSLY APPROVED | 0 | 100% |  | NEXT ROUND |  | NEXT ROUND |  | REPROVED | 0 | 1% | DRONE 30.01.26 | NEXT ROUND | 0 | NEXT ROUND | DRONE 30.01.26 | NEXT ROUND | 0 | NEXT ROUND | DRONE 30.01.26 | REPROVED | 0 | 1% | DRONE 26.01.26 | NEXT ROUND | 0 | NEXT ROUND | DRONE 26.01.26 | NEXT ROUND | 0 | NEXT ROUND | DRONE 26.01.26 | NEXT ROUND | 0 | NEXT ROUND | DRONE 26.01.26 | NEXT ROUND | 0 | NEXT ROUND | DRONE 26.01.26 | NEXT ROUND | 0 | NEXT ROUND | DRONE 26.01.26 | NEXT ROUND | 0 | NEXT ROUND | DRONE 26.01.26 | NEXT ROUND | 0 | NEXT ROUND | DRONE 26.01.26 | NEXT ROUND | 0 | NEXT ROUND | DRONE 26.01.26 | NEXT ROUND | 0 | NEXT ROUND | DRONE 26.01.26 | NEXT ROUND | 0 | NEXT ROUND | DRONE 26.01.26 | NEXT ROUND | 0 | NEXT ROUND | DRONE 26.01.26 | NEXT ROUND | 0 | NEXT ROUND | DRONE 26.01.26 | APPROVED | 1 | 100% | DRONE 26.01.26 | PREVIOUSLY APPROVED | 1 | 100% | DRONE 26.01.26 | PREVIOUSLY APPROVED | 1 | 100% | DRONE 26.01.26 | PREVIOUSLY APPROVED | 1 | 100% | DRONE 26.01.26 | PREVIOUSLY APPROVED | 1 | 100% | DRONE 26.01.26
58 | CPQ11-STRC-CONC-SITE-R24.rvt | CPQ11-STRC-CONC-SITE-R22.rvt | SITE | SERV OBRAS | 1120 | TENAX | 0000 | V17 | 12/05/2026 | V1 | 15/05/2026 | V1 | 2026-05-15 | R24 | YASMIN | REPROVED | 5 | 1% | DONE | IMPROPER | 3 | IMPROPER | DONE | APPROVED | 3 | 100% | 21 e 36 | PREVIOUSLY APPROVED | 3 | 100% | 21 e 36 | PREVIOUSLY APPROVED | 3 | 100% | 21 e 36 | PREVIOUSLY APPROVED | 3 | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | REPROVED | 3 | 75% | 36 | NEXT ROUND | 3 | NEXT ROUND | 36 | REPROVED | 3 | 61% | 36 | NEXT ROUND | 3 | NEXT ROUND | 36 | NEXT ROUND | 3 | NEXT ROUND | 36 | NEXT ROUND | 3 | NEXT ROUND | 36 | NEXT ROUND | 3 | NEXT ROUND | 36 | NEXT ROUND | 3 | NEXT ROUND | 36 | NEXT ROUND | 3 | NEXT ROUND | 36 | NEXT ROUND | 3 | NEXT ROUND | 36 | REPROVED | 2026-07-06 | 86% | 36 | NEXT ROUND | 2026-07-06 | NEXT ROUND | 36 | NEXT ROUND | 2026-07-06 | NEXT ROUND | 36 | NEXT ROUND | 2026-07-06 | NEXT ROUND | 36 | APPROVED | 7 | 100% | 36 | PREVIOUSLY APPROVED | 7 | 100% | 36 | PREVIOUSLY APPROVED | 7 | 100% | 36 | PREVIOUSLY APPROVED | 7 | 100% | 36 | PREVIOUSLY APPROVED | 7 | 100% | 36 | PREVIOUSLY APPROVED | 7 | 100% | 36 | PREVIOUSLY APPROVED | 7 | 100% | 36
3 | CPQ11-ARCH-HMET-SITE-R24.rvt | CPQ11-ARCH-HMET-SITE-R22.rvt | SITE | S-VALE | 1104 | SPBIM | 1127 | V9 | 10/04/2026 | V1 | 15/05/2026 | V7 | 2026-03-17 | R22 | ALINNE | REPROVED | 2 | 1% | DONE | IMPROPER | 0 | IMPROPER | DONE | REPROVED | 0 | 1% | 21,25,31 | NEXT ROUND | 0 | NEXT ROUND | 21,25,31 | NEXT ROUND | 0 | NEXT ROUND | 21,25,31 | NEXT ROUND | 0 | NEXT ROUND |  | REPROVED | 0 | 1% | 36 | OUTDATED | 0 | OUTDATED | 36 | OUTDATED | 0 | OUTDATED | 36 | OUTDATED | 0 | OUTDATED | 36 | APPROVED | 0 | 100% | 36 | PREVIOUSLY APPROVED | 0 | 100% | 36 | PREVIOUSLY APPROVED | 0 | 100% | 36 | PREVIOUSLY APPROVED | 0 | 100% | 36 | PREVIOUSLY APPROVED | 0 | 100% | 36 | PREVIOUSLY APPROVED | 0 | 100% | 36 | PREVIOUSLY APPROVED | 0 | 100% | 36 | PREVIOUSLY APPROVED | 0 | 100% | 36 | PREVIOUSLY APPROVED | 0 | 100% | 36 | PREVIOUSLY APPROVED | 0 | 100% | 36 | PREVIOUSLY APPROVED | 0 | 100% | 36 | PREVIOUSLY APPROVED | 0 | 100% | 36 | PREVIOUSLY APPROVED | 0 | 100% | 36 | PREVIOUSLY APPROVED | 0 | 100% | 36 | PREVIOUSLY APPROVED | 0 | 100% | 36 | PREVIOUSLY APPROVED | 0 | 100% | 36 | PREVIOUSLY APPROVED | 0 | 100% | 36 | PREVIOUSLY APPROVED | 0 | 100% | 36
6 | CPQ11-ARCH-METL-SITE-R24.rvt | CPQ11-ARCH-METL-SITE-R22.rvt | SITE | SERCOP | 1103 | ARE ARQUITETURA | 1130 | V12 | 05/05/2026 | V5 | 22/06/2026 | V5 | 07/01/2026 | R22 |  | REPROVED | 1 | 1% | DONE | IMPROPER | 0 | IMPROPER | DONE | APPROVED | 1 | 100% | 21 e36 | PREVIOUSLY APPROVED | 1 | 100% | 21 e36 | PREVIOUSLY APPROVED | 1 | 100% | 21 e36 | PREVIOUSLY APPROVED | 1 | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100%
52 | CPQ11-CIVL-DRNG-SITE-R24.rvt | CPQ11-CIVL-DRNG-SITE-R22.rvt | SITE | GARCIA | 1119 | CADBIM | 1128 | V20 | 06/05/2026 | V4 | 11/06/2026 | V11 | 2026-02-02 | R22 |  | N/A | 0 | N/A | DONE | IMPROPER | 0 | IMPROPER | DONE | REPROVED | 4 | 1% | 21, 25, 31, 36 | NEXT ROUND | 4 | NEXT ROUND | 21, 25, 31, 36 | REPROVED | 0 | 1% | 21, 25, 31, 36 | APPROVED | 4 | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100%
54 | CPQ11-CIVL-PAVM-SITE-R24.rvt | CPQ11-CIVL-PAVM-SITE-R22.rvt | SITE | GARCIA | 1119 | CADBIM | 1128 | V18 | 30/04/2026 | V2 | 20/05/2026 | V1 | 2025-09-14 | R22 | N/A | APPROVED | 0 | 100% | DONE | PREVIOUSLY APPROVED | 0 | 100% | DONE | PREVIOUSLY APPROVED | 0 | 100% |  | PREVIOUSLY APPROVED | 0 | 100% |  | PREVIOUSLY APPROVED | 0 | 100% |  | PREVIOUSLY APPROVED | 0 | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100%
36 | CPQ11-ELEC-SPDA-SITE-R24.rvt | CPQ11-ELEC-SPDA-SITE-R22.rvt | SITE | MENDES HOLLER | 1112 | MENDES HOLLER | 1112 | V7 | 08/12/2025 | V2 | 03/07/2026 | V7 | 08/12/2025 | R22 | N/A | REPROVED | 4 | 1% | DONE | REPROVED | 2 | 51% | DONE | APPROVED | 4 | 100% | 21,25 e 31 | PREVIOUSLY APPROVED | 4 | 100% | 21,25 e 31 | PREVIOUSLY APPROVED | 4 | 100% | 21,25 e 31 | PREVIOUSLY APPROVED | 4 | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100%
20 | CPQ11-EPMS-DEVS-SITE-R24.rvt | CPQ11-EPMS-DEVS-SITE-R22.rvt | SITE | BLACKBOX | 1114 | BLACKBOX | 1114 | V11 | 03/02/2026 | V1 | 15/05/2026 | V11 | 2026-02-03 | R22 | FLAVIO | REPROVED | 1 | 1% | DONE | IMPROPER | 1 | IMPROPER | DONE | REPROVED | 1 | 1% | 21, 25, 31 | OUTDATED | 1 | OUTDATED | 21, 25, 31 | OUTDATED | 1 | OUTDATED | 21, 25, 31 | NEXT ROUND | 1 | NEXT ROUND |  | APPROVED | 1 | 100% | 21, 36 | PREVIOUSLY APPROVED | 1 | 100% | 21, 36 | PREVIOUSLY APPROVED | 1 | 100% | 21, 36 | PREVIOUSLY APPROVED | 1 | 100% | 21, 36 | PREVIOUSLY APPROVED | 1 | 100% | 21, 36 | PREVIOUSLY APPROVED | 1 | 100% | 21, 36 | PREVIOUSLY APPROVED | 1 | 100% | 21, 36 | PREVIOUSLY APPROVED | 1 | 100% | 21, 36 | PREVIOUSLY APPROVED | 1 | 100% | 21, 36 | PREVIOUSLY APPROVED | 1 | 100% | 21, 36 | PREVIOUSLY APPROVED | 1 | 100% | 21, 36 | PREVIOUSLY APPROVED | 1 | 100% | 21, 36 | PREVIOUSLY APPROVED | 1 | 100% | 21, 36 | PREVIOUSLY APPROVED | 1 | 100% | 21, 36 | PREVIOUSLY APPROVED | 1 | 100% | 21, 36 | PREVIOUSLY APPROVED | 1 | 100% | 21, 36 | PREVIOUSLY APPROVED | 1 | 100% | 21, 36 | PREVIOUSLY APPROVED | 1 | 100% | 21, 36 | PREVIOUSLY APPROVED | 1 | 100% | 21, 36 | PREVIOUSLY APPROVED | 1 | 100% | 21, 36 | PREVIOUSLY APPROVED | 1 | 100% | 21, 36 | PREVIOUSLY APPROVED | 1 | 100% | 21, 36
45 | CPQ11-PLMB-NPWT-SITE-R24.rvt | CPQ11-PLMB-NPWT-SITE-R22.rvt | SITE | STARCENTER | 1118 | STARCENTER | 1118 | V46 | 24/04/2026 | V2 | 15/06/2026 | V46 | 2026-04-24 | R22 | INGRYD | REPROVED | 5 | 1% | DONE | IMPROPER | 0 | IMPROPER | DONE | REPROVED | 0 | 1% | 36 | REPROVED | 0 | 1% | 36 | OUTDATED | 0 | OUTDATED | 36 | NEXT ROUND | 0 | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | REPROVED | 0 | 1% | 25, 31, 36 | NEXT ROUND | 0 | NEXT ROUND | 25, 31, 36 | REPROVED | 0 | 1% | 25, 31, 36 | NEXT ROUND | 0 | NEXT ROUND | 25, 31, 36 | NEXT ROUND | 0 | NEXT ROUND | 25, 31, 36 | REPROVED | 5 | 83% | 36 | NEXT ROUND | 5 | NEXT ROUND | 36 | REPROVED | 5 | 83% | 36 | NEXT ROUND | 5 | NEXT ROUND | 36 | APPROVED | 6 | 100% | 36 | PREVIOUSLY APPROVED | 6 | 100% | 36 | PREVIOUSLY APPROVED | 6 | 100% | 36 | PREVIOUSLY APPROVED | 6 | 100% | 36 | PREVIOUSLY APPROVED | 6 | 100% | 36 | PREVIOUSLY APPROVED | 6 | 100% | 36 | PREVIOUSLY APPROVED | 6 | 100% | 36 | PREVIOUSLY APPROVED | 6 | 100% | 36 | PREVIOUSLY APPROVED | 6 | 100% | 36 | PREVIOUSLY APPROVED | 6 | 100% | 36 | PREVIOUSLY APPROVED | 6 | 100% | 36 | PREVIOUSLY APPROVED | 6 | 100% | 36
32 | CPQ11-SCTY-DEVS-SITE-R24.rvt | CPQ11-SCTY-DEVS-SITE-R22.rvt | SITE | SEGURPRO | 1115 | SEGURPRO | 1115 | V37 | 10/04/2026 | V1 | 20/05/2026 | V30 | 21/11/2025 | R22 |  | REPROVED | 1 | 1% | DONE | IMPROPER | 1 | IMPROPER | DONE | APPROVED | 1 | 100% | 21,25 e 31 | PREVIOUSLY APPROVED | 1 | 100% | 21,25 e 31 | PREVIOUSLY APPROVED | 1 | 100% | 21,25 e 31 | PREVIOUSLY APPROVED | 1 | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100%
65 | CPQ11-STRC-STEE-STIR-2X3.ifc | CPQ11-STRC-STEE-STIR-2X3.ifc | STIR | METASA | 1125 | METASA | 1125 | V3 | 31/10/2025 | V1 | 21/05/2026 | V2 | 2025-07-18 | R22 | N/A | APPROVED | 0 | 100% | DONE | PREVIOUSLY APPROVED | 0 | 100% | DONE | PREVIOUSLY APPROVED | 0 | 100% |  | PREVIOUSLY APPROVED | 0 | 100% |  | PREVIOUSLY APPROVED | 0 | 100% |  | PREVIOUSLY APPROVED | 0 | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100%
41 | CPQ11-FPRT-METK-UTLS-R24.rvt | CPQ11-FPRT-METK-UTLS-R22.rvt | UTLS | PETROTANQUE | 1117 | CADBIM | 1128 | V16 | 06/03/2026 | V5 | 08/07/2026 | V15 | 15/01/2026 | R22 |  | REPROVED | 2 | 1% | DONE | APPROVED | 2 | 100% | DONE | PREVIOUSLY APPROVED | 1 | 100% | 36 | PREVIOUSLY APPROVED | 1 | 100% | 36 | PREVIOUSLY APPROVED | 1 | 100% | 36 | PREVIOUSLY APPROVED | 1 | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100%
46 | CPQ11-PLMB-METK-UTLS-R24.RVT | CPQ11-PLMB-METK-UTLS-R22.RVT | UTLS | STARCENTER | 1118 | STARCENTER | 1118 | V28 | 26/02/2026 | V1 | 19/05/2026 | V28 | 2026-02-26 | R22 | FLAVIO | REPROVED | 3 | 1% | DONE | IMPROPER | 3 | IMPROPER | DONE | REPROVED | 0 | 1% | 36 | REPROVED | 0 | 1% | 36 | OUTDATED | 0 | OUTDATED | 36 | NEXT ROUND | 0 | NEXT ROUND |  | NEXT ROUND |  | NEXT ROUND |  | REPROVED | 2 | 66% | 36 | NEXT ROUND |  | NEXT ROUND |  | REPROVED | 2 | 66% | 36 | OUTDATED | 2 | OUTDATED | 36 | OUTDATED | 2 | OUTDATED | 36 | OUTDATED | 2 | OUTDATED | 36 | OUTDATED | 2 | OUTDATED | 36 | APPROVED | 3 | 100% | 36 | PREVIOUSLY APPROVED | 3 | 100% | 36 | PREVIOUSLY APPROVED | 3 | 100% | 36 | PREVIOUSLY APPROVED | 3 | 100% | 36 | PREVIOUSLY APPROVED | 3 | 100% | 36 | PREVIOUSLY APPROVED | 3 | 100% | 36 | PREVIOUSLY APPROVED | 3 | 100% | 36 | PREVIOUSLY APPROVED | 3 | 100% | 36 | PREVIOUSLY APPROVED | 3 | 100% | 36 | PREVIOUSLY APPROVED | 3 | 100% | 36 | PREVIOUSLY APPROVED | 3 | 100% | 36 | PREVIOUSLY APPROVED | 3 | 100% | 36 | PREVIOUSLY APPROVED | 3 | 100% | 36 | PREVIOUSLY APPROVED | 3 | 100% | 36
63 | CPQ11-STRC-STEE-UTLS-2X3.ifc | CPQ11-STRC-STEE-UTLS-2X3.ifc | UTLS | METASA | 1125 | METASA | 1125 | V6 | 11/02/2026 | V1 | 21/05/2026 | V5 | 27/10/2025 | R22 | N/A | APPROVED | 0 | 100% | DONE | PREVIOUSLY APPROVED | 0 | 100% | DONE | PREVIOUSLY APPROVED | 0 | 100% |  | PREVIOUSLY APPROVED | 0 | 100% |  | PREVIOUSLY APPROVED | 0 | 100% |  | PREVIOUSLY APPROVED | 0 | 100% | 36 | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100%
1 | ARCH ¦ ARCHITECTURE
17 | SYST-SYSTEMS ¦ INFRASTRUCTURE
19 | EPMS-ELECTRICAL POWER MAN/AGEMENT SYSTEM ¦ DEVICES
21 | ROIP-RADIO OVER IP ¦ DEVICES
23 | TELECOM ¦ DEVICES
25 | BAS-BUILDING AUTOMATION SYSTEM ¦ INFRASTRUCTURE
27 | BAS ¦ DEVICES
29 | SCTY-SECURITY ¦ INFRASTRUCTURE
31 | SCTY ¦ DEVICES
33 | ELEC-ELETRICAL
35 | SPDA ¦ PROTECTION SYSTEM ATMOSPHERIC DISCHARGE
37 | FALM-FIRE ALARM
39 | FPRT-FIRE PROTECTION
42 | PLMB-PLUMBING
47 | MECH-MECHANICAL
49 | LAND-LANDSCAPE
51 | CIVIL
57 | STRC-STRUCTURE
Note on AP18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: NOVAS LÂMPADAS INSERIDAS, NÃO RESOLVIDAS
Note on AP28: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: LÂMPADAS EXISTENTES + NOVAS LÂMPADAS ADICIONADAS. NENHUMA RESOLVIDA
Note on B36: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: EM GUAR FOI REPROVADO - CONFERIR PARA VERIFICAR NO ROUND 7 DE UTLS
Note on AK48: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: COM RESSALVAS, PRECISAM AJUSTAR O WASTE SHED

## LOD 500 - WASTE SHED
LOD 500 ¦ WASTE SHED
| FILE NAME (R24) | FILE NAME (R22) | AREA | TRADE COMPANY | CODE | BIM COMPANY | CODE | ACC VERSION (R22) | ACC FILE DATE (R22) | ACC VERSION (R24) | ACC FILE DATE (R24) | VERSION | FILE DATE | RVT TYPE APROVAL (WASTE SHED) | RESPONSAVEL | R0 - AUDIT STATUS | LAMPS QTDE | R0 - APPROVAL (%) | NUVEM UTILIZADA | R1 - AUDIT STATUS | R1 LAMPS QTDE RESOLVIDAS | R1 - APPROVAL (%) | NUVEM UTILIZADA | R2 - AUDIT STATUS | R2 LAMPS QTDE RESOLVIDAS | R2 - APPROVAL (%) | NUVEM UTILIZADA | R3 - AUDIT STATUS | R3 LAMPS QTDE RESOLVIDAS | R3 - APPROVAL (%) | NUVEM UTILIZADA | R4 - AUDIT STATUS | R4 LAMPS QTDE RESOLVIDAS | R4 - APPROVAL (%) | NUVEM UTILIZADA | R5- AUDIT STATUS | R5 LAMPS QTDE RESOLVIDAS | R5 - APPROVAL (%) | R5NUVEM UTILIZADA | R6- AUDIT STATUS | R6 LAMPS QTDE RESOLVIDAS | R6 - APPROVAL (%) | R6 NUVEM UTILIZADA | R7 - AUDIT STATUS | R7 LAMPS QTDE RESOLVIDAS | R7 - APPROVAL (%) | R7 NUVEM UTILIZADA | R8 - AUDIT STATUS | R8 LAMPS QTDE RESOLVIDAS | R8 - APPROVAL (%) | R9 - AUDIT STATUS | R9 LAMPS QTDE RESOLVIDAS | R9 - APPROVAL (%) | R9 NUVEM UTILIZADA | R10 - AUDIT STATUS | R10 LAMPS QTDE RESOLVIDAS | R10 - APPROVAL (%) | R10 NUVEM UTILIZADA | R11 - AUDIT STATUS | R11 LAMPS QTDE RESOLVIDAS | R11 - APPROVAL (%) | R11 NUVEM UTILIZADA | R12 - AUDIT STATUS | R12 LAMPS QTDE RESOLVIDAS | R12 - APPROVAL (%) | R12 NUVEM UTILIZADA | R13 - AUDIT STATUS | R13 LAMPS QTDE RESOLVIDAS | R13 - APPROVAL (%) | R13 NUVEM UTILIZADA | R14 - AUDIT STATUS | R14 LAMPS QTDE RESOLVIDAS | R14 - APPROVAL (%) | R14 NUVEM UTILIZADA | R15 - AUDIT STATUS | R15 LAMPS QTDE RESOLVIDAS | R15 - APPROVAL (%) | R15 NUVEM UTILIZADA
11 | CPQ11-ARCH-BLPR-GUAR-R24.rvt | CPQ11-ARCH-BLPR-GUAR-R22.rvt | GUAR | INOVAGLASS | 1109 | INOVAGLASS | 1109 | V9 | 04/12/2025 | V1 | 20/05/2026 | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A
15 | CPQ11-ARCH-CEIL-SITE-R24.rvt | CPQ11-ARCH-CEIL-SITE-R22.rvt | SITE | IDEIA DRYWALL | 1101 | T2B | 0000 | V2 | 29/04/2026 | V1 | 12/06/2026 | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A
8 | CPQ11-ARCH-CHAI-SITE-R24.rvt | CPQ11-ARCH-CHAI-SITE-R22.rvt | SITE | S-VALE | 1104 | SPBIM | 1127 | V12 | 06/04/2026 | V1 | 15/05/2026 | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A
3 | CPQ11-ARCH-HMET-SITE-R24.rvt | CPQ11-ARCH-HMET-SITE-R22.rvt | SITE | S-VALE | 1104 | SPBIM | 1127 | V9 | 10/04/2026 | V1 | 15/05/2026 | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A
16 | CPQ11-ARCH-STON-SITE-R24.rvt | CPQ11-ARCH-STON-SITE-R23.rvt | SITE | STONE | 0000 | STONE | 0000 | V10 | 11/05/2026 | V3 | 09/06/2026 | N/A | N/A | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A
1 | ARCH ¦ ARCHITECTURE
28 | CPQ11-BASM-DEVS-PUMP-R24.rvt | CPQ11-BASM-DEVS-PUMP-R22.rvt | PUMP | BLACKBOX | 1114 | BLACKBOX | 1114 | V14 | 03/02/2026 | V1 | 15/05/2026 | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A
26 | CPQ11-BASM-INFR-PUMP-R24.rvt | CPQ11-BASM-INFR-PUMP-R22.rvt | PUMP | MENDES HOLLER | 1112 | PGMAK | 1129 | V32 | 24/04/2026 | V3 | 03/07/2026 | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A
52 | CPQ11-CIVL-DRNG-SITE-R24.rvt | CPQ11-CIVL-DRNG-SITE-R22.rvt | SITE | GARCIA | 1119 | CADBIM | 1128 | V20 | 06/05/2026 | V4 | 11/06/2026 | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A
53 | CPQ11-CIVL-ERTH-SITE-R24.rvt | CPQ11-CIVL-ERTH-SITE-R22.rvt | SITE | GARCIA | 1119 | CADBIM | 1128 | V18 | 08/04/2026 | V6 | 24/06/2026 | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A
56 | CPQ11-CIVL-LOCK-SITE-R24.rvt | CPQ11-CIVL-LOCK-SITE-R22.rvt | SITE | STEINER | 0000 | PMD | 0000 | V11 | 21/03/2026 | V1 | 18/05/2026 | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A
54 | CPQ11-CIVL-PAVM-SITE-R24.rvt | CPQ11-CIVL-PAVM-SITE-R22.rvt | SITE | GARCIA | 1119 | CADBIM | 1128 | V18 | 30/04/2026 | V2 | 20/05/2026 | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A
34 | CPQ11-ELEC-ELEC-SITE-R24.rvt | CPQ11-ELEC-ELEC-SITE-R22.rvt | SITE | MENDES HOLLER | 1112 | PGMAK | 1129 | V33 | 05/03/2026 | V1 | 19/05/2026 | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A
36 | CPQ11-ELEC-SPDA-SITE-R24.rvt | CPQ11-ELEC-SPDA-SITE-R22.rvt | SITE | MENDES HOLLER | 1112 | MENDES HOLLER | 1112 | V7 | 08/12/2025 | V2 | 03/07/2026 | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A
20 | CPQ11-EPMS-DEVS-SITE-R24.rvt | CPQ11-EPMS-DEVS-SITE-R22.rvt | SITE | BLACKBOX | 1114 | BLACKBOX | 1114 | V11 | 03/02/2026 | V1 | 15/05/2026 | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A
38 | CPQ11-FALM-FALM-SITE-R24.rvt | CPQ11-FALM-FALM-SITE-R22.rvt | SITE | MENDES HOLLER | 1112 | MENDES HOLLER | 1112 | V11 | 08/05/2026 | V3 | 10/07/2026 | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A
17 | SYST-SYSTEMS ¦ INFRASTRUCTURE
40 | CPQ11-FPRT-FPRT-SITE-R24.rvt | CPQ11-FPRT-FPRT-SITE-R22.rvt | SITE | MENDES HOLLER | 1112 | MENDES HOLLER | 1112 | V16 | 14/05/2026 | V4 | 13/07/2026 | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A
19 | EPMS-ELECTRICAL POWER MAN/AGEMENT SYSTEM ¦ DEVICES
41 | CPQ11-FPRT-METK-UTLS-R24.rvt | CPQ11-FPRT-METK-UTLS-R22.rvt | UTLS | PETROTANQUE | 1117 | CADBIM | 1128 | V16 | 06/03/2026 | V5 | 08/07/2026 | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A
21 | ROIP-RADIO OVER IP ¦ DEVICES
48 | CPQ11-MECH-MECH-GUAR-R24.rvt | CPQ11-MECH-MECH-GUAR-R22.rvt | GUAR | STARCENTER | 1118 | STARCENTER | 1118 | V23 | 16/04/2026 | V1 | 19/05/2026 | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A
23 | TELECOM ¦ DEVICES
44 | CPQ11-PLMB-DIES-SITE-R24.rvt | CPQ11-PLMB-DIES-SITE-R22.rvt | SITE | MENDES HOLLER | 1112 | MENDES HOLLER | 1112 | V14 | 03/03/2026 | V4 | 13/07/2026 | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A
25 | BAS-BUILDING AUTOMATION SYSTEM ¦ INFRASTRUCTURE
46 | CPQ11-PLMB-METK-UTLS-R24.RVT | CPQ11-PLMB-METK-UTLS-R22.RVT | UTLS | STARCENTER | 1118 | STARCENTER | 1118 | V28 | 26/02/2026 | V1 | 19/05/2026 | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A
27 | BAS ¦ DEVICES
45 | CPQ11-PLMB-NPWT-SITE-R24.rvt | CPQ11-PLMB-NPWT-SITE-R22.rvt | SITE | STARCENTER | 1118 | STARCENTER | 1118 | V46 | 24/04/2026 | V2 | 15/06/2026 | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A
29 | SCTY-SECURITY ¦ INFRASTRUCTURE
43 | CPQ11-PLMB-PLMB-SITE-R24.rvt | CPQ11-PLMB-PLMB-SITE-R22.rvt | SITE | MENDES HOLLER | 1112 | PGMAK | 1129 | V27 | 08/04/2026 | V2 | 23/06/2026 | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A
31 | SCTY ¦ DEVICES
22 | CPQ11-ROIP-DEVS-GUAR-R24.rvt | CPQ11-ROIP-DEVS-GUAR-R22.rvt | GUAR | IB TECH | 1113 | IB TECH | 1113 | V12 | 13/05/2026 | V2 | 01/06/2026 | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A
32 | CPQ11-SCTY-DEVS-SITE-R24.rvt | CPQ11-SCTY-DEVS-SITE-R22.rvt | SITE | SEGURPRO | 1115 | SEGURPRO | 1115 | V37 | 10/04/2026 | V1 | 20/05/2026 | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A
33 | ELEC-ELETRICAL
| CPQ11-SCTY-GATE-SITE-R24.rvt | CPQ11-SCTY-GATE-SITE-R24.rvt | SITE | FM SECURITY | 0000 | FM SECURITY | 0000 | V2 | 07/05/2026 | V5 | 08/07/2026 | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A
35 | SPDA ¦ PROTECTION SYSTEM ATMOSPHERIC DISCHARGE
30 | CPQ11-SCTY-INFR-SITE-R24.rvt | CPQ11-SCTY-INFR-SITE-R22.rvt | SITE | MENDES HOLLER | 1112 | PGMAK | 1129 | V34 | 05/05/2026 | V3 | 03/07/2026 | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A
37 | FALM-FIRE ALARM
64 | CPQ11-STRC-STEE-GUAR-2X3.ifc | CPQ11-STRC-STEE-GUAR-2X3.ifc | GUAR | METASA | 1125 | METASA | 1125 | V6 | 01/11/2025 | V1 | 21/05/2026 | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A
39 | FPRT-FIRE PROTECTION
| CPQ11-STRC-STEE-STIR-2X3.ifc | CPQ11-STRC-STEE-STIR-2X3.ifc | STIR | METASA | 1125 | METASA | 1125 | V3 | 31/10/2025 | V1 | 21/05/2026 | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A
18 | CPQ11-SYST-INFR-SITE-R24.rvt | CPQ11-SYST-INFR-SITE-R22.rvt | SITE | MENDES HOLLER | 1112 | PGMAK | 1129 | V39 | 12/05/2026 | V4 | 14/07/2026 | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A
42 | PLMB-PLUMBING
24 | CPQ11-TCOM-DEVS-SITE-R24.rvt | CPQ11-TCOM-DEVS-SITE-R22.rvt | SITE | BLACKBOX | 1114 | BLACKBOX | 1114 | V14 | 29/04/2026 | V2 | 07/07/2026 | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A
5 | CPQ11-ARCH-FENC-SITE-R24.rvt | CPQ11-ARCH-FENC-SITE-R22.rvt | SITE | SERCOP | 1103 | ARE ARQUITETURA | 1130 | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED
9 | CPQ11-ARCH-NEWJ-SITE-R24.rvt | CPQ11-ARCH-NEWJ-SITE-R22.rvt | SITE | RACIONAL | 1106 | TENAX | 0000 | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED
14 | CPQ11-ARCH-SGNH-SITE-R24.rvt | CPQ11-ARCH-SGNH-SITE-R22.rvt | SITE | CONTRACTING | 0000 | CONTRACTING | 0000 | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED
47 | MECH-MECHANICAL
13 | CPQ11-ARCH-SGNV-SITE-R24.rvt | CPQ11-ARCH-SGNV-SITE-R22.rvt | SITE | VISUAL GEAC | 0000 | CONTRACTING | 0000 | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED
49 | LAND-LANDSCAPE
10 | CPQ11-ARCH-WTRP-SITE-R24.rvt | CPQ11-ARCH-WTRP-SITE-R22.rvt | SITE | ITS | 1107 | RBV | 0000 | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED
51 | CIVIL
55 | CPQ11-CIVL-SIGN-SITE-R24.rvt | CPQ11-CIVL-SIGN-SITE-R22.rvt | SITE | CONTRACTING | 0000 | CONTRACTING | 0000 | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED
50 | CPQ11-LAND-LAND-SITE-R24.rvt | CPQ11-LAND-LAND-SITE-R22.rvt | SITE | ORGANISMO VIVO | 0000 | CONTRACTING | 0000 | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED
61 | CPQ11-STRC-CHAI-SITE-R24.rvt | CPQ11-STRC-CHAI-SITE-R22.rvt | SITE | S-VALE | 1104 | SPBIM | 1127 | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED
62 | CPQ11-STRC-FENC-SITE-R24.rvt | CPQ11-STRC-FENC-SITE-R22.rvt | SITE | SERCOP, SERV OBRAS | 1124 | CONTRACTING | 0000 | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED
60 | CPQ11-STRC-FLOO-SITE-R24.rvt | CPQ11-STRC-FLOO-SITE-R22.rvt | SITE | MODAX | 1121 | MODAX | 1121 | V1 | 05/05/2026 | V2 | 26/05/2026 | V2 | 26/05/2026 | R24 |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NOT PUBLISHED |  | NEXT ROUND |  | 0% |  | NEXT ROUND |  | 0% |  | IMPROPER |  | IMPROPER | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED |  | OUTDATED
57 | STRC-STRUCTURE
58 | CPQ11-STRC-CONC-SITE-R24.rvt | CPQ11-STRC-CONC-SITE-R22.rvt | SITE | SERV OBRAS | 1120 | TENAX | 0000 | V17 | 12/05/2026 | V1 | 15/05/2026 | V1 | 15/05/2026 | R24 | ALINNE | REPROVED | 1 | 1% | 36 | NEXT ROUND | 1 | NEXT ROUND |  | NEXT ROUND | 1 | NEXT ROUND |  | NEXT ROUND | 1 | NEXT ROUND |  | APPROVED | 1 | 100% |  | REPROVED | 0 | 1% | 36 | NEXT ROUND | 0 | NEXT ROUND | 36 | NEXT ROUND | 0 | NEXT ROUND | 36 | APPROVED | 0 | 100% | PREVIOUSLY APPROVED |  | 100% | 36 | PREVIOUSLY APPROVED |  | 100% | 36 | PREVIOUSLY APPROVED |  | 100% | 36 | PREVIOUSLY APPROVED |  | 100% | 36 | PREVIOUSLY APPROVED |  | 100% | 36 | PREVIOUSLY APPROVED |  | 100% | 36 | PREVIOUSLY APPROVED |  | 100% | 36
59 | CPQ11-STRC-DPFN-SITE-R24.rvt | CPQ11-STRC-DPFN-SITE-R22.rvt | SITE | GEOFIX/TECNOGEO | 0000 | TENAX | 0000 | V13 | 12/05/2026 | V1 | 15/05/2026 | V1 | 15/05/2026 | R24 | ALINNE | REPROVED | 1 | 1% | 36 | NEXT ROUND | 1 | NEXT ROUND |  | NEXT ROUND | 1 | NEXT ROUND |  | NEXT ROUND | 1 | NEXT ROUND |  | APPROVED | 1 | 100% |  | REPROVED | 0 | 1% | 36 | NEXT ROUND | 0 | NEXT ROUND | 36 | NEXT ROUND | 0 | NEXT ROUND | 36 | APPROVED | 0 | 100% | PREVIOUSLY APPROVED |  | 100% | 36 | PREVIOUSLY APPROVED |  | 100% | 36 | PREVIOUSLY APPROVED |  | 100% | 36 | PREVIOUSLY APPROVED |  | 100% | 36 | PREVIOUSLY APPROVED |  | 100% | 36 | PREVIOUSLY APPROVED |  | 100% | 36 | PREVIOUSLY APPROVED |  | 100% | 36
12 | CPQ11-ARCH-PART-SITE-R24.rvt | CPQ11-ARCH-PART-SITE-R22.rvt | SITE | IDEIA DRYWALL | 1101 | FCH | 1126 | V14 | 18/03/2026 | V2 | 17/06/2026 | V13 | 13/11/2025 | R22 | ALINNE | APPROVED | 0 | 100% |  | PREVIOUSLY APPROVED | 0 | 100% |  | PREVIOUSLY APPROVED | 0 | 100% |  | PREVIOUSLY APPROVED | 0 | 100% |  | PREVIOUSLY APPROVED | 0 | 100% |  | PREVIOUSLY APPROVED | 0 | 100% |  | PREVIOUSLY APPROVED | 0 | 100% |  | PREVIOUSLY APPROVED | 0 | 100% |  | PREVIOUSLY APPROVED | 0 | 100% | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100%
2 | CPQ11-ARCH-ARCH-SITE-R24.rvt | CPQ11-ARCH-ARCH-SITE-R22.rvt | SITE | ARE ARQUITETURA | 1130 | ARE ARQUITETURA | 1130 | V28 | 17/04/2026 | V4 | 15/07/2026 | V22 | 30/01/2026 | R22 | ALINNE | APPROVED | 0 | 100% |  | PREVIOUSLY APPROVED | 0 | 100% |  | PREVIOUSLY APPROVED | 0 | 100% |  | PREVIOUSLY APPROVED | 0 | 100% |  | PREVIOUSLY APPROVED | 0 | 100% |  | PREVIOUSLY APPROVED | 0 | 100% |  | PREVIOUSLY APPROVED | 0 | 100% |  | PREVIOUSLY APPROVED | 0 | 100% |  | PREVIOUSLY APPROVED | 0 | 100% | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100%
6 | CPQ11-ARCH-METL-SITE-R24.rvt | CPQ11-ARCH-METL-SITE-R22.rvt | SITE | SERCOP | 1103 | ARE ARQUITETURA | 1130 | V12 | 05/05/2026 | V5 | 22/06/2026 | V7 | 20/02/2026 | R22 | ALINNE | REPROVED | 1 | 1% | 36 | NEXT ROUND | 1 | NEXT ROUND |  | NEXT ROUND | 1 | NEXT ROUND |  | NEXT ROUND | 1 | NEXT ROUND |  | APPROVED | 1 | 100% |  | PREVIOUSLY APPROVED | 1 | 100% |  | PREVIOUSLY APPROVED | 1 | 100% |  | PREVIOUSLY APPROVED | 1 | 100% |  | PREVIOUSLY APPROVED | 1 | 100% | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100%
63 | CPQ11-STRC-STEE-UTLS-2X3.ifc | CPQ11-STRC-STEE-UTLS-2X3.ifc | UTLS | METASA | 1125 | METASA | 1125 | V6 | 11/02/2026 | V1 | 21/05/2026 | V6 | 11/02/2026 | R22 | ALINNE | REPROVED | 1 | 1% | 36 | NEXT ROUND | 1 | NEXT ROUND |  | NEXT ROUND | 1 | NEXT ROUND |  | NEXT ROUND | 1 | NEXT ROUND |  | APPROVED | 1 | 100% |  | PREVIOUSLY APPROVED | 1 | 100% |  | PREVIOUSLY APPROVED | 1 | 100% |  | PREVIOUSLY APPROVED | 1 | 100% |  | PREVIOUSLY APPROVED | 1 | 100% | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100% |  | PREVIOUSLY APPROVED |  | 100%

## RELATÓRIO ACC
Folder name and path | Name | Software version | Model type | Description | Version number | Published to | Extracted to folder | Added to Packages | Publicly shared | Synced with Bridge | Markups | Issues | File size | Last updated | Last updated for control table
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/ARCH | CPQ11-ARCH-ARCH-DATA-R24.rvt | Revit 2024 | Added manually |  | V3 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 255.8 MB | 2026-06-03 12:16 | 03/06/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/ARCH | CPQ11-ARCH-ARCH-SITE-R24.rvt | Revit 2024 | Added manually |  | V4 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 69.4 MB | 2026-07-15 13:10 | 15/07/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/ARCH | CPQ11-ARCH-BLPR-GUAR-R24.rvt | Revit 2024 | Added manually |  | V1 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 36.2 MB | May 20, 2026 5:55 PM | 20/05/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/ARCH | CPQ11-ARCH-CEIL-DATA-R24.rvt | Revit 2024 | Added manually |  | V1 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 186.8 MB | 2026-06-04 19:11 | 04/06/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/ARCH | CPQ11-ARCH-CEIL-SITE-R24.rvt | Revit 2024 | Added manually |  | V1 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 49.2 MB | 2026-06-12 16:55 | 12/06/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/ARCH | CPQ11-ARCH-CHAI-SITE-R24.rvt | Revit 2024 | Added manually |  | V1 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 10.3 MB | May 15, 2026 3:26 PM | 15/05/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/ARCH | CPQ11-ARCH-FACD-DATA-R24.rvt | Revit 2024 | Added manually |  | V3 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 132.9 MB | 2026-07-07 18:01 | 07/07/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/ARCH | CPQ11-ARCH-HM90-DATA-R24.rvt | Revit 2024 | Added manually |  | V2 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 30.9 MB | 2026-06-26 14:16 | 26/06/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/ARCH | CPQ11-ARCH-HMET-DATA-R24.rvt | Revit 2024 | Added manually |  | V1 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 75.2 MB | May 15, 2026 4:56 PM | 15/05/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/ARCH | CPQ11-ARCH-HMET-SITE-R24.rvt | Revit 2024 | Added manually |  | V1 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 26.7 MB | May 15, 2026 5:26 PM | 15/05/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/ARCH | CPQ11-ARCH-METL-SITE-R24.rvt | Revit 2024 | Added manually |  | V5 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 36.3 MB | 2026-06-22 16:08 | 22/06/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/ARCH | CPQ11-ARCH-OHCD-DATA-R24.rvt | Revit 2024 | Added manually |  | V2 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 11.6 MB | 2026-06-04 11:02 | 04/06/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/ARCH | CPQ11-ARCH-PART-C12A-R24.rvt | Revit 2024 | Added manually |  | V2 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 87.8 MB | May 27, 2026 10:24 AM | 27/05/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/ARCH | CPQ11-ARCH-PART-C345-R24.rvt | Revit 2024 | Added manually |  | V1 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 68.2 MB | May 19, 2026 2:37 PM | 19/05/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/ARCH | CPQ11-ARCH-PART-SITE-R24.rvt | Revit 2024 | Added manually |  | V2 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 21.6 MB | 2026-06-17 19:38 | 17/06/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/ARCH | CPQ11-ARCH-ROOF-DATA-R24.rvt | Revit 2024 | Added manually |  | V2 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 22.6 MB | May 20, 2026 3:57 PM | 20/05/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/ARCH | CPQ11-ARCH-SHLV-DATA-R24.rvt | Revit 2024 | Added manually |  | V1 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 23.3 MB | May 20, 2026 5:54 PM | 20/05/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/ARCH | CPQ11-ARCH-STON-SITE-R24.rvt | Revit 2024 | Added manually |  | V3 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 10.4 MB | 2026-06-09 14:26 | 09/06/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/ARCH | CPQ11-ARCH-WMES-DATA-R24.rvt | Revit 2024 | Added manually |  | V3 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 31.3 MB | 2026-06-24 16:15 | 24/06/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/ARCH/NWC | CPQ11-ARCH-ARCH-DATA-R24.nwc |  |  |  | V3 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 7 MB | 2026-06-03 12:05 | 03/06/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/ARCH/NWC | CPQ11-ARCH-ARCH-SITE-R24.nwc |  |  |  | V3 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 1.7 MB | 2026-07-15 13:08 | 15/07/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/ARCH/NWC | CPQ11-ARCH-CHAI-SITE-R24.nwc |  |  |  | V1 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 11.5 MB | May 15, 2026 3:29 PM | 15/05/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/ARCH/NWC | CPQ11-ARCH-FACD-DATA-R24.nwc |  |  |  | V2 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 120.4 MB | 2026-07-07 17:47 | 07/07/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/ARCH/NWC | CPQ11-ARCH-HM90-DATA-R24.nwc |  |  |  | V2 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 334.4 KB | 2026-06-26 14:13 | 26/06/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/ARCH/NWC | CPQ11-ARCH-HMET-DATA-R24.nwc |  |  |  | V1 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 3.2 MB | May 15, 2026 4:56 PM | 15/05/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/ARCH/NWC | CPQ11-ARCH-HMET-SITE-R24.nwc |  |  |  | V1 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 737.3 KB | May 15, 2026 4:56 PM | 15/05/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/ARCH/NWC | CPQ11-ARCH-METL-SITE-R24.nwc |  |  |  | V5 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 161.1 MB | 2026-06-22 16:04 | 22/06/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/ARCH/NWC | CPQ11-ARCH-OHCD-DATA-R24.nwc |  |  |  | V2 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 8.5 KB | 2026-06-04 11:03 | 04/06/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/ARCH/NWC | CPQ11-ARCH-PART-C12A-R24.nwc |  |  |  | V2 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 5.6 MB | May 27, 2026 10:18 AM | 27/05/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/ARCH/NWC | CPQ11-ARCH-PART-C345-R24.nwc |  |  |  | V1 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 3.8 MB | May 19, 2026 2:27 PM | 19/05/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/ARCH/NWC | CPQ11-ARCH-PART-SITE-R24.nwc |  |  |  | V2 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 677.6 KB | 2026-06-17 19:36 | 17/06/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/ARCH/NWC | CPQ11-ARCH-ROOF-DATA-R24.nwc |  |  |  | V1 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 12.6 MB | May 20, 2026 3:41 PM | 20/05/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/ARCH/NWC | CPQ11-ARCH-STON-SITE-R24.nwc |  |  |  | V3 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 298.8 KB | 2026-06-09 14:27 | 09/06/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/ARCH/NWC | CPQ11-ARCH-WMES-DATA-R24.nwc |  |  |  | V3 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 17.1 MB | 2026-06-24 15:20 | 24/06/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/CIVIL | CPQ11-CIVL-DRNG-SITE-R24.rvt | Revit 2024 | Added manually |  | V4 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 80.9 MB | 2026-06-11 10:40 | 11/06/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/CIVIL | CPQ11-CIVL-ERTH-SITE-R24.rvt | Revit 2024 | Added manually |  | V6 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 38.7 MB | 2026-06-24 09:47 | 24/06/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/CIVIL | CPQ11-CIVL-LOCK-SITE-R24.rvt | Revit 2024 | Added manually |  | V1 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 332.3 MB | May 18, 2026 5:11 PM | 18/05/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/CIVIL | CPQ11-CIVL-PAVM-SITE-R24.rvt | Revit 2024 | Added manually |  | V2 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 47.1 MB | May 20, 2026 3:44 PM | 20/05/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/CIVIL/NWC | CPQ11-CIVL-DRNG-SITE-R24.nwc |  |  |  | V4 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 11.9 MB | 2026-06-22 16:56 | 22/06/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/CIVIL/NWC | CPQ11-CIVL-ERTH-SITE-R24.nwc |  |  |  | V4 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 2 MB | 2026-06-24 09:46 | 24/06/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/CIVIL/NWC | CPQ11-CIVL-LOCK-SITE-R24.nwc |  |  |  | V1 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 187.1 MB | May 18, 2026 5:01 PM | 18/05/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/CIVIL/NWC | CPQ11-CIVL-PAVM-SITE-R24.nwc |  |  |  | V3 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 14 MB | 2026-06-22 16:56 | 22/06/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/MECH | CPQ11-MECH-MECH-DATA-R24.rvt | Revit 2024 | Added manually |  | V5 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 220 MB | 2026-07-06 16:37 | 06/07/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/MECH | CPQ11-MECH-MECH-GUAR-R24.rvt | Revit 2024 | Added manually |  | V1 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 123.7 MB | May 19, 2026 2:43 PM | 19/05/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/MECH | CPQ11-PLMB-METK-UTLS-R24.rvt | Revit 2024 | Added manually |  | V1 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 62.2 MB | May 19, 2026 2:43 PM | 19/05/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/MECH | CPQ11-PLMB-NPWT-DATA-R24.rvt | Revit 2024 | Added manually |  | V3 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 177.4 MB | 2026-07-01 16:45 | 01/07/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/MECH | CPQ11-PLMB-NPWT-SITE-R24.rvt | Revit 2024 | Added manually |  | V2 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 127.6 MB | 2026-06-15 09:27 | 15/06/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/MECH/NWC | CPQ11-MECH-MECH-DATA-R24.nwc |  |  |  | V5 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 30.1 MB | 2026-07-06 16:08 | 06/07/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/MECH/NWC | CPQ11-MECH-MECH-GUAR-R24.nwc |  |  |  | V1 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 863.2 KB | May 15, 2026 1:24 PM | 15/05/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/MECH/NWC | CPQ11-PLMB-METK-UTLS-R24.nwc |  |  |  | V1 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 3.1 MB | May 15, 2026 1:24 PM | 15/05/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/MECH/NWC | CPQ11-PLMB-NPWT-DATA-R24.nwc |  |  |  | V3 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 12.7 MB | 2026-07-01 16:35 | 01/07/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/MECH/NWC | CPQ11-PLMB-NPWT-SITE-R24.nwc |  |  |  | V1 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 5.4 MB | May 15, 2026 1:24 PM | 15/05/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/MEP | CPQ11-BASM-DEVS-DATA-R24.rvt | Revit 2024 | Added manually |  | V2 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 53.4 MB | 2026-07-12 23:05 | 12/07/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/MEP | CPQ11-BASM-DEVS-PUMP-R24.rvt | Revit 2024 | Added manually |  | V1 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 42.4 MB | May 15, 2026 5:44 PM | 15/05/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/MEP | CPQ11-BASM-INFR-DATA-R24.rvt | Revit 2024 | Added manually |  | V2 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 66.1 MB | 2026-07-13 12:44 | 13/07/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/MEP | CPQ11-BASM-INFR-PUMP-R24.rvt | Revit 2024 | Added manually |  | V3 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 34.4 MB | 2026-07-03 16:52 | 03/07/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/MEP | CPQ11-DALI-DEVS-DATA-R24.rvt | Revit 2024 | Added manually |  | V2 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 215.4 MB | 2026-06-02 15:01 | 02/06/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/MEP | CPQ11-DASM-DEVS-DATA-R24.rvt | Revit 2024 | Added manually |  | V4 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 340.4 MB | 2026-06-26 17:37 | 26/06/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/MEP | CPQ11-ELEC-ELEC-DATA-R24.rvt | Revit 2024 | Added manually |  | V4 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 302 MB | 2026-07-06 20:53 | 06/07/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/MEP | CPQ11-ELEC-ELEC-SITE-R24.rvt | Revit 2024 | Added manually |  | V1 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 45.4 MB | May 19, 2026 3:56 PM | 19/05/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/MEP | CPQ11-ELEC-SPDA-DATA-R24.rvt | Revit 2024 | Added manually |  | V5 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 118.1 MB | 2026-07-13 16:54 | 13/07/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/MEP | CPQ11-ELEC-SPDA-SITE-R24.rvt | Revit 2024 | Added manually |  | V2 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 70.9 MB | 2026-07-03 14:02 | 03/07/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/MEP | CPQ11-EPMS-DEVS-DATA-R24.rvt | Revit 2024 | Added manually |  | V3 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 27.3 MB | 2026-07-12 14:52 | 12/07/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/MEP | CPQ11-EPMS-DEVS-SITE-R24.rvt | Revit 2024 | Added manually |  | V1 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 15.5 MB | May 15, 2026 5:45 PM | 15/05/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/MEP | CPQ11-FALM-FALM-DATA-R24.rvt | Revit 2024 | Added manually |  | V2 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 71.8 MB | 2026-07-06 13:45 | 06/07/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/MEP | CPQ11-FALM-FALM-SITE-R24.rvt | Revit 2024 | Added manually |  | V3 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 17.5 MB | 2026-07-10 11:23 | 10/07/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/MEP | CPQ11-FPRT-FPRT-DATA-R24.rvt | Revit 2024 | Added manually |  | V4 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 140.8 MB | 2026-06-25 20:05 | 25/06/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/MEP | CPQ11-FPRT-FPRT-SITE-R24.rvt | Revit 2024 | Added manually |  | V4 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 92.9 MB | 2026-07-13 16:03 | 13/07/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/MEP | CPQ11-FPRT-METK-UTLS-R24.rvt | Revit 2024 | Added manually |  | V5 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 10.4 MB | 2026-07-08 13:50 | 08/07/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/MEP | CPQ11-PLMB-DIES-SITE-R24.rvt | Revit 2024 | Added manually |  | V4 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 11.8 MB | 2026-07-13 22:13 | 13/07/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/MEP | CPQ11-PLMB-PLMB-DATA-R24.rvt | Revit 2024 | Added manually |  | V2 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 138.1 MB | 2026-07-13 12:48 | 13/07/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/MEP | CPQ11-PLMB-PLMB-SITE-R24.rvt | Revit 2024 | Added manually |  | V2 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 68.6 MB | 2026-06-23 11:35 | 23/06/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/MEP | CPQ11-ROIP-DEVS-DATA-R24.rvt | Revit 2024 | Added manually |  | V2 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 698.8 MB | 2026-06-03 18:53 | 03/06/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/MEP | CPQ11-ROIP-DEVS-GUAR-R24.rvt | Revit 2024 | Added manually |  | V2 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 39.5 MB | 2026-06-01 16:02 | 01/06/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/MEP | CPQ11-SCTY-DEVS-DATA-R24.rvt | Revit 2024 | Added manually |  | V3 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 232.5 MB | 2026-07-13 15:44 | 13/07/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/MEP | CPQ11-SCTY-DEVS-SITE-R24.rvt | Revit 2024 | Added manually |  | V1 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 234.5 MB | May 20, 2026 9:33 AM | 20/05/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/MEP | CPQ11-SCTY-GATE-SITE-R24.ifc |  |  |  | V1 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 48 MB | May 19, 2026 2:19 PM | 19/05/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/MEP | CPQ11-SCTY-GATE-SITE-R24.rvt | Revit 2024 | Added manually |  | V5 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 94.6 MB | 2026-07-08 16:48 | 08/07/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/MEP | CPQ11-SCTY-INFR-DATA-R24.rvt | Revit 2024 | Added manually |  | V5 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 35.1 MB | 2026-07-10 15:58 | 10/07/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/MEP | CPQ11-SCTY-INFR-SITE-R24.rvt | Revit 2024 | Added manually |  | V3 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 33.5 MB | 2026-07-03 16:05 | 03/07/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/MEP | CPQ11-SYST-INFR-DATA-R24.rvt | Revit 2024 | Added manually |  | V3 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 121.7 MB | 2026-07-13 12:47 | 13/07/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/MEP | CPQ11-SYST-INFR-SITE-R24.rvt | Revit 2024 | Added manually |  | V4 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 79.4 MB | 2026-07-14 08:36 | 14/07/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/MEP | CPQ11-TCOM-DEVS-DATA-R24.rvt | Revit 2024 | Added manually |  | V3 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 121.8 MB | 2026-06-29 21:37 | 29/06/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/MEP | CPQ11-TCOM-DEVS-SITE-R24.rvt | Revit 2024 | Added manually |  | V2 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 40.3 MB | 2026-07-07 17:07 | 07/07/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/MEP/NWC | CPQ11-BASM-DEVS-DATA-R24.nwc |  |  |  | V2 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 1.6 MB | 2026-07-12 23:04 | 12/07/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/MEP/NWC | CPQ11-BASM-DEVS-PUMP-R24.nwc |  |  |  | V1 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 830 KB | May 15, 2026 5:44 PM | 15/05/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/MEP/NWC | CPQ11-BASM-INFR-DATA-R24.nwc |  |  |  | V2 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 40.9 MB | 2026-07-13 12:42 | 13/07/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/MEP/NWC | CPQ11-BASM-INFR-PUMP-R24.nwc |  |  |  | V3 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 1.3 MB | 2026-07-03 16:50 | 03/07/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/MEP/NWC | CPQ11-DALI-DEVS-DATA-R24.nwc |  |  |  | V2 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 2.2 MB | 2026-06-02 14:52 | 02/06/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/MEP/NWC | CPQ11-DASM-DEVS-DATA-R24.nwc |  |  |  | V4 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 33.1 MB | 2026-06-26 17:34 | 26/06/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/MEP/NWC | CPQ11-ELEC-ELEC-DATA-R24.nwc |  |  |  | V5 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 199.5 MB | 2026-07-06 19:48 | 06/07/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/MEP/NWC | CPQ11-ELEC-ELEC-SITE-R24.nwc |  |  |  | V1 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 162.7 MB | May 18, 2026 8:11 AM | 18/05/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/MEP/NWC | CPQ11-ELEC-SPDA-DATA-R24.nwc |  |  |  | V5 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 55 MB | 2026-07-13 16:47 | 13/07/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/MEP/NWC | CPQ11-ELEC-SPDA-SITE-R24.nwc |  |  |  | V2 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 1.6 MB | 2026-07-03 14:01 | 03/07/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/MEP/NWC | CPQ11-EPMS-DEVS-DATA-R24.nwc |  |  |  | V3 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 57.2 KB | 2026-07-12 14:52 | 12/07/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/MEP/NWC | CPQ11-EPMS-DEVS-SITE-R24.nwc |  |  |  | V1 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 70.1 KB | May 15, 2026 5:44 PM | 15/05/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/MEP/NWC | CPQ11-FALM-FALM-DATA-R24.nwc |  |  |  | V2 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 142.4 MB | 2026-07-06 13:28 | 06/07/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/MEP/NWC | CPQ11-FALM-FALM-SITE-R24.nwc |  |  |  | V4 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 7 MB | 2026-07-10 11:29 | 10/07/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/MEP/NWC | CPQ11-FPRT-FPRT-DATA-R24.nwc |  |  |  | V4 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 111.7 MB | 2026-06-25 19:35 | 25/06/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/MEP/NWC | CPQ11-FPRT-FPRT-SITE-R24.nwc |  |  |  | V4 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 19.2 MB | 2026-07-13 16:00 | 13/07/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/MEP/NWC | CPQ11-FPRT-METK-UTLS-R24.nwc |  |  |  | V3 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 1.6 MB | 2026-07-08 13:49 | 08/07/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/MEP/NWC | CPQ11-PLMB-DIES-SITE-R24.nwc |  |  |  | V4 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 3.9 MB | 2026-07-13 22:11 | 13/07/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/MEP/NWC | CPQ11-PLMB-PLMB-DATA-R24.nwc |  |  |  | V2 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 31.4 MB | 2026-07-13 12:42 | 13/07/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/MEP/NWC | CPQ11-PLMB-PLMB-SITE-R24.nwc |  |  |  | V2 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 6.7 MB | 2026-06-23 11:34 | 23/06/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/MEP/NWC | CPQ11-ROIP-DEVS-DATA-R24.nwc |  |  |  | V2 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 55 MB | 2026-06-03 18:35 | 03/06/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/MEP/NWC | CPQ11-ROIP-DEVS-GUAR-R24.nwc |  |  |  | V2 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 2.3 MB | 2026-06-01 16:05 | 01/06/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/MEP/NWC | CPQ11-SCTY-DEVS-DATA-R24.nwc |  |  |  | V2 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 4.6 MB | 2026-07-13 15:34 | 13/07/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/MEP/NWC | CPQ11-SCTY-GATE-SITE-R24.nwc |  |  |  | V4 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 4.7 MB | 2026-07-08 16:50 | 08/07/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/MEP/NWC | CPQ11-SCTY-INFR-DATA-R24.nwc |  |  |  | V4 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 35.9 MB | 2026-07-10 15:56 | 10/07/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/MEP/NWC | CPQ11-SCTY-INFR-SITE-R24.nwc |  |  |  | V3 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 915.3 KB | 2026-07-03 16:05 | 03/07/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/MEP/NWC | CPQ11-SYST-INFR-DATA-R24.nwc |  |  |  | V3 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 62.5 MB | 2026-07-13 12:42 | 13/07/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/MEP/NWC | CPQ11-SYST-INFR-SITE-R24.nwc |  |  |  | V3 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 155.4 MB | 2026-07-07 09:31 | 07/07/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/MEP/NWC | CPQ11-TCOM-DEVS-DATA-R24.nwc |  |  |  | V3 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 6 MB | 2026-06-29 21:27 | 29/06/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/MEP/NWC | CPQ11-TCOM-DEVS-SITE-R24.nwc |  |  |  | V2 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 190.4 KB | 2026-07-07 17:06 | 07/07/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/STEEL | CPQ11-STRC-STEE-ADMN-R24.rvt | Revit 2024 | Added manually |  | V1 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 213.2 MB | May 20, 2026 9:25 AM | 20/05/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/STEEL | CPQ11-STRC-STEE-COL1-R24.rvt | Revit 2024 | Added manually |  | V1 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 645.9 MB | May 20, 2026 11:13 AM | 20/05/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/STEEL | CPQ11-STRC-STEE-COL2-R24.rvt | Revit 2024 | Added manually |  | V1 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 724 MB | May 20, 2026 12:45 PM | 20/05/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/STEEL | CPQ11-STRC-STEE-COL3-R24.rvt | Revit 2024 | Added manually |  | V1 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 724.3 MB | May 20, 2026 2:16 PM | 20/05/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/STEEL | CPQ11-STRC-STEE-COL4-R24.rvt | Revit 2024 | Added manually |  | V1 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 661.3 MB | May 20, 2026 5:52 PM | 20/05/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/STEEL | CPQ11-STRC-STEE-COL5-R24.rvt | Revit 2024 | Added manually |  | V1 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 740.2 MB | May 20, 2026 5:51 PM | 20/05/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/STEEL | CPQ11-STRC-STEE-GUAR-R24.rvt | Revit 2024 | Added manually |  | V1 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 25.1 MB | May 20, 2026 3:49 PM | 20/05/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/STEEL | CPQ11-STRC-STEE-STIR-R24.rvt | Revit 2024 | Added manually |  | V1 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 103.7 MB | May 20, 2026 4:13 PM | 20/05/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/STEEL | CPQ11-STRC-STEE-UTLS-R24.rvt | Revit 2024 | Added manually |  | V1 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 101.8 MB | May 20, 2026 4:24 PM | 20/05/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/STEEL/IFC | 837-RACIONAL-PROJETO_GALILEU.zip |  |  |  | V1 | -- |  |  | -- | Not synced | -- | -- | 303.1 MB | May 21, 2026 5:25 PM | 21/05/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/STEEL/IFC | CPQ11-STRC-STEE-ADMN-2X3.ifc |  |  |  | V1 | -- |  |  | -- | Not synced | No published markups | No unresolved issues | 36.5 MB | May 21, 2026 5:25 PM | 21/05/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/STEEL/IFC | CPQ11-STRC-STEE-COL1-2X3.ifc |  |  |  | V1 | -- |  |  | -- | Not synced | No published markups | No unresolved issues | 84.9 MB | May 21, 2026 5:25 PM | 21/05/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/STEEL/IFC | CPQ11-STRC-STEE-COL2-2X3.ifc |  |  |  | V1 | -- |  |  | -- | Not synced | No published markups | No unresolved issues | 88.7 MB | May 21, 2026 5:25 PM | 21/05/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/STEEL/IFC | CPQ11-STRC-STEE-COL3-2X3.ifc |  |  |  | V1 | -- |  |  | -- | Not synced | No published markups | No unresolved issues | 88.9 MB | May 21, 2026 5:25 PM | 21/05/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/STEEL/IFC | CPQ11-STRC-STEE-COL4-2X3.ifc |  |  |  | V1 | -- |  |  | -- | Not synced | No published markups | No unresolved issues | 90.6 MB | May 21, 2026 5:25 PM | 21/05/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/STEEL/IFC | CPQ11-STRC-STEE-COL5-2X3.ifc |  |  |  | V1 | -- |  |  | -- | Not synced | No published markups | No unresolved issues | 92.9 MB | May 21, 2026 5:25 PM | 21/05/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/STEEL/IFC | CPQ11-STRC-STEE-GUAR-2X3.ifc |  |  |  | V1 | -- |  |  | -- | Not synced | No published markups | No unresolved issues | 4 MB | May 21, 2026 5:25 PM | 21/05/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/STEEL/IFC | CPQ11-STRC-STEE-STIR-2X3.ifc |  |  |  | V1 | -- |  |  | -- | Not synced | No published markups | No unresolved issues | 12.2 MB | May 21, 2026 5:25 PM | 21/05/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/STEEL/IFC | CPQ11-STRC-STEE-UTLS-2X3.ifc |  |  |  | V1 | -- |  |  | -- | Not synced | No published markups | No unresolved issues | 18.2 MB | May 21, 2026 5:25 PM | 21/05/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/STRC | CPQ11-STRC-CONC-DATA-R24.rvt | Revit 2024 | Added manually |  | V1 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 16.9 MB | May 15, 2026 8:51 AM | 15/05/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/STRC | CPQ11-STRC-CONC-SITE-R24.rvt | Revit 2024 | Added manually |  | V1 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 27.2 MB | May 15, 2026 8:52 AM | 15/05/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/STRC | CPQ11-STRC-DPFN-DATA-R24.rvt | Revit 2024 | Added manually |  | V1 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 11.8 MB | May 15, 2026 8:51 AM | 15/05/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/STRC | CPQ11-STRC-DPFN-SITE-R24.rvt | Revit 2024 | Added manually |  | V1 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 13.6 MB | May 15, 2026 8:51 AM | 15/05/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/STRC | CPQ11-STRC-FLOO-DATA-R24.rvt | Revit 2024 | Added manually |  | V3 | -- |  |  | -- | Sharing to | -- | -- | 122.5 MB | 2026-06-20 21:24 | 20/06/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/STRC | CPQ11-STRC-FLOO-SITE-R24.rvt | Revit 2024 | Added manually |  | V2 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 15.8 MB | May 26, 2026 11:37 AM | 26/05/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/STRC/NWC | CPQ11-STRC-CONC-DATA-R24.nwc |  |  |  | V1 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 476 KB | May 15, 2026 8:50 AM | 15/05/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/STRC/NWC | CPQ11-STRC-CONC-SITE-R24.nwc |  |  |  | V1 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 598.6 KB | May 15, 2026 8:50 AM | 15/05/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/STRC/NWC | CPQ11-STRC-DPFN-DATA-R24.nwc |  |  |  | V1 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 259.5 KB | May 15, 2026 8:50 AM | 15/05/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/STRC/NWC | CPQ11-STRC-DPFN-SITE-R24.nwc |  |  |  | V1 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 1.6 MB | May 15, 2026 8:50 AM | 15/05/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/STRC/NWC | CPQ11-STRC-FLOO-DATA-R24.nwc |  |  |  | V3 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 203.3 MB | 2026-06-20 19:45 | 20/06/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R24/STRC/NWC | CPQ11-STRC-FLOO-SITE-R24.nwc |  |  |  | V2 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 10.2 MB | May 26, 2026 11:36 AM | 26/05/2026

## R22 RELATÓRIO ACC
Folder name and path | Name | Software version | Model type | Description | Version number | Published to | Extracted to folder | Added to Packages | Publicly shared | Synced with Bridge | Markups | Issues | File size | Last updated | Last updated for control table
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/ARCH/NWC | CPQ11-ARCH-ARCH-DATA-R22.nwc |  |  |  | V27 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 7.1 MB | Apr 10, 2026 4:49 PM | 10/04/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/ARCH/NWC | CPQ11-ARCH-ARCH-SITE-R22.nwc |  |  |  | V28 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 1.8 MB | Apr 17, 2026 4:45 PM | 17/04/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/ARCH/NWC | CPQ11-ARCH-BLPR-GUAR-R22.nwc |  |  |  | V9 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 3.9 MB | Dec 4, 2025 6:42 AM | 04/12/2025
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/ARCH/NWC | CPQ11-ARCH-CEIL-DATA-R22.nwc |  |  |  | V4 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 5.3 MB | Apr 29, 2026 6:51 AM | 29/04/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/ARCH/NWC | CPQ11-ARCH-CEIL-SITE-R22.nwc |  |  |  | V3 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 21.9 KB | Apr 29, 2026 6:50 AM | 29/04/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/ARCH/NWC | CPQ11-ARCH-CHAI-SITE-R22.nwc |  |  |  | V11 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 11.5 MB | Apr 6, 2026 10:43 AM | 06/04/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/ARCH/NWC | CPQ11-ARCH-FACD-DATA-R22.nwc |  |  |  | V22 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 120.2 MB | Apr 10, 2026 5:50 PM | 10/04/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/ARCH/NWC | CPQ11-ARCH-HM90-DATA-R22.nwc |  |  |  | V8 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 305.7 KB | 2026-03-27 11:43 | 27/03/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/ARCH/NWC | CPQ11-ARCH-HMET-DATA-R22.nwc |  |  |  | V11 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 3.2 MB | Apr 8, 2026 8:02 AM | 08/04/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/ARCH/NWC | CPQ11-ARCH-HMET-SITE-R22.nwc |  |  |  | V9 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 737.3 KB | Apr 10, 2026 8:25 AM | 10/04/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/ARCH/NWC | CPQ11-ARCH-METL-SITE-R22.nwc |  |  |  | V11 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 162.6 MB | May 5, 2026 10:51 AM | 05/05/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/ARCH/NWC | CPQ11-ARCH-OHCD-DATA-R22.nwc |  |  |  | V4 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 229.3 KB | Apr 10, 2026 9:03 AM | 10/04/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/ARCH/NWC | CPQ11-ARCH-PART-C12A-R22.nwc |  |  |  | V20 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 5.2 MB | Apr 7, 2026 10:09 PM | 07/04/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/ARCH/NWC | CPQ11-ARCH-PART-C345-R22.nwc |  |  |  | V12 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 3.6 MB | 2026-01-30 11:47 | 30/01/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/ARCH/NWC | CPQ11-ARCH-PART-SITE-R22.nwc |  |  |  | V14 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 666.8 KB | 2026-03-18 10:16 | 18/03/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/ARCH/NWC | CPQ11-ARCH-ROOF-DATA-R22.nwc |  |  |  | V26 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 13.1 MB | 2026-03-26 17:41 | 26/03/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/ARCH/NWC | CPQ11-ARCH-SHLV-DATA-R22.nwc |  |  |  | V5 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 47.4 MB | 2025-11-09 19:56 | 09/11/2025
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/ARCH/NWC | CPQ11-ARCH-STON-SITE-R22.nwc |  |  |  | V2 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 390.9 KB | 2026-01-30 14:56 | 30/01/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/ARCH/NWC | CPQ11-ARCH-STON-SITE-R23.nwc |  |  |  | V7 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 5.1 KB | May 11, 2026 12:36 PM | 11/05/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/ARCH/NWC | CPQ11-ARCH-WMES-DATA-R22.nwc |  |  |  | V12 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 113.4 KB | 2026-01-23 11:53 | 23/01/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/ARCH/OBSOLET | CPQ11-ARCH-ARCH-DATA-R22.nwd |  |  |  | V1 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 10.4 MB | Feb 4, 2025 2:38 PM | 04/02/2025
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/ARCH/OBSOLET | CPQ11-ARCH-ARCH-SITE-R22.nwd |  |  |  | V1 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 142.2 MB | Feb 4, 2025 2:38 PM | 04/02/2025
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/ARCH/OBSOLET | CPQ11-ARCH-PART-CL030405-R22.rvt | Revit 2022 | Added manually |  | V9 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 88.3 MB | Feb 4, 2025 10:40 AM | 04/02/2025
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/ARCH/OBSOLET | CPQ11-ARCH-PART-CORE-R22.rvt | Revit 2022 | Added manually |  | V19 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 267.6 MB | Feb 4, 2025 10:40 AM | 04/02/2025
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/ARCH/OBSOLET | CPQ11-ARCH-R23.rvt | Revit 2022 | Added manually |  | V7 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 253.6 MB | Feb 4, 2025 10:41 AM | 04/02/2025
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/ARCH/OBSOLET | CPQ11-ARCH-ROOF-CORE-R22.nwc |  |  |  | V2 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 13 MB | Feb 4, 2025 10:39 AM | 04/02/2025
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/ARCH/OBSOLET | CPQ11-ARCH-ROOF-CORE-R22.rvt |  | Added manually |  | V11 | -- |  |  | -- | Sharing to | -- | -- | 19.3 MB | Feb 4, 2025 10:39 AM | 04/02/2025
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/ARCH/OBSOLET | CPQ11-ARCH-SITE-R23.rvt | Revit 2022 | Added manually |  | V2 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 247 MB | Feb 4, 2025 10:41 AM | 04/02/2025
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/ARCH/OBSOLET | CPQ11-RAC-ARCH-FACD-OMTR-R22.rvt | Revit 2022 | Added manually |  | V4 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 102.9 MB | Feb 4, 2025 10:40 AM | 04/02/2025
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/ARCH | CPQ11-ARCH-ARCH-DATA-R22.rvt | Revit 2022 | Added manually |  | V29 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 226.6 MB | Apr 13, 2026 6:05 PM | 13/04/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/ARCH | CPQ11-ARCH-ARCH-SITE-R22.rvt | Revit 2022 | Added manually |  | V28 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 74.1 MB | Apr 17, 2026 4:46 PM | 17/04/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/ARCH | CPQ11-ARCH-BLPR-GUAR-R22.rvt | Revit 2022 | Added manually |  | V9 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 38.2 MB | Dec 4, 2025 6:42 AM | 04/12/2025
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/ARCH | CPQ11-ARCH-CEIL-DATA-R22.rvt | Revit 2022 | Added manually |  | V4 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 168.5 MB | Apr 29, 2026 7:10 AM | 29/04/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/ARCH | CPQ11-ARCH-CEIL-SITE-R22.rvt | Revit 2022 | Added manually |  | V2 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 47.1 MB | Apr 29, 2026 6:54 AM | 29/04/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/ARCH | CPQ11-ARCH-CHAI-SITE-R22.rvt | Revit 2022 | Added manually |  | V12 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 9.9 MB | Apr 6, 2026 10:44 AM | 06/04/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/ARCH | CPQ11-ARCH-FACD-DATA-R22.rvt | Revit 2022 | Added manually |  | V25 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 128.4 MB | May 6, 2026 5:41 PM | 06/05/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/ARCH | CPQ11-ARCH-HM90-DATA-R22.rvt | Revit 2022 | Added manually |  | V9 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 25 MB | 2026-03-27 11:37 | 27/03/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/ARCH | CPQ11-ARCH-HMET-DATA-R22.rvt | Revit 2022 | Added manually |  | V12 | -- |  |  | -- | Sharing to | No published markups | 3 unresolved issues | 72.6 MB | Apr 8, 2026 8:06 AM | 08/04/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/ARCH | CPQ11-ARCH-HMET-SITE-R22.rvt | Revit 2022 | Added manually |  | V9 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 25.2 MB | Apr 10, 2026 8:28 AM | 10/04/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/ARCH | CPQ11-ARCH-METL-SITE-R22.rvt | Revit 2022 | Added manually |  | V12 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 35.6 MB | May 5, 2026 11:11 AM | 05/05/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/ARCH | CPQ11-ARCH-OHCD-DATA-R22.rvt | Revit 2022 | Added manually |  | V4 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 11 MB | Apr 10, 2026 8:59 AM | 10/04/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/ARCH | CPQ11-ARCH-PART-C12A-R22.rvt | Revit 2022 | Added manually |  | V24 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 112.4 MB | Apr 7, 2026 10:17 PM | 07/04/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/ARCH | CPQ11-ARCH-PART-C345-R22.rvt | Revit 2022 | Added manually |  | V14 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 105.8 MB | 2026-01-30 11:51 | 30/01/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/ARCH | CPQ11-ARCH-PART-SITE-R22.rvt | Revit 2022 | Added manually |  | V14 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 24.9 MB | 2026-03-18 10:17 | 18/03/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/ARCH | CPQ11-ARCH-ROOF-DATA-R22.rvt | Revit 2022 | Added manually |  | V30 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 20.9 MB | 2026-03-26 17:58 | 26/03/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/ARCH | CPQ11-ARCH-SHLV-DATA-R22.rvt | Revit 2022 | Added manually |  | V9 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 22.6 MB | Feb 28, 2026 8:25 PM | 28/02/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/ARCH | CPQ11-ARCH-STON-SITE-R23.ifc |  |  |  | V10 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 3.3 MB | May 11, 2026 12:33 PM | 11/05/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/ARCH | CPQ11-ARCH-STON-SITE-R23.rvt | Revit 2023 | Added manually |  | V10 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 9.7 MB | May 11, 2026 12:33 PM | 11/05/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/ARCH | CPQ11-ARCH-WMES-DATA-R22.rvt | Revit 2022 | Added manually |  | V13 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 14.9 MB | 2026-03-02 16:16 | 02/03/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/CIVIL/NWC | CPQ11-CIVL-DRNG-SITE-R22.nwc |  |  |  | V16 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 12 MB | May 6, 2026 8:32 AM | 06/05/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/CIVIL/NWC | CPQ11-CIVL-ERTH-SITE-R22.nwc |  |  |  | V16 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 1.4 MB | Apr 8, 2026 1:22 PM | 08/04/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/CIVIL/NWC | CPQ11-CIVL-LOCK-SITE-R22.nwc |  |  |  | V12 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 188.4 MB | 2026-03-21 10:42 | 21/03/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/CIVIL/NWC | CPQ11-CIVL-PAVM-SITE-R22.nwc |  |  |  | V15 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 14.4 MB | Apr 30, 2026 9:16 AM | 30/04/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/CIVIL | CPQ11-CIVL-DRNG-SITE-R22.rvt | Revit 2022 | Added manually |  | V20 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 82.7 MB | May 6, 2026 8:34 AM | 06/05/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/CIVIL | CPQ11-CIVL-ERTH-SITE-R22.rvt | Revit 2022 | Added manually |  | V18 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 17.4 MB | Apr 8, 2026 1:25 PM | 08/04/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/CIVIL | CPQ11-CIVL-LOCK-SITE-R22.rvt | Revit 2022 | Added manually |  | V11 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 327.2 MB | 2026-03-21 10:58 | 21/03/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/CIVIL | CPQ11-CIVL-PAVM-SITE-R22.rvt | Revit 2022 | Added manually |  | V18 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 49.5 MB | Apr 30, 2026 9:16 AM | 30/04/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/MECH/NWC | CPQ11-MECH-MECH-DATA-R22.nwc |  |  |  | V50 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 28.5 MB | Apr 17, 2026 3:28 PM | 17/04/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/MECH/NWC | CPQ11-MECH-MECH-GUAR-R22.nwc |  |  |  | V23 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 1.2 MB | Apr 16, 2026 9:16 AM | 16/04/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/MECH/NWC | CPQ11-PLMB-METK-UTLS-R22.nwc |  |  |  | V23 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 3.1 MB | Feb 26, 2026 5:40 PM | 26/02/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/MECH/NWC | CPQ11-PLMB-NPWT-DATA-R22.nwc |  |  |  | V35 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 12.9 MB | Apr 30, 2026 5:21 PM | 30/04/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/MECH/NWC | CPQ11-PLMB-NPWT-SITE-R22.nwc |  |  |  | V41 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 5.4 MB | Apr 24, 2026 2:44 PM | 24/04/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/MECH/OBSOLET | CPQ11-MECH-GENL-R22.nwc |  |  |  | V1 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 24.9 MB | Dec 17, 2024 6:31 PM | 17/12/2024
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/MECH/OBSOLET | CPQ11-MECH-GENL-R22.rvt | Revit 2022 | Added manually |  | V12 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 135.5 MB | Dec 17, 2024 6:31 PM | 17/12/2024
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/MECH/OBSOLET | CPQ11-MECH-MECH-DATA-R22.nwc |  |  |  | V1 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 30.5 MB | Apr 16, 2025 6:20 PM | 16/04/2025
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/MECH/OBSOLET | CPQ11-MECH-MECH-GUAR-R22.nwc |  |  |  | V1 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 1.3 MB | Apr 16, 2025 6:17 PM | 16/04/2025
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/MECH/OBSOLET | CPQ11-PLMB-GENL-R22.nwc |  |  |  | V1 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 6.1 MB | Dec 19, 2024 10:08 AM | 19/12/2024
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/MECH/OBSOLET | CPQ11-PLMB-GENL-R22.rvt | Revit 2022 | Added manually |  | V7 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 105.6 MB | Dec 19, 2024 10:07 AM | 19/12/2024
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/MECH/OBSOLET | CPQ11-PLMB-METK-UTLS-R22.nwc |  |  |  | V1 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 3.1 MB | Apr 16, 2025 6:17 PM | 16/04/2025
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/MECH/OBSOLET | CPQ11-PLMB-NPWT-DATA-R22.nwc |  |  |  | V1 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 10.8 MB | Apr 16, 2025 6:17 PM | 16/04/2025
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/MECH/OBSOLET | CPQ11-PLMB-NPWT-SITE-R22.nwc |  |  |  | V1 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 5.4 MB | Apr 16, 2025 6:17 PM | 16/04/2025
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/MECH/OBSOLET | CPQ11-PLMB-SITE-R22.nwc |  |  |  | V1 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 19.2 MB | Dec 18, 2024 10:34 AM | 18/12/2024
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/MECH/OBSOLET | CPQ11-PLMB-SITE-R22.rvt | Revit 2022 | Added manually |  | V7 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 100.7 MB | Dec 18, 2024 10:34 AM | 18/12/2024
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/MECH | CPQ11-MECH-MECH-DATA-R22.rvt | Revit 2022 | Added manually |  | V59 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 168.9 MB | Apr 17, 2026 3:44 PM | 17/04/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/MECH | CPQ11-MECH-MECH-GUAR-R22.rvt | Revit 2022 | Added manually |  | V23 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 118.5 MB | Apr 16, 2026 9:15 AM | 16/04/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/MECH | CPQ11-PLMB-METK-UTLS-R22.rvt | Revit 2022 | Added manually |  | V28 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 60.5 MB | Feb 26, 2026 5:41 PM | 26/02/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/MECH | CPQ11-PLMB-NPWT-DATA-R22.rvt | Revit 2022 | Added manually |  | V39 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 157.3 MB | Apr 30, 2026 5:57 PM | 30/04/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/MECH | CPQ11-PLMB-NPWT-SITE-R22.rvt | Revit 2022 | Added manually |  | V46 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 123 MB | Apr 24, 2026 2:45 PM | 24/04/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/MEP/NWC | CPQ11-BASM-DEVS-DATA-R22.nwc |  |  |  | V18 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 1.6 MB | May 5, 2026 4:01 PM | 05/05/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/MEP/NWC | CPQ11-BASM-DEVS-PUMP-R22.nwc |  |  |  | V13 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 827.9 KB | Feb 3, 2026 4:35 PM | 03/02/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/MEP/NWC | CPQ11-BASM-INFR-DATA-R22.nwc |  |  |  | V30 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 41.6 MB | 2026-03-04 14:51 | 04/03/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/MEP/NWC | CPQ11-BASM-INFR-PUMP-R22.nwc |  |  |  | V29 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 1.2 MB | Apr 24, 2026 11:18 AM | 24/04/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/MEP/NWC | CPQ11-DALI-DEVS-DATA-R22.nwc |  |  |  | V12 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 2.2 MB | Apr 15, 2026 5:53 PM | 15/04/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/MEP/NWC | CPQ11-DASM-DEVS-DATA-R22.nwc |  |  |  | V16 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 33.5 MB | Apr 27, 2026 6:14 PM | 27/04/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/MEP/NWC | CPQ11-ELEC-ELEC-DATA-R22.nwc |  |  |  | V41 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 194.9 MB | Apr 13, 2026 4:58 PM | 13/04/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/MEP/NWC | CPQ11-ELEC-ELEC-SITE-R22.nwc |  |  |  | V26 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 168.4 MB | Dec 23, 2025 12:43 PM | 23/12/2025
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/MEP/NWC | CPQ11-ELEC-SPDA-DATA-R22.nwc |  |  |  | V13 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 47.1 MB | May 12, 2026 9:35 AM | 12/05/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/MEP/NWC | CPQ11-ELEC-SPDA-SITE-R22.nwc |  |  |  | V7 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 1.2 MB | Dec 8, 2025 12:09 PM | 08/12/2025
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/MEP/NWC | CPQ11-EPMS-DEVS-DATA-R22.nwc |  |  |  | V14 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 84.4 KB | Apr 27, 2026 10:44 PM | 27/04/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/MEP/NWC | CPQ11-EPMS-DEVS-SITE-R22.nwc |  |  |  | V10 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 84.2 KB | Feb 3, 2026 4:34 PM | 03/02/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/MEP/NWC | CPQ11-FALM-FALM-DATA-R22.nwc |  |  |  | V18 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 45.6 MB | May 15, 2026 4:56 PM | 15/05/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/MEP/NWC | CPQ11-FALM-FALM-SITE-R22.nwc |  |  |  | V12 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 7.2 MB | May 8, 2026 8:49 AM | 08/05/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/MEP/NWC | CPQ11-FPRT-FPRT-DATA-R22.nwc |  |  |  | V15 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 119 MB | May 14, 2026 10:42 AM | 14/05/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/MEP/NWC | CPQ11-FPRT-FPRT-SITE-R22.nwc |  |  |  | V14 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 19.7 MB | May 14, 2026 10:42 AM | 14/05/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/MEP/NWC | CPQ11-FPRT-METK-UTLS-R22.nwc |  |  |  | V14 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 1.6 MB | 2026-01-15 15:21 | 15/01/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/MEP/NWC | CPQ11-PLMB-DIES-SITE-R22.nwc |  |  |  | V13 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 4.7 MB | 2026-03-03 08:47 | 03/03/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/MEP/NWC | CPQ11-PLMB-PLMB-DATA-R22.nwc |  |  |  | V29 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 31 MB | 2026-03-24 19:35 | 24/03/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/MEP/NWC | CPQ11-PLMB-PLMB-SITE-R22.nwc |  |  |  | V26 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 34.2 MB | Apr 8, 2026 10:56 AM | 08/04/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/MEP/NWC | CPQ11-ROIP-DEVS-DATA-R22.nwc |  |  |  | V36 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 55 MB | May 8, 2026 3:07 PM | 08/05/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/MEP/NWC | CPQ11-ROIP-DEVS-GUAR-R22.nwc |  |  |  | V10 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 2.3 MB | May 13, 2026 3:04 PM | 13/05/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/MEP/NWC | CPQ11-SCTY-DEVS-DATA-R22.nwc |  |  |  | V45 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 4.8 MB | May 6, 2026 9:07 AM | 06/05/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/MEP/NWC | CPQ11-SCTY-DEVS-SITE-R22.nwc |  |  |  | V38 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 4.1 MB | Apr 10, 2026 4:37 PM | 10/04/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/MEP/NWC | CPQ11-SCTY-GATE-SITE-R24.nwc |  |  |  | V2 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 4.7 MB | May 7, 2026 5:21 PM | 07/05/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/MEP/NWC | CPQ11-SCTY-INFR-DATA-R22.nwc |  |  |  | V36 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 36.5 MB | 2026-03-19 16:05 | 19/03/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/MEP/NWC | CPQ11-SCTY-INFR-SITE-R22.nwc |  |  |  | V30 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 883.5 KB | May 5, 2026 10:22 AM | 05/05/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/MEP/NWC | CPQ11-SYST-INFR-DATA-R22.nwc |  |  |  | V35 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 63.5 MB | Apr 10, 2026 4:17 PM | 10/04/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/MEP/NWC | CPQ11-SYST-INFR-SITE-R22.nwc |  |  |  | V35 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 166.6 MB | May 12, 2026 9:50 AM | 12/05/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/MEP/NWC | CPQ11-TCOM-DEVS-DATA-R22.nwc |  |  |  | V17 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 6.5 MB | Apr 27, 2026 10:44 PM | 27/04/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/MEP/NWC | CPQ11-TCOM-DEVS-SITE-R22.nwc |  |  |  | V13 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 221.9 KB | Apr 29, 2026 4:50 PM | 29/04/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/MEP/OBSOLET | CPQ11-BAS-R22.rvt | Revit 2022 | Added manually |  | V8 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 119.8 MB | Dec 13, 2024 2:45 PM | 13/12/2024
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/MEP/OBSOLET | CPQ11-ELEC-R22.nwc |  |  |  | V1 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 125.5 MB | Dec 18, 2024 10:36 AM | 18/12/2024
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/MEP/OBSOLET | CPQ11-ELEC-R22.rvt | Revit 2022 | Added manually |  | V10 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 360 MB | Dec 18, 2024 10:36 AM | 18/12/2024
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/MEP/OBSOLET | CPQ11-ELEC-SITE-R22.nwc |  |  |  | V1 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 155.7 MB | Dec 18, 2024 10:36 AM | 18/12/2024
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/MEP/OBSOLET | CPQ11-ELEC-SITE-R22.rvt | Revit 2022 | Added manually |  | V9 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 52.1 MB | Dec 18, 2024 10:36 AM | 18/12/2024
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/MEP/OBSOLET | CPQ11-FALM-R22.rvt | Revit 2022 | Added manually |  | V4 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 32.6 MB | 2025-01-10 16:00 | 10/01/2025
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/MEP/OBSOLET | CPQ11-FPRT-R22.rvt | Revit 2022 | Added manually |  | V3 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 197.6 MB | Dec 19, 2024 11:31 AM | 19/12/2024
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/MEP/OBSOLET | CPQ11-FPRT-SITE-R22.rvt | Revit 2022 | Added manually |  | V4 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 68.3 MB | Dec 19, 2024 11:32 AM | 19/12/2024
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/MEP/OBSOLET | CPQ11-FRPT-METK-UTLS-R22.nwc |  |  |  | V2 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 1.7 MB | 2025-03-17 10:57 | 17/03/2025
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/MEP/OBSOLET | CPQ11-FRPT-METK-UTLS-R22.rvt | Revit 2022 | Added manually |  | V5 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 8.4 MB | 2025-01-30 12:11 | 30/01/2025
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/MEP/OBSOLET | CPQ11-FRPT-METK-UTLS_-R22.rvt | Revit 2022 | Added manually |  | V2 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 8.4 MB | 2025-03-17 11:00 | 17/03/2025
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/MEP/OBSOLET | CPQ11-PLMB-R22.rvt | Revit 2022 | Added manually |  | V8 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 148.6 MB | Dec 19, 2024 10:09 AM | 19/12/2024
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/MEP/OBSOLET | CPQ11-PLMB-SITE-R22.nwc |  |  |  | V1 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 37.7 MB | Dec 19, 2024 10:10 AM | 19/12/2024
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/MEP/OBSOLET | CPQ11-PLMB-SITE-R22.rvt | Revit 2022 | Added manually |  | V8 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 105.4 MB | Dec 19, 2024 10:09 AM | 19/12/2024
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/MEP/OBSOLET | CPQ11-SCTY-R22.nwc |  |  |  | V1 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 29.6 MB | Dec 19, 2024 10:09 AM | 19/12/2024
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/MEP/OBSOLET | CPQ11-SCTY-R22.rvt | Revit 2022 | Added manually |  | V8 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 79.4 MB | Dec 19, 2024 10:09 AM | 19/12/2024
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/MEP/OBSOLET | CPQ11-SECURITY-SITE-R22.ifc |  |  |  | V2 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 66.7 MB | May 13, 2026 3:35 PM | 13/05/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/MEP/OBSOLET | CPQ11-SECURITY-SITE-R22.rvt | Revit 2024 | Added manually |  | V2 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 48.3 MB | May 13, 2026 3:35 PM | 13/05/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/MEP/OBSOLET | CPQ11-TCOM-INFR-DATA-R22.nwc |  |  |  | V3 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 88 MB | 2025-01-10 16:00 | 10/01/2025
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/MEP/OBSOLET | CPQ11-TCOM-INFR-DATA-R22.rvt | Revit 2022 | Added manually |  | V4 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 303.2 MB | 2025-01-10 16:00 | 10/01/2025
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/MEP/OBSOLET | CPQ11-TCOM-INFR-SITE-R22.nwc |  |  |  | V3 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 162 MB | 2025-01-10 16:00 | 10/01/2025
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/MEP/OBSOLET | CPQ11-TCOM-INFR-SITE-R22.rvt | Revit 2022 | Added manually |  | V3 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 295.1 MB | 2025-01-10 16:00 | 10/01/2025
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/MEP/OBSOLET | CPQ11-TCOM-R22.nwc |  |  |  | V1 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 249.3 MB | Dec 19, 2024 10:09 AM | 19/12/2024
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/MEP/OBSOLET | CPQ11-TCOM-R22.rvt | Revit 2022 | Added manually |  | V8 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 309.4 MB | Dec 19, 2024 10:09 AM | 19/12/2024
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/MEP | CPQ11-BASM-DEVS-DATA-R22.rvt | Revit 2022 | Added manually |  | V20 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 51.5 MB | May 5, 2026 4:01 PM | 05/05/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/MEP | CPQ11-BASM-DEVS-PUMP-R22.rvt | Revit 2022 | Added manually |  | V14 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 37.9 MB | Feb 3, 2026 4:35 PM | 03/02/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/MEP | CPQ11-BASM-INFR-DATA-R22.rvt | Revit 2022 | Added manually |  | V33 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 52.4 MB | 2026-03-04 14:56 | 04/03/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/MEP | CPQ11-BASM-INFR-PUMP-R22.rvt | Revit 2022 | Added manually |  | V32 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 32.4 MB | Apr 24, 2026 11:20 AM | 24/04/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/MEP | CPQ11-DALI-DEVS-DATA-R22.rvt | Revit 2022 | Added manually |  | V15 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 206.5 MB | Apr 15, 2026 6:03 PM | 15/04/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/MEP | CPQ11-DASM-DEVS-DATA-R22.rvt | Revit 2022 | Added manually |  | V28 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 328.1 MB | Apr 16, 2026 10:45 AM | 16/04/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/MEP | CPQ11-ELEC-ELEC-DATA-R22.rvt |  | Added manually |  | V52 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 282.7 MB | Apr 30, 2026 11:36 PM | 30/04/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/MEP | CPQ11-ELEC-ELEC-SITE-R22.rvt | Revit 2022 | Added manually |  | V33 | -- |  |  | -- | Sharing to | No published markups | 1 unresolved issue | 46.7 MB | 2026-03-05 06:08 | 05/03/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/MEP | CPQ11-ELEC-SPDA-DATA-R22.rvt | Revit 2022 | Added manually |  | V13 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 98.2 MB | May 12, 2026 9:41 AM | 12/05/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/MEP | CPQ11-ELEC-SPDA-SITE-R22.rvt | Revit 2022 | Added manually |  | V7 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 69.3 MB | Dec 8, 2025 12:09 PM | 08/12/2025
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/MEP | CPQ11-EPMS-DEVS-DATA-R22.rvt | Revit 2022 | Added manually |  | V15 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 23.2 MB | Apr 27, 2026 10:43 PM | 27/04/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/MEP | CPQ11-EPMS-DEVS-SITE-R22.rvt | Revit 2022 | Added manually |  | V11 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 14.8 MB | Feb 3, 2026 4:36 PM | 03/02/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/MEP | CPQ11-FALM-FALM-DATA-R22.rvt | Revit 2024 | Added manually |  | V24 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 52.3 MB | May 15, 2026 5:02 PM | 15/05/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/MEP | CPQ11-FALM-FALM-SITE-R22.rvt | Revit 2022 | Added manually |  | V11 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 19.3 MB | May 8, 2026 8:46 AM | 08/05/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/MEP | CPQ11-FPRT-FPRT-DATA-R22.rvt | Revit 2022 | Added manually |  | V17 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 136.1 MB | May 14, 2026 11:16 AM | 14/05/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/MEP | CPQ11-FPRT-FPRT-SITE-R22.rvt | Revit 2022 | Added manually |  | V16 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 106.9 MB | May 14, 2026 10:48 AM | 14/05/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/MEP | CPQ11-FPRT-METK-UTLS-R22.rvt | Revit 2022 | Added manually |  | V16 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 9.9 MB | 2026-03-06 17:05 | 06/03/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/MEP | CPQ11-PLMB-DIES-SITE-R22.rvt | Revit 2022 | Added manually |  | V14 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 13.2 MB | 2026-03-03 08:52 | 03/03/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/MEP | CPQ11-PLMB-PLMB-DATA-R22.rvt | Revit 2022 | Added manually |  | V30 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 123.7 MB | 2026-03-24 19:40 | 24/03/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/MEP | CPQ11-PLMB-PLMB-SITE-R22.rvt | Revit 2022 | Added manually |  | V27 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 61.4 MB | Apr 8, 2026 11:01 AM | 08/04/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/MEP | CPQ11-ROIP-DEVS-DATA-R22.rvt | Revit 2022 | Added manually |  | V36 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 692.6 MB | May 8, 2026 3:16 PM | 08/05/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/MEP | CPQ11-ROIP-DEVS-GUAR-R22.rvt | Revit 2022 | Added manually |  | V12 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 38 MB | May 13, 2026 3:04 PM | 13/05/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/MEP | CPQ11-SCTY-DEVS-DATA-R22.rvt | Revit 2022 | Added manually |  | V40 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 208.4 MB | May 6, 2026 9:11 AM | 06/05/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/MEP | CPQ11-SCTY-DEVS-SITE-R22.rvt | Revit 2022 | Added manually |  | V37 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 222.7 MB | Apr 10, 2026 4:38 PM | 10/04/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/MEP | CPQ11-SCTY-GATE-SITE-R24.ifc |  |  |  | V2 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 48 MB | May 7, 2026 5:22 PM | 07/05/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/MEP | CPQ11-SCTY-GATE-SITE-R24.rvt | Revit 2024 | Added manually |  | V2 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 37.3 MB | May 7, 2026 5:22 PM | 07/05/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/MEP | CPQ11-SCTY-INFR-DATA-R22.rvt | Revit 2022 | Added manually |  | V39 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 43.3 MB | 2026-03-19 16:08 | 19/03/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/MEP | CPQ11-SCTY-INFR-SITE-R22.rvt | Revit 2022 | Added manually |  | V34 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 25.4 MB | May 5, 2026 10:22 AM | 05/05/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/MEP | CPQ11-SYST-INFR-DATA-R22.rvt | Revit 2022 | Added manually |  | V40 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 105.8 MB | Apr 10, 2026 4:26 PM | 10/04/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/MEP | CPQ11-SYST-INFR-SITE-R22.rvt | Revit 2022 | Added manually |  | V39 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 42.9 MB | May 12, 2026 9:54 AM | 12/05/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/MEP | CPQ11-TCOM-DEVS-DATA-R22.rvt | Revit 2022 | Added manually |  | V18 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 98.9 MB | Apr 30, 2026 3:43 PM | 30/04/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/MEP | CPQ11-TCOM-DEVS-SITE-R22.rvt | Revit 2022 | Added manually |  | V14 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 38.5 MB | Apr 29, 2026 4:52 PM | 29/04/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/STEEL STRUCTURE/IFC | 837-RACIONAL-PROJETO_GALILEU.zip |  |  |  | V2 | -- |  |  | -- | Sharing to | -- | -- | 303.1 MB | 2025-06-03 07:38 | 03/06/2025
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/STEEL STRUCTURE/IFC | CPQ11-STRC-STEE-ADMN-2X3.ifc |  |  |  | V8 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 36.5 MB | 2025-11-07 11:49 | 07/11/2025
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/STEEL STRUCTURE/IFC | CPQ11-STRC-STEE-COL1-2X3.ifc |  |  |  | V7 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 84.9 MB | 2025-11-07 11:56 | 07/11/2025
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/STEEL STRUCTURE/IFC | CPQ11-STRC-STEE-COL2-2X3.ifc |  |  |  | V6 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 88.7 MB | 2025-11-07 11:54 | 07/11/2025
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/STEEL STRUCTURE/IFC | CPQ11-STRC-STEE-COL3-2X3.ifc |  |  |  | V6 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 88.9 MB | 2025-11-07 11:56 | 07/11/2025
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/STEEL STRUCTURE/IFC | CPQ11-STRC-STEE-COL4-2X3.ifc |  |  |  | V7 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 90.6 MB | Dec 5, 2025 5:25 PM | 05/12/2025
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/STEEL STRUCTURE/IFC | CPQ11-STRC-STEE-COL5-2X3.ifc |  |  |  | V6 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 92.9 MB | 2025-11-07 11:56 | 07/11/2025
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/STEEL STRUCTURE/IFC | CPQ11-STRC-STEE-GUAR-2X3.ifc |  |  |  | V6 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 4 MB | 2025-11-01 09:45 | 01/11/2025
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/STEEL STRUCTURE/IFC | CPQ11-STRC-STEE-STIR-2X3.ifc |  |  |  | V3 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 12.2 MB | Oct 31, 2025 2:29 PM | 31/10/2025
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/STEEL STRUCTURE/IFC | CPQ11-STRC-STEE-UTLS-2X3.ifc |  |  |  | V6 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 18.2 MB | Feb 11, 2026 11:20 AM | 11/02/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/STEEL STRUCTURE/IFC | CPQ11-STRC-STEE-UTLS-2X3.ifc.log |  |  |  | V1 | -- |  |  | -- | Sharing to | -- | -- | 1.3 KB | Feb 12, 2026 2:44 PM | 12/02/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/STEEL STRUCTURE/IFC | CPQ11-STRC-STEE-UTLS-2X3.ifc.RVT | Revit 2022 | Added manually |  | V1 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 98.5 MB | Feb 12, 2026 2:52 PM | 12/02/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/STEEL STRUCTURE/IFC | CPQ11-STRC-STEE-UTLS-2X3.ifc.sharedparameters.txt |  |  |  | V3 | -- |  |  | -- | Sharing to | -- | -- | 10.4 KB | Feb 12, 2026 2:46 PM | 12/02/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/STEEL STRUCTURE/OBSOLET | CPQ11-STRC-STEE-ADMN-2X3.ifc |  |  |  | V1 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 33.2 MB | Feb 19, 2025 2:46 PM | 19/02/2025
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/STEEL STRUCTURE/OBSOLET | CPQ11-STRC-STEE-COL1-2X3.ifc |  |  |  | V2 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 64.7 MB | Feb 19, 2025 2:46 PM | 19/02/2025
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/STEEL STRUCTURE/OBSOLET | CPQ11-STRC-STEE-COL2-2X3.ifc |  |  |  | V1 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 76.7 MB | Feb 19, 2025 2:46 PM | 19/02/2025
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/STEEL STRUCTURE/OBSOLET | CPQ11-STRC-STEE-COL3-2X3.ifc |  |  |  | V1 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 76.7 MB | Feb 19, 2025 2:46 PM | 19/02/2025
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/STEEL STRUCTURE/OBSOLET | CPQ11-STRC-STEE-COL4-2X3.ifc |  |  |  | V1 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 66.6 MB | Feb 19, 2025 2:46 PM | 19/02/2025
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/STEEL STRUCTURE/OBSOLET | CPQ11-STRC-STEE-COL5-2X3.ifc |  |  |  | V2 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 80.3 MB | Feb 19, 2025 2:46 PM | 19/02/2025
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/STEEL STRUCTURE/OBSOLET | CPQ11-STRC-STEE-ESCA-2X3.ifc |  |  |  | V1 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 11.4 MB | 2025-07-03 16:05 | 03/07/2025
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/STEEL STRUCTURE/OBSOLET | CPQ11-STRC-STEE-GUAR-2X3.00.ifc |  |  |  | V1 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 3.4 MB | May 8, 2025 12:11 PM | 08/05/2025
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/STEEL STRUCTURE/OBSOLET | CPQ11-STRC-STEE-GUAR-2X3.ifc |  |  |  | V1 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 27.2 MB | May 8, 2025 12:11 PM | 08/05/2025
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/STEEL STRUCTURE/OBSOLET | CPQ11-STRC-STEE-UTIL-2X3.ifc |  |  |  | V1 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 17.4 MB | 2025-07-03 16:05 | 03/07/2025
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/STEEL STRUCTURE/OBSOLET | CPQ11-STRC-STEE-UTLS-2X3.ifc |  |  |  | V1 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 27.2 MB | Feb 19, 2025 2:46 PM | 19/02/2025
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/STEEL STRUCTURE/OBSOLET | CPQ11-STRC-STEEL-ADMN-IFC.ifc |  |  |  | V1 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 46.1 MB | 2025-01-07 10:48 | 07/01/2025
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/STEEL STRUCTURE/OBSOLET | CPQ11-STRC-STEEL-ANEX-IFC.ifc |  |  |  | V1 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 17.1 MB | Dec 18, 2024 2:18 PM | 18/12/2024
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/STEEL STRUCTURE/OBSOLET | CPQ11-STRC-STEEL-ANEXO-03-12-2024.ifc |  |  |  | V1 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 18.2 MB | Dec 18, 2024 2:18 PM | 18/12/2024
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/STEEL STRUCTURE/OBSOLET | CPQ11-STRC-STEEL-COL1.ifc |  |  |  | V1 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 48.9 MB | 2025-01-07 10:47 | 07/01/2025
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/STEEL STRUCTURE/OBSOLET | CPQ11-STRC-STEEL-COL2-IFC.ifc |  |  |  | V1 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 40.2 MB | 2025-01-07 10:46 | 07/01/2025
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/STEEL STRUCTURE/OBSOLET | CPQ11-STRC-STEEL-COL3-IFC.ifc |  |  |  | V1 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 40.2 MB | 2025-01-07 10:46 | 07/01/2025
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/STEEL STRUCTURE/OBSOLET | CPQ11-STRC-STEEL-COL4-IFC.ifc |  |  |  | V1 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 32.8 MB | 2025-01-07 10:47 | 07/01/2025
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/STEEL STRUCTURE/OBSOLET | CPQ11-STRC-STEEL-COL5-IFC.ifc |  |  |  | V1 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 41.4 MB | 2025-01-07 10:47 | 07/01/2025
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/STEEL STRUCTURE/OBSOLET | CPQ11-STRC-STEEL-GNRL-IFC.ifc |  |  |  | V2 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 170.7 MB | Dec 18, 2024 2:18 PM | 18/12/2024
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/STEEL STRUCTURE/OBSOLET | CPQ11-STRC-STEEL-PROJETO-GALILEU-COMPLETO-14-11-2024.ifc |  |  |  | V1 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 270.5 MB | Dec 18, 2024 2:18 PM | 18/12/2024
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/STEEL STRUCTURE/OBSOLET | CPQ11-STRC-STEEL-PROJETO-GALILEU-COMPLETO.ifc |  |  |  | V1 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 271.2 MB | Dec 18, 2024 2:18 PM | 18/12/2024
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/STEEL STRUCTURE/OBSOLET | PLAT.GERADORES.ifc |  |  |  | V1 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 48.3 MB | Dec 18, 2024 2:18 PM | 18/12/2024
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/STEEL STRUCTURE/OBSOLET | TORRE DE ESCADA 29-07-2024.ifc |  |  |  | V1 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 8.4 MB | Dec 18, 2024 2:18 PM | 18/12/2024
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/STEEL STRUCTURE | CPQ11-STRC-STEE-ADMN-R22.RVT | Revit 2022 | Added manually |  | V8 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 211.8 MB | 2025-11-04 14:44 | 04/11/2025
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/STEEL STRUCTURE | CPQ11-STRC-STEE-COL1-R22.RVT | Revit 2022 | Added manually |  | V9 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 642 MB | 2025-11-12 14:56 | 12/11/2025
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/STEEL STRUCTURE | CPQ11-STRC-STEE-COL2-R22.RVT | Revit 2022 | Added manually |  | V8 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 717.7 MB | 2025-11-12 15:09 | 12/11/2025
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/STEEL STRUCTURE | CPQ11-STRC-STEE-COL3-R22.RVT | Revit 2022 | Added manually |  | V8 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 719.2 MB | 2025-11-12 15:05 | 12/11/2025
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/STEEL STRUCTURE | CPQ11-STRC-STEE-COL4-R22.RVT | Revit 2022 | Added manually |  | V9 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 656.1 MB | Dec 17, 2025 5:21 PM | 17/12/2025
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/STEEL STRUCTURE | CPQ11-STRC-STEE-COL5-R22.RVT | Revit 2022 | Added manually |  | V8 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 734.7 MB | 2025-11-12 15:13 | 12/11/2025
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/STEEL STRUCTURE | CPQ11-STRC-STEE-GUAR-R22.RVT | Revit 2022 | Added manually |  | V9 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 24.3 MB | 2025-11-04 14:38 | 04/11/2025
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/STEEL STRUCTURE | CPQ11-STRC-STEE-STIR-R22.RVT | Revit 2022 | Added manually |  | V7 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 102.2 MB | 2025-11-04 14:40 | 04/11/2025
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/STEEL STRUCTURE | CPQ11-STRC-STEE-UTLS-R22.RVT | Revit 2022 | Added manually |  | V10 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 99.9 MB | Feb 13, 2026 10:27 AM | 13/02/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/STRC/NWC | CPQ11-STRC-CONC-DATA-R22.nwc |  |  |  | V10 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 472.5 KB | Apr 22, 2026 11:13 AM | 22/04/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/STRC/NWC | CPQ11-STRC-CONC-SITE-R22.nwc |  |  |  | V17 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 586.2 KB | May 12, 2026 10:53 AM | 12/05/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/STRC/NWC | CPQ11-STRC-DPFN-DATA-R22.nwc |  |  |  | V11 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 265.4 KB | Apr 28, 2026 11:32 AM | 28/04/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/STRC/NWC | CPQ11-STRC-DPFN-SITE-R22.nwc |  |  |  | V13 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 1.6 MB | May 12, 2026 10:53 AM | 12/05/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/STRC/NWC | CPQ11-STRC-FLOO-DATA-R22.nwc |  |  |  | V1 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 2.8 GB | May 5, 2026 5:24 PM | 05/05/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/STRC/NWC | CPQ11-STRC-FLOO-SITE-R22.nwc |  |  |  | V1 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 53.7 MB | May 5, 2026 2:44 PM | 05/05/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/STRC | CPQ11-STRC-CONC-DATA-R22.rvt | Revit 2022 | Added manually |  | V10 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 16.6 MB | Apr 22, 2026 11:16 AM | 22/04/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/STRC | CPQ11-STRC-CONC-SITE-R22.rvt | Revit 2022 | Added manually |  | V17 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 27.3 MB | May 12, 2026 10:55 AM | 12/05/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/STRC | CPQ11-STRC-DPFN-DATA-R22.rvt | Revit 2022 | Added manually |  | V11 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 11.5 MB | Apr 28, 2026 11:33 AM | 28/04/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/STRC | CPQ11-STRC-DPFN-SITE-R22.rvt | Revit 2022 | Added manually |  | V13 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 13.7 MB | May 12, 2026 10:53 AM | 12/05/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/STRC | CPQ11-STRC-FLOO-DATA-R22.rvt | Revit 2022 | Added manually |  | V1 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 130.4 MB | May 5, 2026 5:51 PM | 05/05/2026
01-WORK IN PROGRESS/BIM/MODELS/DELEGATED DESIGN R22/STRC | CPQ11-STRC-FLOO-SITE-R22.rvt | Revit 2022 | Added manually |  | V1 | -- |  |  | -- | Sharing to | No published markups | No unresolved issues | 16.8 MB | May 5, 2026 2:44 PM | 05/05/2026

## PLANEJAMENTO INICIAL
| FILE NAME | AREA | TRADE COMPANY | CODE | BIM COMPANY | CODE | ACC VERSION | ACC FILE DATE | RESPONSÁVEL UTILITIES | UTILITIES ESTIMATED DELIVERY | RESPONSÁVEL ADMN | ADMN ESTIMATED DELIVERY | RESPONSÁVEL COLO1 + GUARDHOUSE | COLO1 ESTIMATED DELIVERY
ARCH ¦ ARCHITECTURE
1 | CPQ11-ARCH-ARCH-DATA-R22.rvt | DATA | ARE ARQUITETURA | 1130 | ARE ARQUITETURA | 1130 | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | GUI | 2025-12-12 | RESPONSAVEL | 2025-12-17
2 | CPQ11-ARCH-ARCH-SITE-R22.rvt | SITE | ARE ARQUITETURA | 1130 | ARE ARQUITETURA | 1130 | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | N/A | 2025-12-10 | RESPONSAVEL | 2025-12-17 | APROVADO
3 | CPQ11-ARCH-FNSH-DATA-R22.rvt | DATA | MENDES HOLLER, IDEIA, SERV OBRAS | 1111 | ARE ARQUITETURA | 1130 | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | N/A | N/A | N/A | N/A
4 | CPQ11-ARCH-FNSH-SITE-R22.rvt | SITE | MENDES HOLLER, IDEIA, SERV OBRAS | 1111 | ARE ARQUITETURA | 1130 | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | N/A | N/A | N/A | N/A
5 | CPQ11-ARCH-ALUF-DATA-R22.rvt | DATA | SMVIDROS | 1102 | ARE ARQUITETURA | 1130 | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | N/A | N/A | N/A | N/A
6 | CPQ11-ARCH-ALUF-SITE-R22.rvt | SITE | SMVIDROS | 1102 | ARE ARQUITETURA | 1130 | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | N/A | N/A | N/A | N/A
7 | CPQ11-ARCH-FENC-SITE-R22.rvt | SITE | SERCOP | 1103 | ARE ARQUITETURA | 1130 | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | N/A | N/A | N/A | N/A
8 | CPQ11-ARCH-METL-SITE-R22.rvt | SITE | SERCOP | 1103 | ARE ARQUITETURA | 1130 | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | N/A | 2025-12-10 | RESPONSAVEL | 2025-12-17
9 | CPQ11-ARCH-WOOD-DATA-R22.rvt | DATA | MADEPISO | 0000 | MADEPISO | 0000 | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | N/A | N/A | N/A | N/A
10 | CPQ11-ARCH-HMET-DATA-R22.rvt | DATA | S-VALE | 1104 | SPBIM | 1127 | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | SOPHIA | DELIVERED | RESPONSAVEL | 2025-12-17
11 | CPQ11-ARCH-HMET-SITE-R22.rvt | SITE | S-VALE | 1104 | SPBIM | 1127 | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | N/A | 2025-12-10 | RESPONSAVEL | 2025-12-17
12 | CPQ11-ARCH-HM90-DATA-R22.rvt | DATA | ZEUS/PORTEX | 1105 | SPBIM | 1127 | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | LUCAS | DELIVERED | RESPONSAVEL | 2025-12-17
13 | CPQ11-ARCH-WMES-DATA-R22.rvt | DATA | S-VALE | 1104 | SPBIM | 1127 | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | YASMIN | 2025-12-12 | RESPONSAVEL | 2025-12-17
14 | CPQ11-ARCH-CHAI-SITE-R22.rvt | SITE | S-VALE | 1104 | SPBIM | 1127 | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | N/A | 2025-12-10 | RESPONSAVEL | 2025-12-17
15 | CPQ11-ARCH-FURN-DATA-R22.rvt | DATA | RACIONAL | 1106 | CONTRACTING | 0000 | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | N/A | N/A | N/A | N/A
16 | CPQ11-ARCH-WTRP-DATA-R22.rvt | DATA | ITS | 1107 | RBV | 0000 | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | N/A | N/A | N/A | N/A
18 | CPQ11-ARCH-WTRP-SITE-R22.rvt | SITE | ITS | 1107 | RBV | 0000 | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | N/A | N/A | N/A | N/A
19 | CPQ11-ARCH-OHCD-DATA-R22.rvt | DATA | MEGADOORS | 1108 | MEGADOORS | 1108 | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | N/A | N/A | N/A | N/A
20 | CPQ11-ARCH-BLPR-GUAR-R22.rvt | GUAR | INOVAGLASS | 1109 | INOVAGLASS | 1109 | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | N/A | N/A | RESPONSAVEL | N/A
21 | CPQ11-ARCH-FACD-DATA-R22.rvt | DATA | OMNITRADE | 1110 | CADBIM | 1128 | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | ALINNE | DELIVERED | RESPONSAVEL | 2025-12-17
22 | CPQ11-ARCH-ROOF-DATA-R22.rvt | DATA | OMNITRADE | 1110 | CADBIM | 1128 | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | GUI | 2025-12-12 | RESPONSAVEL | 2025-12-17
23 | CPQ11-ARCH-PART-SITE-R22.rvt | SITE | IDEIA DRYWALL | 1101 | FCH | 1126 | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | N/A | 2025-12-10 | RESPONSAVEL | 2025-12-17
24 | CPQ11-ARCH-PART-C345-R22.rvt | C345 | IDEIA DRYWALL | 1101 | FCH | 1126 | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | N/A | NA | RESPONSAVEL | 2025-12-17
25 | CPQ11-ARCH-PART-C12A-R22.rvt | C12A | IDEIA DRYWALL | 1101 | FCH | 1126 | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | ALINNE | 2025-12-12 | RESPONSAVEL | 2025-12-17
26 | CPQ11-ARCH-COMN-DATA-R22.rvt | DATA | CONTRACTING | 0000 | CONTRACTING | 0000 | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | N/A | N/A | N/A | 2025-12-17
27 | CPQ11-ARCH-SGNV-SITE-R22.rvt | SITE | VISUAL GEAC | 0000 | CONTRACTING | 0000 | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | N/A | N/A | N/A | 2025-12-17
28 | CPQ11-ARCH-SGNH-SITE-R22.rvt | SITE | CONTRACTING | 0000 | CONTRACTING | 0000 | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | N/A | N/A | N/A | 2025-12-17
29 | CPQ11-ARCH-CEIL-DATA-R22.rvt | DATA | IDEIA DRYWALL | 1101 | T2B | 0000 | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | N/A | IMPROPER | RESPONSAVEL | 2025-12-17
30 | CPQ11-ARCH-CEIL-SITE-R22.rvt | SITE | IDEIA DRYWALL | 1101 | T2B | 0000 | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | N/A | 2025-12-10 | RESPONSAVEL | 2025-12-17
31 | CPQ11-ARCH-SHLV-DATA-R22.rvt | DATA | ALTAMIRA | 0000 | ALTAMIRA | 0000 | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | IURY | 2025-12-12 | RESPONSAVEL | 2025-12-17
SYST-SYSTEMS ¦ INFRASTRUCTURE
32 | CPQ11-SYST-INFR-DATA-R22.rvt | DATA | MENDES HOLLER | 1112 | PGMAK | 1129 | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | YASMIN | 2025-12-12 | RESPONSAVEL | 2025-12-17
33 | CPQ11-SYST-INFR-SITE-R22.rvt | SITE | MENDES HOLLER | 1112 | PGMAK | 1129 | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | N/A | 2025-12-10 | RESPONSAVEL | 2025-12-17 | APROVADO
DAS-DISTRIBUTED ANTENN/A SYSTEM ¦ DEVICES
34 | CPQ11-DASM-DEVS-DATA-R22.rvt | DATA | IB TECH | 1113 | IB TECH | 1113 | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | SOPHIA | 2025-12-12 | RESPONSAVEL | 2025-12-17
EPMS-ELECTRICAL POWER MAN/AGEMENT SYSTEM ¦ DEVICES
35 | CPQ11-EPMS-DEVS-DATA-R22.rvt | DATA | BLACKBOX | 1114 | BLACKBOX | 1114 | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | LUCAS | DELIVERED | RESPONSAVEL | 2025-12-17
36 | CPQ11-EPMS-DEVS-SITE-R22.rvt | SITE | BLACKBOX | 1114 | BLACKBOX | 1114 | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | N/A | 2025-12-10 | RESPONSAVEL | 2025-12-17
ROIP-RADIO OVER IP ¦ DEVICES
37 | CPQ11-ROIP-DEVS-GUAR-R22.rvt | GUAR | IB TECH | 1113 | IB TECH | 1113 | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | N/A | 2025-12-10 | RESPONSAVEL | 2025-12-17
38 | CPQ11-ROIP-DEVS-DATA-R22.rvt | DATA | IB TECH | 1113 | IB TECH | 1113 | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | YASMIN | 2025-12-12 | RESPONSAVEL | 2025-12-17
TELECOM ¦ DEVICES
39 | CPQ11-TCOM-DEVS-SITE-R22.rvt | SITE | BLACKBOX | 1114 | BLACKBOX | 1114 | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | N/A | 2025-12-10 | RESPONSAVEL | 2025-12-17
40 | CPQ11-TCOM-DEVS-DATA-R22.rvt | DATA | BLACKBOX | 1114 | BLACKBOX | 1114 | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | SOPHIA | 2025-12-12 | RESPONSAVEL | 2025-12-17
BAS-BUILDING AUTOMATION SYSTEM ¦ INFRASTRUCTURE
41 | CPQ11-BASM-INFR-DATA-R22.rvt | DATA | MENDES HOLLER | 1112 | PGMAK | 1129 | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | ALINNE | ANALYSING | RESPONSAVEL | 2025-12-17
42 | CPQ11-BASM-INFR-PUMP-R22.rvt | PUMP | MENDES HOLLER | 1112 | PGMAK | 1129 | NOT PUBLISHED | NOT PUBLISHED | CLARISSA | N/A | N/A | 2025-12-10 | RESPONSAVEL | 2025-12-17
BAS ¦ DEVICES
43 | CPQ11-BASM-DEVS-PUMP-R22.rvt | PUMP | BLACKBOX | 1114 | BLACKBOX | 1114 | NOT PUBLISHED | NOT PUBLISHED | CLARISSA | N/A | N/A | 2025-12-10 | RESPONSAVEL | 2025-12-17
44 | CPQ11-BASM-DEVS-DATA-R22.rvt | DATA | BLACKBOX | 1114 | BLACKBOX | 1114 | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | GUI | 2025-12-12 | RESPONSAVEL | 2025-12-17
SCTY-SECURITY ¦ INFRASTRUCTURE
45 | CPQ11-SCTY-INFR-DATA-R22.rvt | DATA | MENDES HOLLER | 1112 | PGMAK | 1129 | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | LUCAS | 2025-12-12 | RESPONSAVEL | 2025-12-17
46 | CPQ11-SCTY-INFR-SITE-R22.rvt | SITE | MENDES HOLLER | 1112 | PGMAK | 1129 | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | N/A | 2025-12-10 | RESPONSAVEL | 2025-12-17
SCTY ¦ DEVICES
47 | CPQ11-SCTY-DEVS-SITE-R22.rvt | SITE | SEGURPRO | 1115 | SEGURPRO | 1115 | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | N/A | 2025-12-10 | RESPONSAVEL | 2025-12-17
48 | CPQ11-SCTY-DEVS-DATA-R22.rvt | DATA | SEGURPRO | 1115 | SEGURPRO | 1115 | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | ALINNE | 2025-12-12 | RESPONSAVEL | 2025-12-17
ELEC-ELETRICAL
49 | CPQ11-ELEC-ELEC-SITE-R22.rvt | SITE | MENDES HOLLER | 1112 | PGMAK | 1129 | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | N/A | 2025-12-10 | RESPONSAVEL | 2025-12-17
50 | CPQ11-ELEC-ELEC-DATA-R22.rvt | DATA | MENDES HOLLER | 1112 | PGMAK | 1129 | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | YASMIN | 2025-12-12 | RESPONSAVEL | 2025-12-17
SPDA ¦ PROTECTION SYSTEM ATMOSPHERIC DISCHARGE
51 | CPQ11-ELEC-SPDA-DATA-R22.rvt | DATA | MENDES HOLLER | 1112 | MENDES HOLLER | 1112 | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | SOPHIA | 2025-12-12 | RESPONSAVEL | 2025-12-17
52 | CPQ11-ELEC-SPDA-SITE-R22.rvt | SITE | MENDES HOLLER | 1112 | MENDES HOLLER | 1112 | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | N/A | 2025-12-10 | RESPONSAVEL | 2025-12-17
DALI-DIGITAL ADDRESSABLE LIGHTING INTERFACE-DEVICES
53 | CPQ11-DALI-DEVS-DATA-R22.rvt | DATA | AUTOBRÁS | 1116 | AUTOBRÁS | 1116 | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | GUI | 2025-12-12 | RESPONSAVEL | 2025-12-17
FALM-FIRE ALARM
54 | CPQ11-FALM-FALM-SITE-R22.rvt | SITE | MENDES HOLLER | 1112 | MENDES HOLLER | 1112 | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | N/A | 2025-12-10 | RESPONSAVEL | 2025-12-17 | APROVADO
55 | CPQ11-FALM-FALM-DATA-R22.rvt | DATA | MENDES HOLLER | 1112 | MENDES HOLLER | 1112 | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | YASMIN | 2025-12-12 | RESPONSAVEL | 2025-12-17
FPRT-FIRE PROTECTION
56 | CPQ11-FPRT-FPRT-SITE-R22.rvt | SITE | MENDES HOLLER | 1112 | MENDES HOLLER | 1112 | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | N/A | 2025-12-10 | RESPONSAVEL | 2025-12-17
57 | CPQ11-FPRT-FPRT-DATA-R22.rvt | DATA | MENDES HOLLER | 1112 | MENDES HOLLER | 1112 | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | LUCAS | 2025-12-12 | RESPONSAVEL | 2025-12-17 | v8 - 09/12/2025
58 | CPQ11-FPRT-METK-UTLS-R22.rvt | UTLS | PETROTANQUE | 1117 | CADBIM | 1128 | NOT PUBLISHED | NOT PUBLISHED | CLARISSA | N/A | N/A | 2025-12-10 | N/A | 2025-12-17
PLMB-PLUMBING
59 | CPQ11-PLMB-PLMB-SITE-R22.rvt | SITE | MENDES HOLLER | 1112 | PGMAK | 1129 | NOT PUBLISHED | NOT PUBLISHED | CLARISSA | N/A | N/A | 2025-12-10 | RESPONSAVEL | 2025-12-17
60 | CPQ11-PLMB-PLMB-DATA-R22.rvt | DATA | MENDES HOLLER | 1112 | PGMAK | 1129 | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | ALINNE | 2025-12-12 | RESPONSAVEL | 2025-12-17
61 | CPQ11-PLMB-DIES-SITE-R22.rvt | SITE | MENDES HOLLER | 1112 | MENDES HOLLER | 1112 | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | N/A | 2025-12-10 | RESPONSAVEL | 2025-12-17
62 | CPQ11-PLMB-NPWT-SITE-R22.rvt | SITE | STARCENTER | 1118 | STARCENTER | 1118 | NOT PUBLISHED | NOT PUBLISHED | CLARISSA | N/A | N/A | 2025-12-10 | RESPONSAVEL | 2025-12-17
63 | CPQ11-PLMB-NPWT-DATA-R22.rvt | DATA | STARCENTER | 1118 | STARCENTER | 1118 | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | GUI | 2025-12-12 | RESPONSAVEL | 2025-12-17
64 | CPQ11-PLMB-METK-UTLS-R22.rvt | UTLS | STARCENTER | 1118 | STARCENTER | 1118 | NOT PUBLISHED | NOT PUBLISHED | CLARISSA | N/A | N/A | 2025-12-10 | N/A | 2025-12-17
MECH-MECHANICAL
65 | CPQ11-MECH-MECH-DATA-R22.rvt | DATA | STARCENTER | 1118 | STARCENTER | 1118 | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | ALINNE | 2025-12-12 | RESPONSAVEL | 2025-12-17
66 | CPQ11-MECH-MECH-GUAR-R22.rvt | GUAR | STARCENTER | 1118 | STARCENTER | 1118 | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | N/A | 2025-12-10 | RESPONSAVEL | 2025-12-17
LAND-LANDSCAPE
67 | CPQ11-LAND-LAND-SITE-R22.rvt | SITE | ORGANISMO VIVO | 0000 | CONTRACTING | 0000 | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | N/A | N/A | N/A | N/A
CIVIL
68 | CPQ11-CIVL-DRNG-SITE-R22.rvt | SITE | GARCIA | 1119 | CADBIM | 1128 | NOT PUBLISHED | NOT PUBLISHED | CLARISSA | N/A | N/A | 2025-12-10 | RESPONSAVEL | 2025-12-17
69 | CPQ11-CIVL-ERTH-SITE-R22.rvt | SITE | GARCIA | 1119 | CADBIM | 1128 | NOT PUBLISHED | NOT PUBLISHED | CLARISSA | N/A | N/A | 2025-12-10 | RESPONSAVEL | 2025-12-17 | APROVADO
70 | CPQ11-CIVL-PAVM-SITE-R22.rvt | SITE | GARCIA | 1119 | CADBIM | 1128 | NOT PUBLISHED | NOT PUBLISHED | CLARISSA | N/A | N/A | 2025-12-10 | RESPONSAVEL | 2025-12-17 | APROVADO
71 | CPQ11-CIVL-SIGN-SITE-R22.rvt | SITE | CONTRACTING | 0000 | CONTRACTING | 0000 | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | N/A | N/A | N/A | N/A
72 | CPQ11-CIVL-LOCK-SITE-R22.rvt | SITE | STEINER | 0000 | PMD | 0000 | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | N/A | 2025-12-10 | RESPONSAVEL | 2025-12-17
STRC-STRUCTURE
73 | CPQ11-STRC-CONC-DATA-R22.rvt | DATA | SERV OBRAS | 1120 | TENAX | 0000 | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | LUCAS | 2025-12-12 | RESPONSAVEL | 2025-12-17
74 | CPQ11-STRC-CONC-SITE-R22.rvt | SITE | SERV OBRAS | 1120 | TENAX | 0000 | NOT PUBLISHED | NOT PUBLISHED | CLARISSA | N/A | N/A | 2025-12-10 | RESPONSAVEL | 2025-12-17
75 | CPQ11-STRC-DPFN-DATA-R22.rvt | DATA | GEOFIX/TECNOGEO | 0000 | TENAX | 0000 | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | GUI | 2025-12-12 | RESPONSAVEL | 2025-12-17
76 | CPQ11-STRC-DPFN-SITE-R22.rvt | SITE | GEOFIX/TECNOGEO | 0000 | TENAX | 0000 | NOT PUBLISHED | NOT PUBLISHED | CLARISSA | N/A | N/A | 2025-12-10 | RESPONSAVEL | 2025-12-17 | APROVADO
77 | CPQ11-STRC-FLOO-DATA-R22.rvt | DATA | FERNANDES | 1121 | RBV | 0000 | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | N/A | N/A | N/A | N/A
78 | CPQ11-STRC-FLOO-SITE-R22.rvt | SITE | FERNANDES | 1121 | RBV | 0000 | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | N/A | N/A | N/A | N/A
79 | CPQ11-STRC-DPF1-SITE-R22.rvt | SITE | GEOFIX | 1122 | TENAX | 0000 | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | N/A | N/A | N/A | N/A
80 | CPQ11-STRC-DPF1-DATA-R22.rvt | DATA | GEOFIX | 1122 | TENAX | 0000 | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | N/A | N/A | N/A | N/A
81 | CPQ11-STRC-DPF2-SITE-R22.rvt | SITE | TECNOGEO | 1123 | TENAX | 0000 | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | N/A | N/A | N/A | N/A
82 | CPQ11-STRC-DPF2-DATA-R22.rvt | DATA | TECNOGEO | 1123 | TENAX | 0000 | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | N/A | N/A | N/A | N/A
83 | CPQ11-STRC-CHAI-SITE-R22.rvt | SITE | S-VALE | 1104 | SPBIM | 1127 | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | N/A | N/A | N/A | N/A
84 | CPQ11-STRC-FENC-SITE-R22.rvt | SITE | SERCOP, SERV OBRAS | 1124 | CONTRACTING | 0000 | NOT PUBLISHED | NOT PUBLISHED | N/A | N/A | N/A | N/A | N/A | N/A
85 | CPQ11-STRC-STEE-ADMN-2X3.ifc | ADMN | METASA | 1125 | METASA | 1125 | V1 | 21/05/2026 | N/A | N/A | SOPHIA | 2025-12-12 | N/A | 2025-12-17
86 | CPQ11-STRC-STEE-COL1-2X3.ifc | COL1 | METASA | 1125 | METASA | 1125 | V1 | 21/05/2026 | N/A | N/A | N/A | N/A | RESPONSAVEL | 2025-12-17
87 | CPQ11-STRC-STEE-COL2-2X3.ifc | COL2 | METASA | 1125 | METASA | 1125 | V1 | 21/05/2026 | N/A | N/A | N/A | N/A | RESPONSAVEL | 2025-12-17
88 | CPQ11-STRC-STEE-COL3-2X3.ifc | COL3 | METASA | 1125 | METASA | 1125 | V1 | 21/05/2026 | N/A | N/A | N/A | N/A | RESPONSAVEL | 2025-12-17
89 | CPQ11-STRC-STEE-COL4-2X3.ifc | COL4 | METASA | 1125 | METASA | 1125 | V1 | 21/05/2026 | N/A | N/A | N/A | N/A | RESPONSAVEL | 2025-12-17
90 | CPQ11-STRC-STEE-COL5-2X3.ifc | COL5 | METASA | 1125 | METASA | 1125 | V1 | 21/05/2026 | N/A | N/A | N/A | N/A | RESPONSAVEL | 2025-12-17
91 | CPQ11-STRC-STEE-UTLS-2X3.ifc | UTLS | METASA | 1125 | METASA | 1125 | V1 | 21/05/2026 | N/A | N/A | N/A | 2025-12-10 | RESPONSAVEL | 2025-12-17 | APROVADO
92 | CPQ11-STRC-STEE-GUAR-2X3.ifc | GUAR | METASA | 1125 | METASA | 1125 | V1 | 21/05/2026 | N/A | N/A | N/A | 2025-12-10 | RESPONSAVEL | 2025-12-17
93 | CPQ11-STRC-STEE-STIR-2X3.ifc | STIR | METASA | 1125 | METASA | 1125 | V1 | 21/05/2026 | N/A | N/A | N/A | 2025-12-10 | RESPONSAVEL | 2025-12-17 | APROVADO
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113

## CRONOGRAMA
CPQ11 ¦ TIMELINE DECEMBER 2025- JANUARY 2026
|  |  | 2025-12-01 | [23 empty] | 2026-01-01 | [30 empty] | 2026-02-01 | [30 empty] | março | [29 empty] | abril
|  |  | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
| 4D E GERAL | MODELADORES | 2025-12-01 9: FIM; 2026-02-01 10: FIM; 2026-02-01 20: FIM
|  | SPBIM | 2025-12-01 9: FIM; 2025-12-01 15: AUDIT; 2025-12-01 19: FIM; 2026-01-01 12: AUDIT T1 E T2; 2026-01-01 20: FIM; 2026-01-01 21: AUDIT T1 E T2; 2026-01-01 30: FIM; 2026-02-01 10: FIM; 2026-02-01 20: FIM; 2026-02-01 27: FIM
UTILITIES, GUARDHOUSE, ADMIN, COLO 1 | LOD 300 | MODELADORES | 2025-12-01 9: FIM; 2026-02-01 10: FIM; 2026-02-01 20: FIM; março 10: FIM; março 20: FIM; março 31: FIM
|  | SPBIM | 2025-12-01 9: FIM; 2025-12-01 18: AUDIT; 2025-12-01 30: FIM; 2026-01-01 2: AUDIT; 2026-01-01 9: FIM; 2026-01-01 12: AUDIT T1 E T2; 2026-01-01 20: FIM; 2026-01-01 21: AUDIT T1 E T2; 2026-01-01 30: FIM; 2026-02-01 10: FIM; 2026-02-01 20: FIM; 2026-02-01 27: FIM; 2026-02-01 2: INÍCIO COL 3 E 4; março 10: FIM; março 11: COL 3 E 4; março 16: COL 3 E 4; março 20: FIM; março 23: COL 3 E 4; março 31: FIM
| LOD 400 | MODELADORES | 2025-12-01 9: FIM; 2026-02-01 10: FIM; 2026-02-01 20: FIM; março 10: FIM; março 20: FIM; março 31: FIM
|  | SPBIM | 2025-12-01 9: FIM; 2025-12-01 18: AUDIT; 2025-12-01 30: FIM; 2026-01-01 2: AUDIT; 2026-01-01 9: FIM; 2026-01-01 12: AUDIT T1 E T2; 2026-01-01 20: FIM; 2026-01-01 21: AUDIT T1 E T2; 2026-01-01 30: FIM; 2026-02-01 10: FIM; 2026-02-01 20: FIM; 2026-02-01 27: FIM; 2026-02-01 2: INÍCIO COL 3 E 4; março 10: FIM; março 11: COL 3 E 4; março 16: COL 3 E 4; março 20: FIM; março 23: COL 3 E 4; março 31: FIM
| LOD 500 | MODELADORES | 2025-12-01 10: ROUND 1; 2025-12-01 19: FIM; 2025-12-01 22: ROUND 2; 2026-01-01 2: FIM; 2026-01-01 5: ROUND 3; 2026-01-01 9: FIM; 2026-01-01 19: ROUND FINAL; 2026-01-01 30: FIM; 2026-02-01 10: FIM; 2026-02-01 20: FIM; 2026-02-01 27: FIM; março 10: FIM; março 20: FIM
|  | SPBIM | 2025-12-01 8: ROUND 0; 2026-01-01 7: FIM; 2026-01-01 8: AUDIT T1; 2026-01-01 23: FIM; 2026-01-01 30: FIM; 2026-02-01 10: FIM; 2026-02-01 20: FIM; 2026-02-01 27: FIM; março 10: FIM; março 20: FIM; março 31: FIM
data final do final - caso atrasem
4d, geral, 300 e 400 - atualizar modelos até dia 20/02
[70 empty] | GUARD | [5 empty] | T1 = COLO 1, ADM, ANEXOS
[70 empty] | UTLS | [5 empty] | T2= COLO 2, SITE
SITE
ADM
COL1
COL2
Note on BH12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: ADMN E COLO1= ROUND 3 COLO2 E SITE= ROUND 0 GUAR= ROUND 3 UTLS= ROUND 5
Note on BQ12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: ADMN E COLO1= ROUND 4 COLO2 E SITE= ROUND 0 GUAR= ROUND 4 UTLS= ROUND 6
Note on CC12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: ADMN E COLO1= ROUND 5 COLO2 E SITE= ROUND 1 GUAR= ROUND 5 UTLS= ROUND 7
Note on CJ12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: ADMN E COLO1= ROUND 6 COLO2 E SITE= ROUND 2 GUAR= ROUND 6 UTLS= ROUND 8
Note on CS12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: ADMN E COLO1= ROUND 7 COLO2 E SITE= ROUND 3 GUAR= ROUND 7 UTLS= ROUND 9
Note on DE12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: ADMN E COLO1= ROUND 8 COLO2 E SITE= ROUND 4 GUAR= ROUND 8 UTLS= ROUND 10